## Sheet9
Count of Job OPEN | Total Jobs
361 | 361

## DASHBOARD
SAI FILE NO | Job OPEN | Contract # | Building | School Name | WA # | Alias_WA | Service ID | Project Type | Primary Hygienist | Alias_Hygienist | Service Name | WA Type | WA Status | Initiation Date (WA) | Column2 | Estimated Cost (WA) | Actual Start Date (RFP) | Actual Date of Completion (RFP) | Days to Complete | Days from Initial to Start DT | RFP No | Date of RFP | Amount Invoiced (RFP) | Cost Variance | Amount Received | Amount Outstanding | CHECK NO. | DATE ON CHECK | PAID / UNPAID | NOTES
17SD-136 | OPEN | C000013440 | M470 | LOUIS D. BRANDEIS HS - MANHATTAN | 888431 | xxxx431 | 68127 | CIP | Langlois, Bret | Hygienist 01 | LAP Design Review & Specification | Amendment | Closed | 2017-11-07 | 2017-11-07 | 3575 | 2017-11-19 | 2018-01-26 | 68 | 12 | 230 | 2019-06-10 | 7470.5 | 3895.5 | 0 | -7470.5 |  |  | UNPAID
19S-261 | OPEN | C000015128 | K011 | P.S. 11 - BROOKLYN | 999593 | xxxx593 | 74734 | CIP | Walsh, Joseph | Hygienist 02 | LAP Construction Phase Services | RFA | Closed | 2019-11-14 | 2019-11-14 | 22300 | 2020-02-08 | 2022-07-22 | 895 | 86 | 4200 | 2024-03-27 | 43264.55 | 20964.55 | 43264.55 | 0 | 819088 | 2024-05-02 | PAID
21S-102 | OPEN | C000015128 | K061 | I.S. 61 - BROOKLYN | 1096267 | xxxx267 | 83439 | CIP | Palermo, Albert | Hygienist 03 | LAP Construction Phase Services | RFA | Closed | 2021-11-01 | 2021-11-01 | 500 | 2022-01-23 | 2022-12-15 | 326 | 83 | 4196 | 2023-10-25 | 20190.01 | 19690.01 | 20190.01 | 0 | 813482 | 2024-08-24 | PAID
19S-010 | OPEN | C000015128 | K110 | P.S. 110 - BROOKLYN | 967469 | xxxx469 | 72073 | CIP | Towers, Daniel | Hygienist 04 | PO 18 Asbestos Service | RFA | Closed | 2019-04-11 | 2019-04-11 | 500 | 2020-07-23 | 2020-08-02 | 10 | 469 | 4184 | 2023-07-20 | 18196.52 | 17696.52 | 18196.52 | 0 | 800185 | 2023-07-25 | PAID
22S-083 | OPEN | C000015128 | K163 | P.S. 163 - BROOKLYN | 1062263 | xxxx263 | 81072 | CIP | Scott, Richard | Hygienist 05 | LAP Construction Phase Services | Initial | WIP | 2021-02-12 | 2021-02-12 | 3500 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
21S-100 | OPEN | C000015128 | K186 | P.S. 186 - BROOKLYN | 1097498 | xxxx498 | 82916 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Amendment | WIP | 2021-11-05 | 2021-11-05 | 10700 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
19S-001 | OPEN | C000015128 | K480 | BUSHWICK EDUCATIONAL CAMPUS - BROOKLYN | 958748 | xxxx748 | 68455 | CIP | Walsh, Joseph | Hygienist 02 | LAP Construction Phase Services | RFA | WIP | 2018-01-16 | 2018-01-16 | 93000 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
19SD- | OPEN | C000015128 | K540 | JOHN DEWEY HS - BROOKLYN | 992170 | xxxx170 | 74401 | CIP | Kordes, Kristin | Hygienist 06 | LAP Design Review & Specification | Amendment | WIP | 2019-10-08 | 2019-10-08 | 1750 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
21S-026 | OPEN | C000015128 | M015 | P.S. 15 - MANHATTAN | 1067993 | xxxx993 | 81283 | CIP | Lazicki, Rafal | Hygienist 07 | LAP Construction Phase Services | RFA | Closed | 2021-03-17 | 2021-03-17 | 28500 | 2021-06-03 | 2022-09-07 | 461 | 78 | 4201 | 2024-04-01 | 167322.32 | 138822.32 | 167322.32 | 0 | 817916 | 2024-04-17 | PAID
20S-064 | OPEN | C000015128 | M110 | P.S. 110 - MANHATTAN | 1053130 | xxxx130 | 80200 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | RFA | Closed | 2020-11-13 | 2020-11-13 | 6000 | 2020-11-13 | 2020-11-14 | 1 | 0 | 4205 | 2024-04-05 | 4097.91 | -1902.09 | 4097.91 | 0 | 848655 | 2025-04-15 | PAID
19S-276 | OPEN | C000015128 | M165 | P.S. 165 - MANHATTAN | 1002890 | xxxx890 | 74984 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | RFA | Closed | 0 | 0 | 500 | 2020-01-16 | 2022-05-18 | 853 | 43846 | 4180 | 2023-06-15 | 2003.42 | 1503.42 | 2003.42 | 0 | 799179 | 2023-07-11 | PAID
19S-273 | OPEN | C000015128 | M620 | NORMAN THOMAS HS (ECF) - MANHATTAN | 983314 | xxxx314 | 73197 | CIP | Lazicki, Rafal | Hygienist 07 | LAP Construction Phase Services | RFA | Closed | 2019-08-09 | 2019-08-09 | 5500 | 2019-12-18 | 2021-10-30 | 682 | 131 | 4179 | 2023-06-06 | 11228.81 | 5728.81 | 11228.81 | 0 | 798708 | 2023-07-03 | PAID
21S-059 | OPEN | C000015128 | Q021 | P.S. 21 - QUEENS | 1081024 | xxxx024 | 82138 | CIP | Kondilis, Milton | Hygienist 08 | LAP Construction Phase Services | RFA | Closed | 2021-06-29 | 2021-06-29 | 27000 | 2021-08-30 | 2023-08-10 | 710 | 62 | 4198 | 2023-11-08 | 40541.88 | 13541.88 | 40541.88 | 0 | 811654 | 2024-01-11 | PAID
23S-091 | OPEN | C000015128 | Q041 | P.S. 41 - QUEENS | 1199787 | xxxx787 | 89442 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-10-06 | 2023-10-06 | 7700 | 2023-10-07 | 2023-10-08 | 1 | 1 | 69 | 2024-03-29 | 3864.83 | -3835.17 | 3864.83 | 0 | 820024 | 2024-05-13 | PAID
21S-037 | OPEN | C000015128 | Q060 | P.S. 60 - QUEENS | 1071623 | xxxx623 | 81514 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Amendment | Closed | 2021-04-22 | 2021-04-22 | 500 | 2021-05-13 | 2021-05-16 | 3 | 21 | 4183 | 2023-07-14 | 5286.62 | 4786.62 | 5286.62 | 0 | 800186 | 2023-07-25 | PAID
21S-106 | OPEN | C000015128 | Q081 | P.S. 81 - QUEENS | 1098684 | xxxx684 | 83571 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2021-11-16 | 2021-11-16 | 500 | 2023-08-01 | 2023-08-01 | 0 | 623 | 4188 | 2023-08-01 | 500 | 0 | 500 | 0 | 800966 | 2020-08-04 | PAID
24S-077 | OPEN | C000015128 | Q089 | P.S. 89 - QUEENS | 1302817 | xxxx817 | 91977 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | NEW | 2024-08-09 | 2024-08-09 | 575 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
19S-002 | OPEN | C000015128 | Q094 | P.S. 94 - QUEENS | 962451 | xxxx451 | 71734 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2019-03-15 | 2019-03-15 | 500 | 2019-03-20 | 2020-08-17 | 516 | 5 | 4185 | 2023-07-20 | 12150.12 | 11650.12 | 12150.12 | 0 | 804162 | 2023-09-22 | PAID
21S-057 | OPEN | C000015128 | Q192 | I.S. 192 - QUEENS | 1080851 | xxxx851 | 82009 | CIP | Zarrabi, Abdi | Hygienist 10 | PO 18 Asbestos Service | RFA | Closed | 2021-06-22 | 2021-06-22 |  | 2021-10-28 | 2022-04-19 | 173 | 128 | 4155 | 2022-09-01 | 30791.17 | 30791.17 | 30791.17 | 0 | 798794 | 2023-07-05 | PAID
21S-019 | OPEN | C000015128 | Q192 | I.S. 192 - QUEENS | 1065824 | xxxx824 | 81133 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | RFA | Closed | 2021-03-02 | 2021-03-02 | 900 | 2021-04-15 | 2021-04-15 | 0 | 44 | 4203 | 2024-04-04 | 1226.11 | 326.11 | 1226.11 | 0 | 819962 | 2024-05-13 | PAID
21S-070 | OPEN | C000015128 | Q216 | J.H.S. 216 - QUEENS | 1084164 | xxxx164 | 82491 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | RFA | Closed | 2021-08-03 | 2021-08-03 | 500 | 2021-12-02 | 2022-04-03 | 122 | 121 | 4187 | 2023-07-31 | 14987.36 | 14487.36 | 14987.36 | 0 | 803144 | 2023-09-08 | PAID
20S-052 | OPEN | C000015128 | Q450 | NEWCOMERS HIGH SCHOOL (OLD LIC) - QUEENS | 1048150 | xxxx150 | 80036 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2020-10-22 | 2020-10-22 | 500 | 2020-10-22 | 2020-10-25 | 3 | 0 | 4189 | 2023-08-01 | 8330.37 | 7830.37 | 8330.37 | 0 | 801177 | 2023-08-08 | PAID
19S-280 | OPEN | C000015128 | X040 | P.S. 40 - QUEENS | 1006948 | xxxx948 | 75115 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2019-12-27 | 2019-12-27 | 500 | 2019-12-27 | 2019-12-30 | 3 | 0 | 4191 | 2023-09-29 | 7569.4 | 7069.4 | 7569.4 | 0 | 808702 | 2023-11-27 | PAID
21S-056 | OPEN | C000015128 | X050 | P.S. 50 - BRONX | 1080758 | xxxx758 | 82026 | CIP | Kowalski, Zbigniew | Hygienist 12 | LAP Construction Phase Services | RFA | Closed | 2021-06-21 | 2021-06-21 | 2900 | 2022-02-04 | 2022-04-02 | 57 | 228 | 4181 | 2023-06-28 | 7742.94 | 4842.94 | 7742.94 | 0 | 799844 | 2023-07-19 | PAID
19S-281 | OPEN | C000015128 | X062 | P.S. 62 - BRONX | 1003970 | xxxx970 | 75093 | CIP | Zarrabi, Abdi | Hygienist 10 | PO 18 Asbestos Service | RFA | Closed | 2019-12-27 | 2019-12-27 | 500 | 2020-08-11 | 2020-08-19 | 8 | 228 | 4190 | 2023-09-06 | 22411.43 | 21911.43 | 22411.43 | 0 | 805306 | 2023-10-06 | PAID
20S-063 | OPEN | C000015128 | X066 | P.S. 66 - BRONX | 1052226 | xxxx226 | 80086 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Amendment | Closed | 2020-11-23 | 2020-11-23 | 500 | 2021-01-01 | 2021-01-16 | 15 | 39 | 4204 | 2024-04-05 | 18887.1 | 18387.1 | 18887.1 | 0 | 821670 | 2024-05-29 | PAID
20S-019 | OPEN | C000015128 | X074 | I.S. 201 - BRONX | 1034251 | xxxx251 | 77151 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2020-06-25 | 2020-06-25 | 250 | 2020-06-25 | 2020-06-29 | 4 | 0 | 4197 | 2023-10-31 | 11356.93 | 11106.93 | 11356.93 | 0 | 813195 | 2024-02-02 | PAID
21S-107 | OPEN | C000015128 | X132 | P.S. 132 - BRONX | 1099356 | xxxx356 | 82902 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Amendment | Closed | 2021-11-19 | 2021-11-19 |  | 2023-07-19 | 2023-07-21 | 2 | 607 | 4199 | 2024-02-01 | 5354.41 | 5354.41 | 5354.41 | 0 | 826308 | 2024-07-30 | PAID
21S-109 | OPEN | C000015128 | X151 | I.S. 151 - BRONX | 1097816 | xxxx816 | 83513 | CIP | Alawamleh, Eman | Hygienist 11 | LAP Construction Phase Services | RFA | Closed | 2022-01-27 | 2022-01-27 | 500 | 2022-01-27 | 2022-10-10 | 256 | 0 | 4176 | 2022-12-27 | 15437.96 | 14937.96 | 15437.96 | 0 | 798123 | 2023-06-22 | PAID
21S-105 | OPEN | C000015128 | X405 | HERBERT H. LEHMAN HS - BRONX | 1098818 | xxxx818 | 83582 | CIP | Alawamleh, Eman | Hygienist 11 | LAP Construction Phase Services | Initial | WIP | 2021-11-16 | 2021-11-16 | 500 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
| Not Started | C000015869 | K014 | I.S. 14 - BROOKLYN | 1129904 | xxxx904 | 85451 | CIP | Clyne, Sean | Hygienist 13 | LAP Construction Phase Services | Initial | WIP | 2022-07-12 | 2022-07-12 | 9700 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
22S-057 | OPEN | C000015869 | K016 | P.S. 16 - BROOKLYN | 1141526 | xxxx526 | 86136 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | Closed | 2022-09-12 | 2022-09-12 | 575 | 2022-11-03 | 2022-11-12 | 9 | 52 | 43 | 2023-10-11 | 17026.88 | 16451.88 | 17026.88 | 0 | 806701 | 2023-10-25 | PAID
24S-012 | OPEN | C000015869 | K017 | P.S. 17 - BROOKLYN | 1218759 | xxxx759 | 90624 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | NEW | 2024-02-08 | 2024-02-08 | 575 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
23S-093 | OPEN | C000015869 | K019 | P.S. 19 - BROOKLYN | 1196510 | xxxx510 | 89478 | CIP | Walsh, Joseph | Hygienist 02 | LAP Construction Phase Services | Initial | Closed | 2023-09-22 | 2023-09-22 | 90000 | 2023-10-06 | 2024-07-26 | 294 | 14 | 163 | 2025-05-12 | 70574.1 | -19425.9 | 0 | -70574.1 |  |  | UNPAID
24S-108 | OPEN | C000015869 | K027 | P.S. 27 - BROOKLYN | 1314173 | xxxx173 | 93452 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-09-30 | 2024-09-30 | 4000 | 2024-11-22 | 2024-11-23 | 1 | 53 | 245 | 2025-07-28 | 3552.53 | -447.47 | 0 | -3552.53 |  |  | UNPAID
| Not Started | C000015869 | K043 | I.S. 98 - BROOKLYN | 1320962 | xxxx962 | 93925 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | NEW | 2024-11-13 | 2024-11-13 | 4100 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
24S-004 | OPEN | C000015869 | K050 | J.H.S. 50 - BROOKLYN | 1219382 | xxxx382 | 90587 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-02-16 | 2024-02-16 | 18700 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
22S-075 | OPEN | C000015869 | K051 | I.S. 51 - BROOKLYN | 1154680 | xxxx680 | 86753 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | Closed | 2022-12-05 | 2022-12-05 | 575 | 2023-07-14 | 2023-07-21 | 7 | 221 | 197 | 2025-06-16 | 12748.05 | 12173.05 | 0 | -12748.05 |  |  | UNPAID
24S-072 | OPEN | C000015869 | K051 | I.S. 51 - BROOKLYN | 1302806 | xxxx806 | 92774 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-08-04 | 2024-08-04 | 4000 | 2024-08-20 | 2024-08-21 | 1 | 16 | 156 | 2025-05-06 | 2236.93 | -1763.07 | 2236.93 | 0 | 854005 | 2025-06-12 | PAID | CHECK 24S-072 K051
23S-016 | OPEN | C000015869 | K054 | P.S. 54 - BROOKLYN | 1166957 | xxxx957 | 87386 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | Closed | 2023-02-10 | 2023-02-10 | 575 | 2023-03-23 | 2023-03-25 | 2 | 41 | 28 | 2023-07-11 | 6616.23 | 6041.23 | 6616.23 | 0 | 799845 | 2023-07-19 | PAID
22S-055 | OPEN | C000015869 | K055 | I.S. 55 - BROOKLYN | 1138365 | xxxx365 | 86018 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | RFA | Closed | 2022-09-06 | 2022-09-06 | 19775 | 2022-09-20 | 2022-11-13 | 54 | 14 | 15 | 2022-06-21 | 27095.76 | 7320.76 | 27095.76 | 0 | 807815 | 2023-11-09 | PAID
22S-027 | OPEN | C000015869 | K055 | I.S. 55 - BROOKLYN | 1130690 | xxxx690 | 85488 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2022-07-07 | 2022-07-07 | 6075 | 2022-08-11 | 2022-08-14 | 3 | 35 | 80 | 2024-07-17 | 7902.2 | 1827.2 | 7902.2 | 0 | 831865 | 2024-10-04 | PAID
23S-134 | OPEN | C000015869 | K055 | I.S. 55 - BROOKLYN | 1208358 | xxxx358 | 89203 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2023-12-05 | 2023-12-05 | 21075 | 2024-04-04 | 2024-04-20 | 16 | 121 | 239 | 2025-07-24 | 25778.76 | 4703.76 | 0 | -25778.76 |  |  | UNPAID
24S-090 | OPEN | C000015869 | K061 | I.S. 61 - BROOKLYN | 1310278 | xxxx278 | 93260 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2024-09-06 | 2024-09-06 | 5575 | 2024-09-07 | 2024-09-07 | 0 | 1 | 213 | 2025-06-24 | 2905.59 | -2669.41 | 0 | -2905.59 |  |  | UNPAID
23S-133 | OPEN | C000015869 | K061 | I.S. 61 - BROOKLYN | 1211600 | xxxx600 | 90221 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2023-12-27 | 2023-12-27 | 575 | 2024-01-12 | 2024-01-13 | 1 | 16 | 78 | 2024-04-22 | 2731 | 2156 | 2731 | 0 | 824707 | 2024-07-09 | PAID
24S-068 | OPEN | C000015869 | K085 | P.S. 73 (OLD P85/STERLING HS) | 1301194 | xxxx194 | 92638 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-07-24 | 2024-07-24 | 4000 | 2024-08-01 | 2024-08-02 | 1 | 8 | 185 | 2025-06-05 | 2123.08 | -1876.92 | 0 | -2123.08 |  |  | UNPAID
23S-017 | OPEN | C000015869 | K086 | P.S. 86 - BROOKLYN | 1168027 | xxxx027 | 87459 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | WIP | 2023-02-22 | 2023-02-22 | 575 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
24S-063 | OPEN | C000015869 | K095 | P.S. 95 - BROOKLYN | 1300411 | xxxx411 | 92557 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-07-21 | 2024-07-21 | 4000 | 2024-08-24 | 2024-10-13 | 50 | 34 | 154 | 2025-05-06 | 3574.99 | -425.01 | 3574.99 | 0 | 854006 | 2025-06-12 | PAID | CHECK 24S-063 K095
| Not Started | C000015869 | K102 | P.S. 102 - BROOKLYN | 1306782 | xxxx782 | 92043 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | NEW | 2024-08-29 | 2024-08-29 | 575 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
24S-038 | OPEN | C000015869 | K104 | P.S. 104 - BROOKLYN | 1237242 | xxxx242 | 91880 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | NEW | 2024-05-23 | 2024-05-23 | 9075 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
23S-087 | OPEN | C000015869 | K110 | P.S. 110 - BROOKLYN | 1196133 | xxxx133 | 89196 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | Closed | 2023-09-15 | 2023-09-15 | 575 | 2023-10-03 | 2023-12-02 | 60 | 18 | 222 | 2025-06-27 | 37770.33 | 37195.33 | 0 | -37770.33 |  |  | UNPAID
23S-067 | OPEN | C000015869 | K111 | I.S. 111 - BROOKLYN | 1188750 | xxxx750 | 88871 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | WIP | 2023-07-26 | 2023-07-26 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
24S-079 | OPEN | C000015869 | K114 | P.S. 114 - BROOKLYN | 1304841 | xxxx841 | 92925 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-08-13 | 2024-08-13 | 4000 | 2024-08-24 | 2024-08-25 | 1 | 11 | 166 | 2025-05-16 | 2454.75 | -1545.25 | 2454.75 | 0 | 855119 | 2025-06-23 | PAID | CHECK 24S-079 K114
22S-085 | OPEN | C000015869 | K127 | P.S. 127 - BROOKLYN | 1160020 | xxxx020 | 86987 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | Closed | 2022-12-19 | 2022-12-19 | 5175 | 2022-12-17 | 2022-12-31 | 14 | -2 | 97 | 2024-05-28 | 7813.38 | 2638.38 | 7813.38 | 0 | 824627 | 2024-07-08 | PAID
22S-072 | OPEN | C000015869 | K127 | P.S. 127 - BROOKLYN | 1156790 | xxxx790 | 86876 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | Closed | 2022-12-07 | 2022-12-07 | 15575 | 2022-12-08 | 2022-12-19 | 11 | 1 | 233 | 2025-07-24 | 28177.26 | 12602.26 | 0 | -28177.26 |  |  | UNPAID
23S-029 | OPEN | C000015869 | K128 | P.S. 128 - BROOKLYN | 1177163 | xxxx163 | 88004 | CIP | Clyne, Sean | Hygienist 13 | PO 18 Asbestos Service | Initial | Closed | 2023-04-25 | 2023-04-25 | 7975 | 2023-07-06 | 2023-07-09 | 3 | 72 | 210 | 2025-06-20 | 9672.08 | 1697.08 | 0 | -9672.08 |  |  | UNPAID
23S-049 | OPEN | C000015869 | K128 | P.S. 128 - BROOKLYN | 1184671 | xxxx671 | 88464 | CIP | Clyne, Sean | Hygienist 13 | PO 18 Asbestos Service | Initial | Closed | 2023-06-21 | 2023-06-21 | 8075 | 2023-06-23 | 2023-06-25 | 2 | 2 | 217 | 2025-06-26 | 6220.81 | -1854.19 | 0 | -6220.81 |  |  | UNPAID
23S-104 | OPEN | C000015869 | K136 | I.S. 136 - BROOKLYN | 1201696 | xxxx696 | 89448 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | Closed | 2023-10-24 | 2023-10-24 | 1575 | 2024-01-11 | 2024-02-17 | 37 | 79 | 128 | 2024-08-16 | 24419.64 | 22844.64 | 24419.64 | 0 | 830191 | 2024-09-19 | PAID
| Not Started | C000015869 | K138 | P.S. 138 - BROOKLYN | 1335922 | xxxx922 | 94843 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | NEW | 2025-02-13 | 2025-02-13 | 6275 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-066 | OPEN | C000015869 | K142 | J.H.S. 142 - BROOKLYN | 1187574 | xxxx574 | 88679 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | WIP | 2023-07-24 | 2023-07-24 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-103 | OPEN | C000015869 | K145 | P.S. 145 - BROOKLYN | 1311813 | xxxx813 | 93324 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | Closed | 2024-09-20 | 2024-09-20 | 575 | 2024-11-27 | 2024-12-23 | 26 | 68 | 190 | 2025-06-05 | 20442.88 | 19867.88 | 0 | -20442.88 |  |  | UNPAID
22S-054 | OPEN | C000015869 | K149 | P.S. 149 - BROOKLYN | 1139236 | xxxx236 | 85940 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2022-09-06 | 2022-09-06 | 8975 | 2022-10-28 | 2022-11-19 | 22 | 52 | 52 | 2024-02-01 | 11479.15 | 2504.15 | 11479.15 | 0 | 817450 | 2024-04-15 | PAID
23S-084 | OPEN | C000015869 | K150 | P.S. 150 - BROOKLYN | 1195461 | xxxx461 | 89302 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | WIP | 2023-09-12 | 2023-09-12 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-061 | OPEN | C000015869 | K151 | P.S. 151 - BROOKLYN | 1302568 | xxxx568 | 92321 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | NEW | 2024-08-05 | 2024-08-05 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-046 | OPEN | C000015869 | K159 | P.S. 159 - BROOKLYN | 1136527 | xxxx527 | 85893 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2022-08-15 | 2022-08-15 | 5175 | 2022-10-06 | 2022-10-08 | 2 | 52 | 81 | 2024-04-29 | 6613.85 | 1438.85 | 6613.85 | 0 | 825164 | 2024-07-15 | PAID
24S-014 | OPEN | C000015869 | K160 | P.S. 160 - BROOKLYN | 1222094 | xxxx094 | 90892 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | NEW | 2024-02-28 | 2024-02-28 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-054 | OPEN | C000015869 | K162 | I.S. 162 - BROOKLYN | 1244202 | xxxx202 | 92352 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | NEW | 2024-07-02 | 2024-07-02 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-064 | OPEN | C000015869 | K162 | I.S. 162 - BROOKLYN | 1300412 | xxxx412 | 92561 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-07-21 | 2024-07-21 | 4000 | 2024-08-04 | 2024-08-04 | 0 | 14 | 150 | 2025-03-18 | 2284.61 | -1715.39 | 2284.61 | 0 | 851724 | 2025-05-19 | PAID | CHECK 24S-064 K162
24S-136 | OPEN | C000015869 | K164 | P.S. 164 - BROOKLYN | 1320983 | xxxx983 | 93856 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | Closed | 2024-11-19 | 2024-11-19 | 10000 | 2024-12-06 | 2024-12-08 | 2 | 17 | 228 | 2025-07-15 | 6517.93 | -3482.07 | 0 | -6517.93 |  |  | UNPAID
24S-092 | OPEN | C000015869 | K166 | I.S. 166 - BROOKLYN | 1308220 | xxxx220 | 93184 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-09-04 | 2024-09-04 | 4000 | 2024-09-22 | 2024-09-22 | 0 | 18 | 191 | 2025-06-13 | 2309 | -1691 | 0 | -2309 |  |  | UNPAID
| Not Started | C000015869 | K171 | I.S. 171 - BROOKLYN | 1320958 | xxxx958 | 93926 | CIP |  | #N/A | Special Program | Initial | NEW | 2024-11-13 | 2024-11-13 | 4100 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-081 | OPEN | C000015869 | K174 | P.S. 174 - BROOKLYN | 1304843 | xxxx843 | 92927 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-08-13 | 2024-08-13 | 4000 | 2024-08-25 | 2024-08-25 | 0 | 12 | 165 | 2025-05-16 | 2732.08 | -1267.92 | 2732.08 | 0 | 855116 | 2025-06-23 | PAID | CHECK 24S-081 K174
23S-005 | OPEN | C000015869 | K183 | P.S. 183 - BROOKLYN | 1160059 | xxxx059 | 87043 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Amendment | WIP | 2023-01-10 | 2023-01-10 | 5575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-077 | OPEN | C000015869 | K183 | P.S. 183 - BROOKLYN | 1141523 | xxxx523 | 86004 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2022-12-12 | 2022-12-12 | 8575 | 2023-02-16 | 2023-02-20 | 4 | 66 | 121 | 2024-07-31 | 10543.6 | 1968.6 | 10543.6 | 0 | 832141 | 2024-10-08 | PAID
24S-080 | OPEN | C000015869 | K184 | P.S. 184 - BROOKLYN | 1304844 | xxxx844 | 92928 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-08-13 | 2024-08-13 | 4000 | 2024-08-31 | 2024-08-31 | 0 | 18 | 167 | 2025-05-16 | 3285.06 | -714.94 | 3285.06 | 0 | 855118 | 2025-06-23 | PAID | CHECK 24S-080 K184
| Not Started | C000015869 | K224 | P.S. 224 - BROOKLYN | 1212815 | xxxx815 | 90349 | CIP | Vafiadis, Jon | Hygienist 16 | Special Program | Initial | NEW | 2024-01-12 | 2024-01-12 | 1500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-120 | OPEN | C000015869 | K224 | P.S. 224 - BROOKLYN |  | xxxx |  |  |  | #N/A | SAFE ACCESS | Initial |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | K226 | P.S. 126 - BROOKLYN | 1317417 | xxxx417 | 93720 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | NEW | 2024-10-22 | 2024-10-22 | 4100 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | K226 | P.S. 226 - BROOKLYN | 1317422 | xxxx422 | 93720 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | NEW | 2024-10-22 | 2024-10-22 | 7800.06 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-074 | OPEN | C000015869 | K231 | P.S. 231 - BROOKLYN | 1302808 | xxxx808 | 92767 | CIP | Bracamonte, Jesus | Hygienist 14 | SAFE ACCESS | Initial | Closed | 2024-08-04 | 2024-08-04 | 4000 | 2024-08-14 | 2024-08-14 | 0 | 10 | 141 | 2025-01-09 | 2483.03 | -1516.97 | 2483.03 | 0 | 842240 | 2025-01-28 | PAID
24S-016 | OPEN | C000015869 | K232 | I.S. 232 - BROOKLYN | 1223724 | xxxx724 | 89776 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-03-13 | 2024-03-13 | 13900 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-018 | OPEN | C000015869 | K232 | I.S. 232 - BROOKLYN | 1223723 | xxxx723 | 89768 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-03-14 | 2024-03-14 | 13900 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-017 | OPEN | C000015869 | K232 | I.S. 232 - BROOKLYN | 1223722 | xxxx722 | 89766 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-03-14 | 2024-03-14 | 13900 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | K233 | P.S. 233 - BROOKLYN | 1212811 | xxxx811 | 90339 | CIP | Vafiadis, Jon | Hygienist 16 | Special Program | Initial | NEW | 2024-01-11 | 2024-01-11 | 1500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-121 | OPEN | C000015869 | K233 | P.S. 233 - BROOKLYN |  | xxxx |  |  |  | #N/A | SAFE ACCESS | Initial |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | K244 | P.S. 244 - BROOKLYN | 1212812 | xxxx812 | 90338 | CIP | Vafiadis, Jon | Hygienist 16 | Special Program | Initial | NEW | 2024-01-11 | 2024-01-11 | 1500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-122 | OPEN | C000015869 | K244 | P.S. 244 - BROOKLYN |  | xxxx |  |  |  | #N/A | SAFE ACCESS | Initial |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-082 | OPEN | C000015869 | K246 | I.S. 246 - BROOKLYN | 1304840 | xxxx840 | 92924 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-08-13 | 2024-08-13 | 4000 | 2024-08-23 | 2024-08-24 | 1 | 10 | 159 | 2025-05-07 | 2629.78 | -1370.22 | 2629.78 | 0 | 854350 | 2025-06-16 | PAID | CHECK 24S-082 K246
| Not Started | C000015869 | K250 | P.S. 250 - BROOKLYN | 1212797 | xxxx797 | 90325 | CIP | Vafiadis, Jon | Hygienist 16 | Special Program | Initial | NEW | 2024-01-11 | 2024-01-11 | 1500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-131 | OPEN | C000015869 | K250 | P.S. 250 - BROOKLYN |  | xxxx |  |  |  | #N/A | SAFE ACCESS | Initial |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | K260 | P.S. 260 - BROOKLYN | 1212816 | xxxx816 | 90348 | CIP | Vafiadis, Jon | Hygienist 16 | Special Program | Initial | NEW | 2024-01-12 | 2024-01-12 | 1500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-123 | OPEN | C000015869 | K260 | P.S. 260 - BROOKLYN |  | xxxx |  |  |  | #N/A | SAFE ACCESS | Initial |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-007 | OPEN | C000015869 | K261 | P.S. 261 - BROOKLYN | 1220932 | xxxx932 | 90763 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-02-21 | 2024-02-21 | 14900 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-009 | OPEN | C000015869 | K263 | P.S./I.S. 323 - BROOKLYN | 1162471 | xxxx471 | 87190 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2023-01-26 | 2023-01-26 | 10175 | 2023-04-27 | 2023-05-06 | 9 | 91 | 111 | 2024-06-24 | 10960.83 | 785.83 | 10960.83 | 0 | 829476 | 2024-09-12 | PAID
24S-066 | OPEN | C000015869 | K265 | I.S. 265 - BROOKLYN | 1301193 | xxxx193 | 92598 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-07-24 | 2024-07-24 | 4000 | 2024-08-08 | 2024-08-09 | 1 | 15 | 225 | 2025-07-07 | 2562.91 | -1437.09 | 0 | -2562.91 |  |  | UNPAID
| Not Started | C000015869 | K273 | P.S. 273 - BROOKLYN | 1212817 | xxxx817 | 90347 | CIP | Vafiadis, Jon | Hygienist 16 | Special Program | Initial | NEW | 2024-01-12 | 2024-01-12 | 1500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-124 | OPEN | C000015869 | K273 | P.S. 273 - BROOKLYN |  | xxxx |  |  |  | #N/A | SAFE ACCESS | Initial |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | K276 | P.S. 276 - BROOKLYN | 1212812 | xxxx812 | 90337 | CIP | Vafiadis, Jon | Hygienist 16 | Special Program | Initial | NEW | 2024-01-12 | 2024-01-12 | 1500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-125 | OPEN | C000015869 | K276 | P.S. 276 - BROOKLYN |  | xxxx |  |  |  | #N/A | SAFE ACCESS | Initial |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | K279 | P.S. 279 - BROOKLYN | 1212814 | xxxx814 | 90336 | CIP | Vafiadis, Jon | Hygienist 16 | Special Program | Initial | NEW | 2024-01-12 | 2024-01-12 | 1500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-126 | OPEN | C000015869 | K279 | P.S. 279 - BROOKLYN |  | xxxx |  |  |  | #N/A | SAFE ACCESS | Initial |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-079 | OPEN | C000015869 | K287 | P.S. 287 - BROOKLYN | 1191864 | xxxx864 | 89110 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | Closed | 2023-08-16 | 2023-08-16 | 575 | 2024-03-21 | 2024-08-23 | 155 | 218 | 157 | 2025-05-06 | 24201.38 | 23626.38 | 24201.38 | 0 | 852980 | 24201.38 | PAID | CHECK 23S-079 K287
| Not Started | C000015869 | K287 | P.S. 287 - BROOKLYN | 1212544 | xxxx544 | 90316 | CIP | Vafiadis, Jon | Hygienist 16 | Special Program | Initial | NEW | 2024-01-11 | 2024-01-11 | 1500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-130 | OPEN | C000015869 | K287 | P.S. 287 - BROOKLYN |  | xxxx |  |  |  | #N/A | SAFE ACCESS | Initial |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-050 | OPEN | C000015869 | K289 | P.S. 289 - BROOKLYN | 1183304 | xxxx304 | 88347 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2023-06-16 | 2023-06-16 | 7575 | 2023-07-27 | 2023-07-29 | 2 | 41 | 123 | 2024-08-01 | 7078.33 | -496.67 | 7078.33 | 0 | 832411 | 2024-10-10 | PAID
24S-045 | OPEN | C000015869 | K316 | P.S. 16 - BROOKLYN | 1238681 | xxxx681 | 91953 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2024-05-30 | 2024-05-30 | 15400 | 2024-06-19 | 2024-07-20 | 31 | 20 | 199 | 2025-06-16 | 5530.33 | -9869.67 | 5530.33 | 0 | 855121 | 2025-06-23 | PAID | CHECK 24S-045 K316
24S-126 | OPEN | C000015869 | K316 | P.S. 16 - BROOKLYN | 1323387 | xxxx387 | 94073 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2024-11-27 | 2024-11-27 | 5275 | 2024-11-23 | 2024-11-24 | 1 | -4 | 206 | 2025-06-17 | 3276.11 | -1998.89 | 0 | -3276.11 |  |  | UNPAID
22S-035 | OPEN | C000015869 | K324 | I.S. 324 - BROOKLYN | 1132555 | xxxx555 | 85598 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2022-07-20 | 2022-07-20 | 26020 | 2022-07-15 | 2024-06-09 | 695 | -5 | 232 | 2025-07-24 | 28774.67 | 2754.67 | 0 | -28774.67 |  |  | UNPAID
23S-075 | OPEN | C000015869 | K335 | P.S. 335 - BROOKLYN | 1189823 | xxxx823 | 88936 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | WIP | 2023-08-14 | 2023-08-14 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-072 | OPEN | C000015869 | K335 | P.S. 335 - BROOKLYN | 1189824 | xxxx824 | 88935 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2023-08-11 | 2023-08-11 | 575 | 2023-10-05 | 2023-10-14 | 9 | 55 | 73 | 2024-04-16 | 20514.03 | 19939.03 | 20514.03 | 0 | 824531 | 2024-07-05 | PAID
23S-042 | OPEN | C000015869 | K364 | P.S. 364 - BROOKLYN | 1184787 | xxxx787 | 88107 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2023-07-12 | 2023-07-12 | 11575 | 2023-07-24 | 2023-07-26 | 2 | 12 | 47 | 2023-10-17 | 7578.28 | -3996.72 | 7578.28 | 0 | 813787 | 2024-02-13 | PAID
| Not Started | C000015869 | K370 | P.S. 370 - BROOKLYN | 1317423 | xxxx423 |  | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | NEW | 2024-10-22 | 2024-10-22 | 7800.06 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-121 | OPEN | C000015869 | K370 | P.S. 370 - BROOKLYN | 1317418 | xxxx418 | 93721 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-10-22 | 2024-10-22 | 4100 | 2024-10-29 | 2024-10-30 | 1 | 7 | 193 | 2025-07-07 | 2211.51 | -1888.49 | 0 | -2211.51 |  |  | UNPAID
| Not Started | C000015869 | K384 | P.S. 384 - BROOKLYN | 1334321 | xxxx321 | 94618 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | NEW | 2025-02-04 | 2025-02-04 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24s-109 | OPEN | C000015869 | K425 | JAMES MADISON HS - BROOKLYN | 1314171 | xxxx171 | 93480 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-09-30 | 2024-09-30 | 4000 | 2024-11-01 | 2024-12-23 | 52 | 32 | 194 | 2025-06-16 | 4725.83 | 725.83 | 0 | -4725.83 |  |  | UNPAID
23S-069 | OPEN | C000015869 | K445 | NEW UTRECHT HS - BROOKLYN | 1187087 | xxxx087 | 88602 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | Closed | 2023-07-13 | 2023-07-13 | 575 | 2023-08-08 | 2024-02-22 | 198 | 26 | 107 | 2024-06-12 | 29861.89 | 29286.89 | 29861.89 | 0 | 827033 | 2024-08-12 | PAID
24S-107 | OPEN | C000015869 | K445 | NEW UTRECHT HS - BROOKLYN | 1314172 | xxxx172 | 93454 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-09-30 | 2024-09-30 | 4000 | 2024-11-29 | 2024-11-29 | 0 | 60 | 177 | 2025-06-03 | 2849.88 | -1150.12 | 0 | -2849.88 |  |  | UNPAID
| Not Started | C000015869 | K455 | BOYS & GIRLS HS - BROOKLYN | 1302807 | xxxx807 | 92773 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | NEW | 2024-08-04 | 2024-08-04 | 4000 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-124 | OPEN | C000015869 | K486 | I.S. 187 - BROOKLYN | 1319899 | xxxx899 | 93871 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2024-11-27 | 2024-11-27 | 5275 | 2024-11-30 | 2024-11-30 | 0 | 3 | 204 | 2025-06-17 | 2747.64 | -2527.36 | 0 | -2747.64 |  |  | UNPAID
| Not Started | C000015869 | K495 | FRANK J MACCHIAROLA EDU COMPLEX | 1310002 | xxxx002 | 93224 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-09-25 | 2024-09-25 | 16345 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-110 | OPEN | C000015869 | K505 | FRANKLIN D ROOSEVELT HS - BROOKLYN | 1314174 | xxxx174 | 93451 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-09-30 | 2024-09-30 | 4000 | 2024-10-14 | 2024-10-14 | 0 | 14 | 178 | 2025-06-03 | 2720.1 | -1279.9 | 0 | -2720.1 |  |  | UNPAID
24S-119 | OPEN | C000015869 | K515 | SOUTH SHORE EDU COMPLEX - BROOKLYN | 1317424 | xxxx424 | 93750 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-10-22 | 2024-10-22 | 7800.06 | 2024-11-30 | 2024-12-28 | 28 | 39 | 244 | 2025-07-24 | 5128.76 | -2671.3 | 0 | -5128.76 |  |  | UNPAID
| Not Started | C000015869 | K515 | SOUTH SHORE EDU COMPLEX - BROOKLYN | 1317419 | xxxx419 | 93750 | CIP |  | #N/A | Special Program | Initial | NEW | 2024-10-22 | 2024-10-22 | 4100 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-064 | OPEN | C000015869 | K600 | CLARA BARTON HS - BROOKLYN | 1148840 | xxxx840 | 85963 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2022-10-20 | 2022-10-20 | 5475 | 2023-02-02 | 1900-01-22 | -44936 | 105 | 54 | 2024-02-06 | 6733.25 | 1258.25 | 6733.25 | 0 | 819514 | 2024-05-08 | PAID
24S-030 | OPEN | C000015869 | K600 | CLARA BARTON HS - BROOKLYN | 1231082 | xxxx082 | 91760 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2024-05-03 | 2024-05-03 | 9675 | 2024-06-20 | 2024-06-23 | 3 | 48 | 209 | 2025-06-20 | 16741.46 | 7066.46 | 0 | -16741.46 |  |  | UNPAID
23S-008 | OPEN | C000015869 | K600 | CLARA BARTON HS - BROOKLYN | 1160045 | xxxx045 | 87001 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-01-24 | 2023-01-24 | 21345 | 2023-09-28 | 2023-10-01 | 3 | 247 | 120 | 2024-07-31 | 11247.98 | -10097.02 | 11247.98 | 0 | 828331 | 2024-08-28 | PAID
22S-051 | OPEN | C000015869 | K600 | CLARA BARTON HS - BROOKLYN | 1138802 | xxxx802 | 86052 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2022-08-26 | 2022-08-26 | 29462.38 | 2022-12-20 | 2024-02-04 | 411 | 116 | 171 | 2025-05-28 | 23934.9 | -5527.48 | 23934.9 | 0 | 854348 | 2025-06-16 | PAID | CHECK 22S-051 K600
| Not Started | C000015869 | K615 | E NY VOC HS OF TRANSIT TECH - BROOKLYN | 1210691 | xxxx691 | 90158 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Amend 1 | NEW | 2023-12-19 | 2023-12-19 | 5375 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-026 | OPEN | C000015869 | K620 | WILLIAM E GRADY VOC HS - BROOKLYN | 1224928 | xxxx928 | 91352 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-03-27 | 2024-03-27 | 12400 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-062 | OPEN | C000015869 | K650 | HARRY VANARSDALE VOC HS(WHITNEY) - BROOKLYN | 1245092 | xxxx092 | 92439 | CIP | Walsh, Joseph | Hygienist 02 | PO 18 Asbestos Service | Initial | Closed | 2024-07-10 | 2024-07-10 | 575 | 2024-09-28 | 2024-09-29 | 1 | 80 | 246 | 2025-07-28 | 4484.75 | 3909.75 | 0 | -4484.75 |  |  | UNPAID
24S-141 | OPEN | C000015869 | K799 | BKLYN EAST ALT LEARNING CENTER - BROOKLYN | 1326820 | xxxx820 | 94278 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2024-12-17 | 2024-12-17 | 4100 | 2024-12-27 | 2024-12-27 | 0 | 10 | 183 | 2025-06-04 | 2354.13 | -1745.87 | 0 | -2354.13 |  |  | UNPAID
23S-081 | OPEN | C000015869 | K804 | COBBLE HILL SCL OF AMR STD (OL6) - BROOKLYN | 1194796 | xxxx796 | 88907 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | WIP | 2023-09-05 | 2023-09-05 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-037 | OPEN | C000015869 | K845 | P.S. 295 - BROOKLYN | 1138182 | xxxx182 | 85820 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | RFA | Closed | 2022-07-28 | 2022-07-28 | 6375 | 2022-08-04 | 2022-08-07 | 3 | 7 | 17 | 2023-06-22 | 9715.23 | 3340.23 | 9715.23 | 0 | 800027 | 2023-07-24 | PAID
| Not Started | C000015869 | K851 | P.S. 159 MINI SCHOOL - BROOKLYN | 1320959 | xxxx959 | 93959 | CIP | Bracamonte, Jesus | Hygienist 14 | SAFE ACCESS | Initial | NEW | 2024-11-13 | 2024-11-13 | 4100 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | K854 | P.S. 178 AX (BED STUY ECC 1) - BROOKLYN | 1327986 | xxxx986 | 94350 | CIP |  | #N/A | PO 18 Asbestos Service | Initial | NEW | 2024-12-26 | 2024-12-26 | 4100 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-056 | OPEN | C000015869 | K872 | I.S. 364 ANNEX - BROOKLYN | 1140683 | xxxx683 | 86135 | CIP | Palermo, Albert | Hygienist 03 | PO 18 Asbestos Service | Initial | Closed | 2022-09-12 | 2022-09-12 | 11575 | 2022-10-27 | 2022-11-26 | 30 | 45 | 53 | 2024-02-01 | 15829.9 | 4254.9 | 15829.9 | 0 | 819271 | 2024-05-08 | PAID
24S-069 | OPEN | C000015869 | K874 | I.S. 340 (OLD 249 AX) - BROOKLYN | 1301195 | xxxx195 | 92644 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-07-24 | 2024-07-24 | 4000 | 2024-08-11 | 2024-08-11 | 0 | 18 | 208 | 2025-06-20 | 2830.21 | -1169.79 | 0 | -2830.21 |  |  | UNPAID
24S-087 | OPEN | C000015869 | K932 | HIGH SCHOOL SUSPENSION CENTER - BROOKLYN | 1305383 | xxxx383 | 92976 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | NEW | 2024-08-16 | 2024-08-16 | 4000 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-037 | OPEN | C000015869 | M001 | P.S. 1 - MANHATTAN | 1182354 | xxxx354 | 74694 | CIP |  | #N/A | LAP Construction Phase Services | Initial | WIP | 2023-06-05 | 2023-06-05 | 19000 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-094 | OPEN | C000015869 | M022 | M022 N.E.S.T (OLD J22) - MANHATTAN | 1200324 | xxxx324 | 89727 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2024-10-03 | 2024-10-03 | 5500 | 2023-10-03 | 2023-10-04 | 1 | -366 | 66 | 2024-03-26 | 2511.13 | -2988.87 | 2511.13 | 0 | 820328 | 2024-05-15 | PAID
24S-022 | OPEN | C000015869 | M028 | P.S. 28 - MANHATTAN | 1224747 | xxxx747 | 91258 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2024-03-20 | 2024-03-20 | 575 | 2024-08-01 | 2024-08-03 | 2 | 134 | 240 | 2025-07-24 | 6730.39 | 6155.39 | 0 | -6730.39 |  |  | UNPAID
24S-078 | OPEN | C000015869 | M028 | P.S. 28 - MANHATTAN | 1305847 | xxxx847 | 93050 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2024-08-16 | 2024-08-16 | 575 | 2024-08-15 | 2024-08-18 | 3 | -1 | 214 | 2025-06-24 | 9069.99 | 8494.99 | 0 | -9069.99 |  |  | UNPAID
22S-047 | OPEN | C000015869 | M046 | P.S. 46 - MANHATTAN | 1142123 | xxxx123 | 86125 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | RFA | Closed | 2022-08-23 | 2022-08-23 | 300 | 2022-08-23 | 2022-08-26 | 3 | 0 | 41 | 2023-09-15 | 5954.03 | 5654.03 | 5954.03 | 0 | 807569 | 2023-11-08 | PAID
24S-048 | OPEN | C000015869 | M050 | P.S. 50 (UDC) - MANHATTAN | 1240803 | xxxx803 | 91997 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | NEW | 2024-06-10 | 2024-06-10 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | M061 | P.S. 61 - MANHATTAN | 1301457 | xxxx457 | 92654 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | NEW | 2024-07-25 | 2024-07-25 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-042 | OPEN | C000015869 | M064 | P.S. 64 (OLD 71) - MANHATTAN | 1301470 | xxxx470 | 91998 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2024-06-07 | 2024-06-07 | 24375 | 2024-06-06 | 2024-07-07 | 31 | -1 | 200 | 2025-06-16 | 30605.65 | 6230.65 | 0 | -30605.65 |  |  | UNPAID
23S-033 | OPEN | C000015869 | M066 | RICHARD R GREEN HS OF TEACHING - MANHATTAN | 1169343 | xxxx343 | 87470 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2023-05-04 | 2023-05-04 | 16575 | 2024-04-11 | 2024-04-21 | 10 | 343 | 236 | 2025-07-24 | 19912.42 | 3337.42 | 19912.42 | 0 |  |  | UNPAID
22S-017 | OPEN | C000015869 | M070 | I.S. 70 - MANHATTAN | 1126983 | xxxx983 | 85293 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | RFA | Closed | 2022-06-08 | 2022-06-08 | 575 | 2022-07-24 | 2022-08-02 | 9 | 46 | 20 | 2023-06-23 | 21497.37 | 20922.37 | 21497.37 | 0 |  | 2023-08-08 | PAID
23S-100 | OPEN | C000015869 | M081 | MID MAN ADULT LRNG CTR (81) - MANHATTAN | 1193755 | xxxx755 | 89109 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2023-08-23 | 2023-08-23 | 575 | 2024-04-22 | 2024-04-24 | 2 | 243 | 143 | 2025-01-09 | 6575.51 | 6000.51 | 6575.51 | 0 |  | 2025-02-11 | PAID
22S-043 | OPEN | C000015869 | M098 | P.S. 98 - MANHATTAN | 1136220 | xxxx220 | 85864 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2022-08-10 | 2022-08-10 | 575 | 2023-01-12 | 2023-01-28 | 16 | 155 | 48 | 2023-10-17 | 17824.18 | 17249.18 | 17824.18 | 0 | 808704 | 2023-11-27 | PAID
| Not Started | C000015869 | M099 | I.S. 99 - MANHATTAN | 1327637 | xxxx637 | 94204 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | NEW | 2024-12-13 | 2024-12-13 | 7575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-011 | OPEN | C000015869 | M110 | P.S. 110 - MANHATTAN | 1129736 | xxxx736 | 85354 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2022-06-03 | 2022-06-03 | 9575 | 2022-06-03 | 2022-06-04 | 1 | 0 | 151 | 2025-05-05 | 5589.53 | -3985.47 | 5589.53 | 0 | 852979 | 2025-06-03 | PAID | CHECK 22S-011 M110
24S-049 | OPEN | C000015869 | M115 | P.S. 115 - MANHATTAN | 1241224 | xxxx224 | 92097 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-06-12 | 2024-06-12 | 20200 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-095 | OPEN | C000015869 | M115 | P.S. 115 - MANHATTAN | 1197647 | xxxx647 | 89597 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-10-04 | 2023-10-04 | 575 | 2023-10-05 | 2023-10-07 | 2 | 1 | 138 | 2024-08-21 | 6672.58 | 6097.58 | 6672.58 | 0 | 841880 | 2025-01-23 | PAID
23S-045 | OPEN | C000015869 | M115 | P.S. 115 - MANHATTAN | 1182352 | xxxx352 | 88295 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-06-08 | 2023-06-08 | 575 | 2023-07-20 | 2023-10-07 | 79 | 42 | 181 | 2025-06-03 | 60014.45 | 59439.45 | 60014.45 | 0 | 855122 | 2025-06-23 | PAID | CHECK 23S-045 M115
| Not Started | C000015869 | M124 | P.S. 124 (ECF) - MANHATTAN | 1316025 | xxxx025 | 93166 | CIP |  | #N/A | PO 18 Asbestos Service | Initial | NEW | 2024-10-10 | 2024-10-10 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | M125 | P.S. 125 - MANHATTAN | 1303172 | xxxx172 | 92796 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-08-06 | 2024-08-06 | 15445 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | M125 | P.S. 125 - MANHATTAN | 1335879 | xxxx879 | 94453 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2025-02-20 | 2025-02-20 | 16200 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-054 | OPEN | C000015869 | M128 | P.S. 128 - MANHATTAN | 1186684 | xxxx684 | 88621 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-07-06 | 2023-07-06 | 575 | 2023-09-20 | 2023-09-30 | 10 | 76 | 106 | 2024-06-12 | 17521.67 | 16946.67 | 17521.67 | 0 | 826173 | 2024-07-29 | PAID
23S-136 | OPEN | C000015869 | M128 | P.S. 128 - MANHATTAN | 1211273 | xxxx273 | 90120 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-12-19 | 2023-12-19 | 575 | 2024-10-01 | 2024-10-04 | 3 | 287 | 231 | 2025-07-16 | 9659.2 | 9084.2 | 0 | -9659.2 |  |  | UNPAID
22S-019 | OPEN | C000015869 | M129 | P.S. 129 - MANHATTAN | 1127850 | xxxx850 | 85282 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | RFA | Closed | 2022-06-10 | 2022-06-10 | 575 | 2022-07-28 | 2022-07-31 | 3 | 48 | 13 | 2023-06-20 | 8548.59 | 7973.59 | 8548.59 | 0 | 802867 | 2023-09-05 | PAID
22S-065 | OPEN | C000015869 | M129 | P.S. 129 - MANHATTAN | 1149690 | xxxx690 | 86609 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | RFA | Closed | 2022-10-29 | 2022-10-29 | 575 | 2022-10-29 | 2022-11-05 | 7 | 0 | 40 | 2023-09-15 | 15915.63 | 15340.63 | 15915.63 | 0 | 808703 | 2023-11-27 | PAID
23S-036 | OPEN | C000015869 | M133 | P.S. 133 - MANHATTAN | 1179854 | xxxx854 | 88183 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-05-17 | 2023-05-17 | 575 | 2023-05-19 | 2023-05-21 | 2 | 2 | 87 | 2024-05-06 | 6212.43 | 5637.43 | 6212.43 | 0 | 824039 | 2024-07-01 | PAID
22S-066 | OPEN | C000015869 | M136 | I.S. 136 - MANHATTAN | 1149650 | xxxx650 | 86514 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2022-11-07 | 2022-11-07 | 25000 | 2023-02-16 | 2023-02-25 | 9 | 101 | 95 | 2024-05-24 | 11844.74 | -13155.26 | 11844.74 | 0 | 824629 | 2024-07-08 | PAID
22S-068 | OPEN | C000015869 | M137 | P.S. 137 - MANHATTAN | 1150094 | xxxx094 | 86602 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Amendment | Closed | 2022-11-09 | 2022-11-09 | 575 | 2023-01-12 | 2023-01-21 | 9 | 64 | 38 | 2023-08-01 | 16393.86 | 15818.86 | 16393.86 | 0 | 803195 | 2023-09-11 | PAID
22S-018 | OPEN | C000015869 | M137 | P.S. 137 - MANHATTAN | 1126982 | xxxx982 | 85286 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2022-06-08 | 2022-06-08 | 575 | 2022-12-22 | 2022-12-28 | 6 | 197 | 140 | 2024-12-19 | 19983.26 | 19408.26 | 19983.26 | 0 | 841881 | 2025-01-23 | PAID
23S-015 | OPEN | C000015869 | M144 | P.S. 242 (OLD 144) - MANHATTAN | 1166775 | xxxx775 | 87340 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2023-02-08 | 2023-02-08 | 575 | 2023-10-26 | 2023-10-28 | 2 | 260 | 109 | 2024-06-17 | 7130.58 | 6555.58 | 7130.58 | 0 | 826174 | 2024-07-29 | PAID
24S-053 | OPEN | C000015869 | M152 | P.S. 152 - MANHATTAN | 1243709 | xxxx709 | 92223 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | NEW | 2024-02-21 | 2024-02-21 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-039 | OPEN | C000015869 | M155 | I.S. 155 - MANHATTAN | 1180534 | xxxx534 | 88234 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2023-05-23 | 2023-05-23 | 575 | 2023-06-09 | 2023-06-10 | 1 | 17 | 61 | 2024-03-08 | 5751.75 | 5176.75 | 5751.75 | 0 | 819023 | 2024-05-02 | PAID
24S-023 | OPEN | C000015869 | M163 | P.S. 163 - MANHATTAN | 1225180 | xxxx180 | 91391 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | NEW | 2024-03-26 | 2024-03-26 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-050 | OPEN | C000015869 | M164 | I.S. 164 - MANHATTAN | 1138190 | xxxx190 | 85906 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | RFA | Closed | 2022-08-09 | 2022-08-09 | 20345 | 2022-11-13 | 2023-04-11 | 149 | 96 | 19 | 2023-06-22 | 25350.54 | 5005.54 | 25350.54 | 0 | 799865 | 2023-07-20 | PAID
22S-014 | OPEN | C000015869 | M165 | P.S. 165 - MANHATTAN | 1131052 | xxxx052 | 85304 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | RFA | Closed | 2022-06-11 | 2022-06-11 | 10575 | 2022-06-11 | 2022-08-30 | 80 | 0 | 22 | 2023-06-27 | 7140.93 | -3434.07 | 7140.93 | 0 | 800530 | 2023-07-31 | PAID
23S-078 | OPEN | C000015869 | M169 | P.S. 169 (ECF) - MANHATTAN | 1191264 | xxxx264 | 88870 | CIP | Lazicki, Rafal | Hygienist 07 | LAP Construction Phase Services | Initial | WIP | 2023-08-15 | 2023-08-15 | 11190 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-114 | OPEN | C000015869 | M180 | P.S. 180 - MANHATTAN | 1315970 | xxxx970 | 93632 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2024-10-10 | 2024-10-10 | 575 | 2024-10-18 | 2024-10-19 | 1 | 8 | 202 | 2025-06-17 | 4759.59 | 4184.59 | 0 | -4759.59 |  |  | UNPAID
22S-053 | OPEN | C000015869 | M185 | P.S. 185 (TANDEM M208) - MANHATTAN | 1141636 | xxxx636 | 86051 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2022-09-01 | 2022-09-01 | 9300 | 2022-09-01 | 2022-09-03 | 2 | 0 | 23 | 2023-06-27 | 7033.25 | -2266.75 | 7033.25 | 0 | 800529 | 2023-07-31 | PAID
24S-003 | OPEN | C000015869 | M187 | P.S./I.S 187 - MANHATTAN | 1216944 | xxxx944 | 90610 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2024-02-05 | 2024-02-05 | 575 | 2024-01-23 | 2024-02-18 | 26 | -13 | 131 | 2024-08-23 | 17848.38 | 17273.38 | 17848.38 | 0 | 834096 | 2024-10-25 | PAID
24S-006 | OPEN | C000015869 | M192 | P.S. 192 - MANHATTAN | 1218023 | xxxx023 | 90701 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | NEW | 2024-02-05 | 2024-02-05 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | M192 | P.S. 192 - MANHATTAN | 1322940 | xxxx940 | 94022 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | NEW | 2024-11-18 | 2024-11-18 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-101 | OPEN | C000015869 | M197 | P.S. 197 - MANHATTAN | 137330 | xxxx330 | 89611 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-10-12 | 2023-10-12 | 575 | 2024-04-12 | 2024-04-14 | 2 | 183 | 139 | 2024-12-03 | 8303.85 | 7728.85 | 8303.85 | 0 | 842154 | 2025-01-24 | PAID
22S-045 | OPEN | C000015869 | M435 | MANHTN CT FOR MATH & SCI. HS - MANHATTAN | 1135506 | xxxx506 | 85822 | CIP | Lazicki, Rafal | Hygienist 07 | LAP Construction Phase Services | Initial | Closed | 2022-08-04 | 2022-08-04 | 7000 | 2022-12-28 | 2023-06-08 | 162 | 146 | 108 | 2024-06-12 | 13333.61 | 6333.61 | 13333.61 | 0 | 826175 | 2024-07-29 | PAID
24S-002 | OPEN | C000015869 | M440 | BAYARD RUSTIN EDUCATIONAL COMPLEX - MANHATTAN | 1213594 | xxxx594 | 90375 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | NEW | 2024-01-10 | 2024-01-10 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-028 | OPEN | C000015869 | M440 | BAYARD RUSTIN EDUCATIONAL COMPLEX - MANHATTAN | 1177691 | xxxx691 | 88001 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2023-04-28 | 2023-04-28 | 6075 | 2023-04-21 | 2023-04-21 | 0 | -7 | 124 | 2024-08-05 | 2603.21 | -3471.79 | 2603.21 | 0 | 828521 | 2024-08-30 | PAID
24S-024 | OPEN | C000015869 | M465 | G. WASHINGTON HS EDUC. CAMPUS - M465 | 1225222 | xxxx222 | 91363 | CIP |  | #N/A | PO 18 Asbestos Service | Initial | NEW | 2024-02-11 | 2024-02-11 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-113 | OPEN | C000015869 | M465 | G. WASHINGTON HS EDUC. CAMPUS - M465 | 1204463 | xxxx463 | 89908 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-11-09 | 2023-11-09 | 575 | 2023-11-09 | 2023-11-12 | 3 | 0 | 101 | 2024-06-05 | 7865.63 | 7290.63 | 7865.63 | 0 | 824708 | 2024-07-09 | PAID
| Not Started | C000015869 | M470 | LOUIS D. BRANDEIS HS - MANHATTAN | 1198033 | xxxx033 | 89608 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Initial | 2023-10-03 | 2023-10-03 | 19020 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-076 | OPEN | C000015869 | M470 | LOUIS D. BRANDEIS HS - MANHATTAN | 1156228 | xxxx228 | 86844 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2022-12-08 | 2022-12-08 | 20220 | 2022-12-19 | 2023-12-27 | 373 | 11 | 110 | 2024-06-19 | 26234.98 | 6014.98 | 26234.98 | 0 | 825055 | 2024-07-12 | PAID
24S-134 | OPEN | C000015869 | M480 | JULIA RICHMAN ED. COMPLEX - M480 | 1334563 | xxxx563 | 94196 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2025-01-25 | 2025-01-25 | 6575 | 2025-01-25 | 2025-01-26 | 1 | 0 | 155 | 2025-05-06 | 2437.03 | -4137.97 | 2437.03 | 0 | 853126 | 2025-06-04 | PAID | CHECK 24S-134 M480
23S-019 | OPEN | C000015869 | M490 | MARTIN LUTHER KING, JR. HS - MANHATTAN | 1167441 | xxxx441 | 87398 | CIP | Lazicki, Rafal | Hygienist 07 | LAP Construction Phase Services | Initial | Closed | 2023-02-16 | 2023-02-16 | 8035 | 2023-03-02 | 2023-07-29 | 149 | 14 | 72 | 2024-04-09 | 18216.88 | 10181.88 | 18216.88 | 0 | 829815 | 2024-09-17 | PAID
22S-063 | OPEN | C000015869 | M490 | MARTIN LUTHER KING, JR. HS - MANHATTAN | 1147501 | xxxx501 | 86372 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2022-10-19 | 2022-10-19 | 14345 | 2023-02-17 | 2023-02-19 | 2 | 121 | 76 | 2024-04-18 | 6509.07 | -7835.93 | 6509.07 | 0 | 819831 | 2024-05-10 | PAID
22S-002 | OPEN | C000015869 | M512 | 3 K CENTER @ 163-165 EAST 84TH STREET - MANHATTAN | 1118075 | xxxx075 | 84666 | CIP | Lazicki, Rafal | Hygienist 07 | LAP Construction Phase Services | RFA | Closed | 2022-04-01 | 2022-04-01 | 22000 | 2022-04-05 | 2022-09-03 | 151 | 4 | 3 | 2022-11-09 | 38819.14 | 16819.14 | 38819.14 | 0 | 787514 | 2022-11-09 | PAID
23S-048 | OPEN | C000015869 | M520 | MURRAY BERGTRAUM HS (ECF) - MANHATTAN | 1186758 | xxxx758 | 87328 | CIP | Lazicki, Rafal | Hygienist 07 | LAP Construction Phase Services | Initial | Closed | 2023-07-19 | 2023-07-19 | 19000 | 2023-05-17 | 2023-12-19 | 216 | -63 | 113 | 2024-07-05 | 31267.67 | 12267.67 | 31267.67 | 0 | 827383 | 2024-08-15 | PAID
23S-060 | OPEN | C000015869 | M520 | MURRAY BERGTRAUM HS (ECF) - MANHATTAN | 1186745 | xxxx745 | 87777 | CIP | Lazicki, Rafal | Hygienist 07 | LAP Construction Phase Services | Initial | Closed | 2023-07-19 | 2023-07-19 | 500 | 2023-08-04 | 2023-08-05 | 1 | 16 | 149 | 2025-03-13 | 2131.98 | 1631.98 | 2131.98 | 0 | 852978 | 2025-06-03 | PAID | CHECK 23S-060 M520
| Not Started | C000015869 | M528 | I.S. 528 - MANHATTAN | 1126308 | xxxx308 | 85125 | CIP | Alawamleh, Eman | Hygienist 11 | LAP Construction Phase Services | Initial | WIP | 2022-05-31 | 2022-05-31 | 500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-049 | OPEN | C000015869 | M600 | FASHION INDUSTRIES VOC HS - MANHATTAN | 1138188 | xxxx188 | 85959 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2022-08-26 | 2022-08-26 | 19845 | 2022-10-27 | 2023-12-11 | 410 | 62 | 82 | 2024-05-01 | 30284.62 | 10439.62 | 30284.62 | 0 | 820909 | 2024-05-21 | PAID
22S-070 | OPEN | C000015869 | M615 | CHELSEA VOC HS - MANHATTAN | 1158465 | xxxx465 | 86969 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2022-12-02 | 2022-12-02 | 9075 | 2022-12-02 | 2022-12-05 | 3 | 0 | 25 | 2023-07-06 | 12766 | 3691 | 12766 | 0 | 800963 | 2023-08-04 | PAID
24S-071 | OPEN | C000015869 | M615 | CHELSEA VOC HS - MANHATTAN | 1301468 | xxxx468 | 92332 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2024-07-25 | 2024-07-25 | 575 | 2024-10-31 | 2024-11-02 | 2 | 98 | 164 | 2025-05-15 | 6586.68 | 6011.68 | 6586.68 | 0 | 853439 | 2025-06-06 | PAID | CHECK 24S-071 M615
22S-005 | OPEN | C000015869 | M620 | NORMAN THOMAS HS (ECF) - MANHATTAN | 1123363 | xxxx363 | 84986 | CIP | Lazicki, Rafal | Hygienist 07 | LAP Construction Phase Services | RFA | Closed | 2022-06-06 | 2022-06-06 | 500 | 2022-07-14 | 2022-07-18 | 4 | 38 | 21 | 2023-06-23 | 21825.8 | 21325.8 | 21825.8 | 0 | 800470 | 2023-07-28 | PAID
24S-140 | OPEN | C000015869 | M660 | SCHL OF THE FUTURE (OLD BACON) - MANHATTAN | 1333677 | xxxx677 | 94298 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2024-12-20 | 2024-12-20 | 5000 | 2024-12-20 | 2024-12-21 | 1 | 0 | 205 | 2025-06-17 | 2243.94 | -2756.06 | 0 | -2243.94 |  |  | UNPAID
23S-119 | OPEN | C000015869 | M844 | P.S. 138 ANNEX (OLD M047 AX) | 1214485 | xxxx485 | 89905 | CIP | Lazicki, Rafal | Hygienist 07 | PO 18 Asbestos Service | Initial | Closed | 2023-12-08 | 2023-12-08 | 7800 | 2023-12-08 | 2023-12-09 | 1 | 0 | 198 | 2025-06-16 | 2131.98 | -5668.02 | 0 | -2131.98 |  |  | UNPAID
23S-031 | OPEN | C000015869 | Q014 | P.S. 14 - QUEENS | 1179823 | xxxx823 | 88171 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-05-16 | 2023-05-16 | 4400 | 2023-05-13 | 2023-05-14 | 1 | -3 | 104 | 2024-06-11 | 4293.03 | -106.97 | 4293.03 | 0 | 824043 | 2024-07-01 | PAID
22S-030 | OPEN | C000015869 | Q015 | P.S. 15 - QUEENS | 1133898 | xxxx898 | 85649 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-07-13 | 2022-07-13 | 9375 | 2022-07-13 | 2022-07-16 | 3 | 0 | 99 | 2024-05-30 | 8999.02 | -375.98 | 8999.02 | 0 | 824628 | 2024-07-08 | PAID
24S-025 | OPEN | C000015869 | Q021 | P.S. 21 - QUEENS | 1224438 | xxxx438 | 91310 | CIP |  | #N/A | PO 18 Asbestos Service | Initial | NEW | 2024-03-27 | 2024-03-27 | 4100 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-073 | OPEN | C000015869 | Q022 | P.S. 22 - QUEENS | 1189469 | xxxx469 | 88744 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-08-02 | 2023-08-02 | 575 | 2024-10-30 | 2024-11-09 | 10 | 455 | 219 | 2025-06-26 | 13872.14 | 13297.14 | 0 | -13872.14 |  |  | UNPAID
24S-031 | OPEN | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1243757 | xxxx757 | 92210 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2024-06-21 | 2024-06-21 | 4100 | 2024-05-04 | 2024-05-05 | 1 | -48 | 135 | 2024-10-10 | 4933.3 | 833.3 | 4933.3 | 0 | 835020 | 2024-11-06 | PAID
24S-060 | OPEN | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1243867 | xxxx867 | 92257 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2024-07-02 | 2024-07-02 | 575 | 2024-07-11 | 2024-07-12 | 1 | 9 | 153 | 2025-05-06 | 6963.25 | 6388.25 | 6963.25 | 0 | 853127 | 2025-06-04 | PAID | CHECK 24S-060 Q023
24S-051 | OPEN | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1233398 | xxxx398 | 91807 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2024-05-04 | 2024-05-04 | 4400 | 2024-06-22 | 2024-06-22 | 0 | 49 | 174 | 2025-06-03 | 1901 | -2499 | 1901 | 0 | 854823 | 2025-06-20 | PAID | CHECK 24S-051 Q023
24S-047 | OPEN | C000015869 | Q024 | P.S. 24 - QUEENS | 1239285 | xxxx285 | 91978 | CIP |  | #N/A | PO 18 Asbestos Service | Initial | NEW | 2024-06-05 | 2024-06-05 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-070 | OPEN | C000015869 | Q029 | P.S. 29 - QUEENS | 1187894 | xxxx894 | 88759 | CIP | Kondilis, Milton | Hygienist 08 | LAP Construction Phase Services | Initial | Closed | 2023-07-25 | 2023-07-25 | 14735 | 2023-09-07 | 2024-07-25 | 322 | 44 | 237 | 2025-07-24 | 16573.38 | 1838.38 | 0 | -16573.38 |  |  | UNPAID
23S-062 | OPEN | C000015869 | Q030 | P.S. 30 - QUEENS | 1186771 | xxxx771 | 88617 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-07-19 | 2023-07-19 | 575 | 2024-02-01 | 2024-02-18 | 17 | 197 | 125 | 2024-08-09 | 20699.7 | 20124.7 | 20699.7 | 0 | 829475 | 2024-09-12 | PAID
23S-011 | OPEN | C000015869 | Q035 | P.S. 35 - QUEENS | 1163182 | xxxx182 | 87037 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-01-31 | 2023-01-31 | 575 | 2023-08-03 | 2023-10-09 | 67 | 184 | 102 | 2024-06-10 | 71368.5 | 70793.5 | 71368.5 | 0 | 826307 | 2024-07-30 | PAID
24S-036 | OPEN | C000015869 | Q037 | P.S. 37 - QUEENS | 1232763 | xxxx763 | 91803 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-05-10 | 2024-05-10 | 15400 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-035 | OPEN | C000015869 | Q037 | P.S. 37 - QUEENS | 1232764 | xxxx764 | 91801 | CIP |  | #N/A | LAP Construction Phase Services | Initial | NEW | 2024-05-10 | 2024-05-10 | 11700 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-077 | OPEN | C000015869 | Q038 | P.S. 38 - QUEENS | 1190869 | xxxx869 | 88352 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-08-14 | 2023-08-14 | 27418.09 | 2024-09-12 | 2024-09-28 | 16 | 395 | 152 | 2025-05-06 | 27200.01 | -218.08 | 27200.01 | 0 | 853280 | 2025-06-05 | PAID | CHECK 23S-077 Q038
22S-038 | OPEN | C000015869 | Q059 | I.S. 59 - QUEENS | 1133896 | xxxx896 | 85646 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-07-28 | 2022-07-28 | 575 | 2022-10-07 | 2022-12-30 | 84 | 71 | 137 | 2024-10-28 | 32571.72 | 31996.72 | 32571.72 | 0 | 839873 | 2024-12-30 | PAID
23S-089 | OPEN | C000015869 | Q060 | P.S.60 - QUEENS | 1197103 | xxxx103 | 89472 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-09-22 | 2023-09-22 | 4375 | 2023-09-22 | 2023-09-23 | 1 | 0 | 60 | 2024-03-04 | 3397.18 | -977.82 | 3397.18 | 0 | 816891 | 2024-04-02 | PAID
| Not Started | C000015869 | Q061 | I.S. 61 - QUEENS | 1124663 | xxxx663 | 85105 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | WIP | 2022-05-24 | 2022-05-24 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-027 | OPEN | C000015869 | Q067 | J.H.S. 67 - QUEENS | 1225935 | xxxx935 | 90816 | CIP |  | #N/A | PO 18 Asbestos Service | Initial | NEW | 2024-04-02 | 2024-04-02 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-047 | OPEN | C000015869 | Q079 | I.S. 79 - QUEENS | 1182975 | xxxx975 | 88112 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | WIP | 2023-06-07 | 2023-06-07 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-074 | OPEN | C000015869 | Q085 | P.S. 85 - QUEENS | 1157266 | xxxx266 | 86894 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | RFA | Closed | 2022-12-10 | 2022-12-10 | 5000 | 2022-12-10 | 2022-12-11 | 1 | 0 | 27 | 2023-07-11 | 5249.18 | 249.18 | 5249.18 | 0 | 799711 | 2023-07-18 | PAID
24S-076 | OPEN | C000015869 | Q089 | P.S. 89 - QUEENS | 1302817 | xxxx817 | 91977 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2024-08-09 | 2024-08-09 | 575 | 2025-04-10 | 2025-04-15 | 5 | 244 | 184 | 2025-06-04 | 11142.81 | 10567.81 | 11142.81 | 0 | 854143 | 2025-06-13 | PAID | CHECK 24S-076 Q089
22S-025 | OPEN | C000015869 | Q112 | P.S. 112 - QUEENS | 1129728 | xxxx728 | 84939 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2022-06-30 | 2022-06-30 | 575 | 2022-12-15 | 2023-12-18 | 368 | 168 | 116 | 2024-07-31 | 23786.87 | 23211.87 | 23786.87 | 0 | 828151 | 2024-08-27 | PAID
23S-088 | OPEN | C000015869 | Q116 | P.S. 116 - QUEENS | 1196944 | xxxx944 | 89473 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | RFA | Closed | 2023-09-25 | 2023-09-25 | 6400 | 2023-09-21 | 2023-09-26 | 5 | -4 | 63 | 2024-03-18 | 5116.55 | -1283.45 | 5116.55 | 0 | 819272 | 2024-05-08 | PAID
| Not Started | C000015869 | Q122 | P.S. 122 - QUEENS | 1125492 | xxxx492 | 85171 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | WIP | 2022-05-25 | 2022-05-25 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-108 | OPEN | C000015869 | Q122 | P.S. 122 - QUEENS | 1203131 | xxxx131 | 89849 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-10-27 | 2023-10-27 | 3775 | 2023-10-27 | 2023-10-28 | 1 | 0 | 220 | 2025-06-26 | 2244.92 | -1530.08 | 0 | -2244.92 |  |  | UNPAID
23S-004 | OPEN | C000015869 | Q126 | I.S. 126 - QUEENS | 1158587 | xxxx587 | 86983 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-01-04 | 2023-01-04 | 575 | 2023-08-05 | 2023-08-22 | 17 | 213 | 68 | 2024-03-29 | 25616.36 | 25041.36 | 25616.36 | 0 | 819270 | 2024-05-08 | PAID
24S-112 | OPEN | C000015869 | Q126 | I.S. 126 - QUEENS | 1315213 | xxxx213 | 93426 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2024-10-04 | 2024-10-04 | 4000 | 2024-10-04 | 2024-10-05 | 1 | 0 | 242 | 2025-07-24 | 3821.05 | -178.95 | 0 | -3821.05 |  |  | UNPAID
24S-028 | OPEN | C000015869 | Q141 | I.S. 141 - QUEENS | 1229285 | xxxx285 | 91394 | CIP |  | #N/A | PO 18 Asbestos Service | Initial | NEW | 2024-04-12 | 2024-04-12 | 5575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-015 | OPEN | C000015869 | Q165 | P.S. 165 - QUEENS | 1223510 | xxxx510 | 88306 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | NEW | 2024-03-08 | 2024-03-08 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
25S-001 | OPEN | C000015869 | Q165 | P.S. 165 - QUEENS | 1330550 | xxxx550 | 94416 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2025-01-03 | 2025-01-03 | 4100 | 2025-01-04 | 2025-01-05 | 1 | 1 | 186 | 2025-06-05 | 3943.88 | -156.12 | 3943.88 | 0 | 855123 | 2025-06-23 | PAID | CHECK 25S-001 Q165
| Not Started | C000015869 | Q166 | P.S. 166 - QUEENS | 1314909 | xxxx909 | 93419 | CIP |  | #N/A | PO 18 Asbestos Service | Initial | NEW | 2024-10-03 | 2024-10-03 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-058 | OPEN | C000015869 | Q168 | J.H.S. 168 - QUEENS | 1144603 | xxxx603 | 86289 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-09-16 | 2022-09-16 | 4840.73 | 2022-10-16 | 2022-10-17 | 1 | 30 | 85 | 2024-05-01 | 4040.73 | -800 | 4040.73 | 0 | 822747 | 2024-06-13 | PAID
22S-073 | OPEN | C000015869 | Q168 | J.H.S. 168 - QUEENS | 1160261 | xxxx261 | 86877 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-12-11 | 2022-12-11 | 3900 | 2022-12-11 | 2022-12-11 | 0 | 0 | 227 | 2025-07-11 | 2384.13 | -1515.87 | 0 | -2384.13 |  |  | UNPAID
23S-086 | OPEN | C000015869 | Q173 | P.S. 173 - QUEENS | 1196148 | xxxx148 | 89297 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-09-19 | 2023-09-19 | 5100 | 2023-09-16 | 2023-09-17 | 1 | -3 | 229 | 2025-07-15 | 3363.57 | -1736.43 | 0 | -3363.57 |  |  | UNPAID
23S-063 | OPEN | C000015869 | Q176 | P.S. 176 - QUEENS | 1188566 | xxxx566 | 88205 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | WIP | 2023-07-24 | 2023-07-24 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-139 | OPEN | C000015869 | Q185 | J.H.S. 185 - QUEENS | 1329981 | xxxx981 | 94438 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2024-12-18 | 2024-12-18 | 16800 | 2024-12-18 | 2024-12-23 | 5 | 0 | 173 | 2025-06-03 | 9674.83 | -7125.17 | 9674.83 | 0 | 854824 | 2025-06-20 | PAID | CHECK 24S-139 Q185
| Not Started | C000015869 | Q188 | P.S. 188 - QUEENS | 1301654 | xxxx654 | 92693 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | NEW | 2024-07-29 | 2024-07-29 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-016 | OPEN | C000015869 | Q189 | J.H.S. 189 - QUEENS | 1126762 | xxxx762 | 85253 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | RFA | Closed | 2022-06-09 | 2022-06-09 | 575 | 2022-08-11 | 2022-08-14 | 3 | 63 | 18 | 2023-06-22 | 9012.85 | 8437.85 | 9012.85 | 0 | 799332 | 2023-07-12 | PAID
23S-102 | OPEN | C000015869 | Q189 | J.H.S. 189 - QUEENS | 1197401 | xxxx401 | 89542 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-10-03 | 2023-10-03 | 29538.65 | 2024-12-19 | 2025-02-23 | 66 | 443 | 218 | 2025-06-26 | 27816.65 | -1722 | 0 | -27816.65 |  |  | UNPAID
22S-004 | OPEN | C000015869 | Q191 | P.S. 191 - QUEENS | 1123683 | xxxx683 | 84992 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-04-29 | 2022-04-29 | 3500 | 2022-04-29 | 2022-05-01 | 2 | 0 | 96 | 2024-05-24 | 5171.03 | 1671.03 | 5171.03 | 0 | 824530 | 2024-07-05 | PAID
22S-013 | OPEN | C000015869 | Q192 | I.S. 192 - QUEENS | 1117713 | xxxx713 | 84478 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-06-08 | 2022-06-08 | 1075 | 2022-09-23 | 2022-09-25 | 2 | 107 | 42 | 2023-09-29 | 8661.09 | 7586.09 | 8661.09 | 0 | 806700 | 2023-10-25 | PAID
22S-012 | OPEN | C000015869 | Q192 | I.S. 192 - QUEENS | 1126399 | xxxx399 | 84618 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-06-06 | 2022-06-06 | 575 | 2022-07-28 | 2022-08-14 | 17 | 52 | 50 | 2023-10-31 | 20556.68 | 19981.68 | 20556.68 | 0 | 809817 | 2023-12-11 | PAID
22S-052 | OPEN | C000015869 | Q192 | I.S. 192 - QUEENS | 1139744 | xxxx744 | 86129 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-08-30 | 2022-08-30 | 5775 | 2022-08-30 | 2022-09-01 | 2 | 0 | 118 | 2024-07-31 | 4911.53 | -863.47 | 4911.53 | 0 | 828522 | 2024-08-30 | PAID
22S-042 | OPEN | C000015869 | Q192 | I.S. 192 - QUEENS | 1134708 | xxxx708 | 85703 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-08-02 | 2022-08-02 | 575 | 2023-08-11 | 2023-08-26 | 15 | 374 | 127 | 2024-08-13 | 16413.17 | 15838.17 | 16413.17 | 0 | 832021 | 2024-10-07 | PAID
| Not Started | C000015869 | Q192 | I.S. 192 - QUEENS | 1140015 | xxxx015 | 86082 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | WIP | 2022-09-07 | 2022-09-07 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-033 | OPEN | C000015869 | Q192 | I.S. 192 - QUEENS | 1131965 | xxxx965 | 85545 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-07-12 | 2022-07-12 | 575 | 2023-07-12 | 2023-07-29 | 17 | 365 | 148 | 2025-03-18 | 14183.93 | 13608.93 | 14183.93 | 0 | 852349 | 2025-05-22 | PAID | CHECK 22S-033 Q192
23S-112 | OPEN | C000015869 | Q193 | P.S. 193 - QUEENS | 1204825 | xxxx825 | 89737 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-11-03 | 2023-11-03 | 4200 | 2023-11-02 | 2023-11-05 | 3 | -1 | 98 | 2024-05-30 | 5440.93 | 1240.93 | 5440.93 | 0 | 824527 | 2024-07-05 | PAID
23S-076 | OPEN | C000015869 | Q193 | I.S. 193 - QUEENS | 1191451 | xxxx451 | 88616 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | WIP | 2023-08-14 | 2023-08-14 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | Q196 | P.S. 196 - QUEENS | 1192028 | xxxx028 | 88590 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | WIP | 2023-08-23 | 2023-08-23 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-041 | OPEN | C000015869 | Q203 | P.S. 203 - QUEENS | 1243762 | xxxx762 | 92007 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2024-05-31 | 2024-05-31 | 4100 | 2024-06-01 | 2024-06-02 | 1 | 1 | 136 | 2024-10-10 | 3557.55 | -542.45 | 3557.55 | 0 | 835021 | 2024-11-06 | PAID
23S-006 | OPEN | C000015869 | Q205 | P.S. 205 - QUEENS | 1161238 | xxxx238 | 86946 | CIP | Bracamonte, Jesus | Hygienist 14 | CTF | Initial | Closed | 2023-01-11 | 2023-01-11 | 25845 | 2023-02-15 | 2023-09-06 | 203 | 35 | 235 | 2025-07-24 | 23289.08 | -2555.92 | 0 | -23289.08 |  |  | UNPAID
23S-007 | OPEN | C000015869 | Q210 | I.S. 210 - QUEENS | 1160021 | xxxx021 | 87036 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-01-13 | 2023-01-13 | 575 | 2023-04-12 | 2023-08-05 | 115 | 89 | 115 | 2024-07-31 | 48501.86 | 47926.86 | 48501.86 | 0 | 828152 | 2024-08-27 | PAID
22S-069 | OPEN | C000015869 | Q216 | J.H.S. 216 - QUEENS | 1153592 | xxxx592 | 86738 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2022-11-22 | 2022-11-22 | 15045 | 2023-07-21 | 2023-07-23 | 2 | 241 | 86 | 2024-05-03 | 6607.2 | -8437.8 | 6607.2 | 0 | 820793 | 2024-05-20 | PAID
23S-071 | OPEN | C000015869 | Q217 | I.S. 217 - QUEENS | 1188339 | xxxx339 | 88787 | CIP | Poskrobko, Lukasz | Hygienist 09 | LAP Construction Phase Services | Initial | WIP | 2023-07-26 | 2023-07-26 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-010 | OPEN | C000015869 | Q221 | P.S. 221 - QUEENS | 1162079 | xxxx079 | 87060 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-01-27 | 2023-01-27 | 575 | 2023-08-24 | 2023-11-04 | 72 | 209 | 90 | 2024-05-07 | 39716.84 | 39141.84 | 39716.84 | 0 | 824529 | 2024-07-05 | PAID
23S-026 | OPEN | C000015869 | Q223 | P.S. 223 - QUEENS | 1170969 | xxxx969 | 87623 | CIP | Bracamonte, Jesus | Hygienist 14 | CTF | Initial | Closed | 2023-04-12 | 2023-04-12 | 21520 | 2023-04-19 | 2023-08-13 | 116 | 7 | 207 | 2025-06-18 | 25507.87 | 3987.87 | 0 | -25507.87 |  |  | UNPAID
24S-020 | OPEN | C000015869 | Q225 | P.S. 225 - QUEENS | 1223718 | xxxx718 | 89963 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-03-14 | 2024-03-14 | 13900 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-019 | OPEN | C000015869 | Q225 | P.S. 225 - QUEENS | 1223719 | xxxx719 | 89359 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-03-14 | 2024-03-14 | 13900 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-071 | OPEN | C000015869 | Q231 | I.S. 231 (TANDEM Q251) - QUEENS | 1152671 | xxxx671 | 86707 | CIP | Kondilis, Milton | Hygienist 08 | LAP Construction Phase Services | Initial | Closed | 2022-12-02 | 2022-12-02 | 13200 | 2023-10-08 | 2023-10-09 | 1 | 310 | 93 | 2024-05-21 | 5505.39 | -7694.61 | 5505.39 | 0 | 824041 | 2024-07-01 | PAID
22S-039 | OPEN | C000015869 | Q231 | I.S. 231 (TANDEM Q251) - QUEENS | 1135183 | xxxx183 | 85777 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2022-07-29 | 2022-07-29 | 3900 | 2022-07-29 | 2022-07-30 | 1 | 0 | 192 | 2025-06-16 | 2079.2 | -1820.8 | 0 | -2079.2 |  |  | UNPAID
22S-022 | OPEN | C000015869 | Q397 | PRE-K CENTER @ 32-52 37TH STREET - QUEENS | 1129932 | xxxx932 | 85470 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | RFA | Closed | 2022-06-24 | 2022-06-24 | 4100 | 2022-06-25 | 2022-06-26 | 1 | 1 | 5 | 2022-12-15 | 3300.38 | -799.62 | 3300.38 | 0 | 788350 | 2023-02-09 | PAID
23S-044 | OPEN | C000015869 | Q397 | PRE-K CENTER @ 32-52 37TH STREET - QUEENS | 1183628 | xxxx628 | 88349 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-06-09 | 2023-06-09 | 6175 | 2023-06-09 | 2023-06-10 | 1 | 0 | 49 | 2023-10-17 | 7665.88 | 1490.88 | 7665.88 | 0 | 807569 | 2023-11-08 | PAID
22S-021 | OPEN | C000015869 | Q400 | AUGUST MARTIN HS - QUEENS | 1134593 | xxxx593 | 85622 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | RFA | Closed | 2022-07-22 | 2022-07-22 | 6575 | 2022-07-22 | 2022-08-14 | 23 | 0 | 16 | 2023-06-22 | 15635.03 | 9060.03 | 15635.03 | 0 | 799300 | 2023-07-12 | PAID
| Not Started | C000015869 | Q400 | AUGUST MARTIN HS - QUEENS | 1323411 | xxxx411 | 94004 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-11-26 | 2024-11-26 | 14100 |  |  | 0 | 0 |  |  |  |  | 0 |  |  |  | UNPAID
22S-008 | OPEN | C000015869 | Q405 | BAYSIDE HS - QUEENS | 1120169 | xxxx169 | 67089 | CIP | Kondilis, Milton | Hygienist 08 | LAP Construction Phase Services | RFA | Closed | 2022-04-08 | 2022-04-08 | 4100 | 2022-04-08 | 2023-07-02 | 450 | 0 | 162 | 2025-05-07 | 9949.73 | 5849.73 | 9949.73 | 0 | 853438 | 2025-06-06 | PAID | CHECK 22S-008 Q405
23S-099 | OPEN | C000015869 | Q425 | JOHN BOWNE HS, INC - QUEENS | 1200347 | xxxx347 | 89726 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | Closed | 2023-10-18 | 2023-10-18 | 5700 | 2023-10-13 | 2023-10-15 | 2 | -5 | 74 | 2024-04-18 | 5378.1 | -321.9 | 5378.1 | 0 | 822278 | 2024-06-07 | PAID
24S-052 | OPEN | C000015869 | Q438 | P.S. 256 ANNEX - QUEENS | 1300385 | xxxx385 | 92209 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | NEW | 2024-07-18 | 2024-07-18 | 6198.04 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-032 | OPEN | C000015869 | Q442 | DISTRICT 29 PRE-K CENTER - QUEENS | 1233875 | xxxx875 | 91854 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | NEW | 2024-05-17 | 2024-05-17 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-037 | OPEN | C000015869 | Q442 | DISTRICT 29 PRE-K CENTER - QUEENS | 1233397 | xxxx397 | 91832 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | NEW | 2024-05-14 | 2024-05-14 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-023 | OPEN | C000015869 | Q450 | NEWCOMERS HIGH SCHOOL (OLD LIC) - QUEENS | 1174986 | xxxx986 | 87897 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-04-12 | 2023-04-12 | 5575 | 2023-04-07 | 2023-04-13 | 6 | -5 | 59 | 2024-02-07 | 7810.55 | 2235.55 | 7810.55 | 0 | 816890 | 2024-04-02 | PAID
23S-002 | OPEN | C000015869 | Q450 | NEWCOMERS HIGH SCHOOL (OLD LIC) - QUEENS | 1159967 | xxxx967 | 87016 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2023-01-04 | 2023-01-04 | 4500 | 2023-01-30 | 2024-09-22 | 601 | 26 | 234 | 2025-07-24 | 64978.59 | 60478.59 | 0 | -64978.59 |  |  | UNPAID
23S-068 | OPEN | C000015869 | Q456 | HS FOR ARTS AND BUS. (OLNUTN X) - QUEENS | 1189784 | xxxx784 | 88945 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-07-31 | 2023-07-31 | 6575 | 2023-07-31 | 2023-08-01 | 1 | 0 | 56 | 2024-02-07 | 5992.9 | -582.1 | 5992.9 | 0 | 818439 | 2024-04-24 | PAID
24S-009 | OPEN | C000015869 | Q460 | FLUSHING HS - QUEENS | 1216051 | xxxx051 | 90480 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | NEW | 2024-01-30 | 2024-01-30 | 1575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-013 | OPEN | C000015869 | Q460 | FLUSHING HS - QUEENS | 1218989 | xxxx989 | 90784 | CIP | Kondilis, Milton | Hygienist 08 | PO 18 Asbestos Service | Initial | NEW | 2024-02-28 | 2024-02-28 | 1775 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-040 | OPEN | C000015869 | Q475 | RICHMOND HILLS HS - QUEENS | 1181631 | xxxx631 | 88287 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-05-26 | 2023-05-26 | 5600 | 2023-05-25 | 2023-05-28 | 3 | -1 | 62 | 2024-02-20 | 5783.81 | 183.81 | 5783.81 | 0 | 817321 | 2024-04-08 | PAID
24S-056 | OPEN | C000015869 | Q480 | JOHN ADAMS HS - QUEENS | 1243886 | xxxx886 | 92299 | CIP |  | #N/A | Special Program | Initial | Closed | 2024-06-27 | 2024-06-27 | 4400 | 2024-07-13 | 2024-07-14 | 1 | 16 | 142 | 2024-12-31 | 2273.91 | -2126.09 | 2273.91 | 0 |  | 2025-02-08 | PAID
22S-062 | OPEN | C000015869 | Q593 | P.S. @ 140 BEACH 112 STREET - QUEENS | 1149305 | xxxx305 | 86549 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | RFA | Closed | 2022-10-19 | 2022-10-19 | 4800 | 2022-10-19 | 2022-10-21 | 2 | 0 | 39 | 2023-08-01 | 4742.45 | -57.55 | 4742.45 | 0 | 800965 | 2023-08-04 | PAID
22S-084 | OPEN | C000015869 | Q593 | P.S. @ 140 BEACH 112 STREET - QUEENS | 1159686 | xxxx686 | 86999 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-01-03 | 2023-01-03 | 3575 | 2022-12-29 | 2022-12-30 | 1 | -5 | 147 | 2025-05-05 | 2762.41 | -812.59 | 2762.41 | 0 | 851186 | 2025-05-13 | PAID | CHECK 22S-084 Q593
23S-020 | OPEN | C000015869 | Q725 | HS FOR INFORMATION TECH - QUEENS | 1170402 | xxxx402 | 87585 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2023-03-09 | 2023-03-09 | 21520 | 2023-03-30 | 2023-10-14 | 198 | 21 | 119 | 2024-07-31 | 10752.68 | -10767.32 | 10752.68 | 0 | 827289 | 2024-08-14 | PAID
23S-001 | OPEN | C000015869 | Q800 | DOE ADMINISTRATIVE / STUDENT SERVICES - QUEENS | 1147905 | xxxx905 | 86152 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | WIP | 2023-01-03 | 2023-01-03 | 575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-044 | OPEN | C000015869 | Q801 | OSSS / DSF - QUEENS | 1137231 | xxxx231 | 85867 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2022-09-01 | 2022-09-01 | 575 | 2023-01-05 | 2023-02-04 | 30 | 126 | 29 | 2023-07-11 | 12701.34 | 12126.34 | 12701.34 | 0 | 799843 | 2023-07-25 | PAID
23S-012 | OPEN | C000015869 | Q801 | OSSS / DSF - QUEENS | 1163723 | xxxx723 | 87297 | CIP | Poskrobko, Lukasz | Hygienist 09 | PO 18 Asbestos Service | Initial | Closed | 2023-02-06 | 2023-02-06 | 575 | 2023-03-23 | 2023-04-01 | 9 | 45 | 31 | 2023-07-20 | 11664.66 | 11089.66 | 11664.66 | 0 | 800964 | 2023-08-04 | PAID
23S-043 | OPEN | C000015869 | R002 | I.S. 2 - STATEN ISLAND | 1183983 | xxxx983 | 88353 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-06-09 | 2023-06-09 | 875 | 2023-06-09 | 2023-06-10 | 1 | 0 | 44 | 2023-10-11 | 8535.7 | 7660.7 | 8535.7 | 0 | 806509 | 2023-10-24 | PAID
24S-008 | OPEN | C000015869 | R002 | I.S. 2 - STATEN ISLAND | 1224066 | xxxx066 | 91184 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | NEW | 2024-03-01 | 2024-03-01 | 4200 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | R002 | I.S. 2 - STATEN ISLAND | 1305317 | xxxx317 | 92968 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | NEW | 2024-08-15 | 2024-08-15 | 4000 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-059 | OPEN | C000015869 | R007 | I.S. 7 - STATEN ISLAND | 1142107 | xxxx107 | 86217 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Amendment | Closed | 2022-09-14 | 2022-09-14 | 13000 | 2022-11-09 | 2022-11-19 | 10 | 56 | 172 | 2025-05-29 | 11726.56 | -1273.44 | 11726.56 | 0 | 854347 | 2025-06-16 | PAID | CHECK 22S-059 R007
24S-043 | OPEN | C000015869 | R008 | P.S. 8 - STATEN ISLAND | 1243679 | xxxx679 | 92211 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2024-06-07 | 2024-06-07 | 4000 | 2024-06-07 | 2024-06-08 | 1 | 0 | 160 | 2025-05-07 | 2152.98 | -1847.02 | 2152.98 | 0 | 851064 | 2025-05-12 | PAID | CHECK 24S-043 R008
24S-033 | OPEN | C000015869 | R013 | P.S. 13 - STATEN ISLAND | 1232533 | xxxx533 | 91809 | CIP |  | #N/A | LAP Construction Phase Services | Initial | NEW | 2024-05-09 | 2024-05-09 | 15400 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-034 | OPEN | C000015869 | R013 | P.S. 13 - STATEN ISLAND | 1232548 | xxxx548 | 91836 | CIP |  | #N/A | LAP Construction Phase Services | Initial | NEW | 2024-05-10 | 2024-05-10 | 11200 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-092 | OPEN | C000015869 | R014 | P.S. 14 - STATEN ISLAND | 1198180 | xxxx180 | 89628 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-09-30 | 2023-09-30 | 7875 | 2023-09-30 | 2023-10-01 | 1 | 0 | 65 | 2024-03-20 | 5413.73 | -2461.27 | 5413.73 | 0 | 819024 | 2024-05-02 | PAID
22s-082 | OPEN | C000015869 | R018 | P.S. 18 - STATEN ISLAND | 1158460 | xxxx460 | 86961 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-01-23 | 2023-01-23 | 190287.5 | 2023-02-16 | 2023-07-18 | 152 | 24 | 211 | 2025-06-24 | 37545.44 | -152742.06 | 0 | -37545.44 |  |  | UNPAID
24S-011 | OPEN | C000015869 | R022 | P.S. 22 - STATEN ISLAND | 1213407 | xxxx407 | 82742 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-01-09 | 2024-01-09 | 5500 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-083 | OPEN | C000015869 | R024 | I.S. 24 - STATEN ISLAND | 1304867 | xxxx867 | 92944 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-08-15 | 2024-08-15 | 4000 | 2024-08-20 | 2025-08-21 | 366 | 5 | 161 | 2025-05-07 | 2032.9 | -1967.1 | 2032.9 | 0 | 854349 | 2025-06-16 | PAID | CHECK 24S-083 R024
22S-034 | OPEN | C000015869 | R026 | P.S. 26 - STATEN ISLAND | 1132987 | xxxx987 | 85620 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | RFA | Closed | 2022-04-28 | 2022-04-28 | 21075 | 2022-07-21 | 2022-07-27 | 6 | 84 | 2 | 2022-10-06 | 29313.56 | 8238.56 | 29313.56 | 0 | 780525 | 2022-10-06 | PAID
23S-027 | OPEN | C000015869 | R026 | P.S. 26 - STATEN ISLAND | 1177420 | xxxx420 | 87998 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-04-20 | 2023-04-20 |  | 2023-04-20 | 2023-04-21 | 1 | 0 | 36 | 2023-08-01 | 6062.8 | 6062.8 | 6062.8 | 0 | 800921 | 2023-08-04 | PAID
23S-107 | OPEN | C000015869 | R026 | P.S. 26 - STATEN ISLAND | 1202649 | xxxx649 | 89785 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-11-13 | 2023-11-13 | 3875 | 2023-10-28 | 2023-10-28 | 0 | -16 | 122 | 2024-07-31 | 2523.58 | -1351.42 | 2523.58 | 0 | 827896 | 2024-08-23 | PAID
24S-089 | OPEN | C000015869 | R026 | P.S. 26 - STATEN ISLAND | 1310116 | xxxx116 | 93264 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | NEW | 2024-09-06 | 2024-09-06 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-115 | OPEN | C000015869 | R030 | P.S 30 - STATEN ISLAND | 1205691 | xxxx691 | 90030 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-11-17 | 2023-11-17 | 11375 | 2023-11-17 | 2023-11-18 | 1 | 0 | 70 | 2024-04-02 | 6029.25 | -5345.75 | 6029.25 | 0 | 818641 | 2024-04-26 | PAID
| Not Started | C000015869 | R032 | P.S. 32 - STATEN ISLAND | 1132984 | xxxx984 | 85600 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | WIP | 2022-07-20 | 2022-07-20 | 6000 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-003 | OPEN | C000015869 | R034 | P.S 34 - STATEN ISLAND | 1123686 | xxxx686 | 84927 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | RFA | Closed | 2022-04-28 | 2022-04-28 | 8300 | 2022-04-28 | 2022-04-30 | 2 | 0 | 1 | 2022-10-06 | 6453.9 | -1846.1 | 6453.9 | 0 | 780524 | 2022-10-06 | PAID
23S-030 | OPEN | C000015869 | R034 | P.S 34 - STATEN ISLAND | 1179156 | xxxx156 | 88108 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-05-12 | 2023-05-12 |  | 2023-05-05 | 2023-05-06 | 1 | -7 | 37 | 2023-08-01 | 5264.23 | 5264.23 | 5264.23 | 0 | 800922 | 2023-08-04 | PAID
24S-086 | OPEN | C000015869 | R034 | P.S 34 - STATEN ISLAND | 1305386 | xxxx386 | 92969 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-08-16 | 2024-08-16 | 4000 | 2024-09-01 | 2024-09-01 | 0 | 16 | 180 | 2025-06-03 | 3166.68 | -833.32 | 0 | -3166.68 |  |  | UNPAID
23S-080 | OPEN | C000015869 | R040 | P.S. 373 (OLD P40) - STATEN ISLAND | 1194257 | xxxx257 | 89229 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2024-06-03 | 2024-06-03 |  | 2023-09-01 | 2023-09-02 | 1 | -276 | 126 | 2024-08-12 | 2964.88 | 2964.88 | 2964.88 | 0 | 828332 | 2024-08-28 | PAID
24S-046 | OPEN | C000015869 | R040 | P.S. 373 (OLD P40) - STATEN ISLAND | 1194257 | xxxx257 | 89229 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | NEW | 2024-08-30 | 2024-08-30 | 5575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-015 | OPEN | C000015869 | R045 | P.S. 45 - STATEN ISLAND | 1129757 | xxxx757 | 85321 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | RFA | Closed | 2022-06-08 | 2022-06-08 | 8275 | 2022-06-08 | 2022-06-12 | 4 | 0 | 12 | 2023-06-14 | 7579.36 | -695.64 | 7579.36 | 0 | 798454 | 2023-06-25 | PAID
| Not Started | C000015869 | R049 | I.S. 49 - STATEN ISLAND | 1212835 | xxxx835 | 90300 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | NEW | 2024-01-09 | 2024-01-09 | 3100 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-074 | OPEN | C000015869 | R053 | P.S. 53 - STATEN ISLAND | 1189854 | xxxx854 | 88746 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-08-07 | 2023-08-07 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
| Not Started | C000015869 | R055 | P.S. 55 - STATEN ISLAND | 1311249 | xxxx249 | 93283 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | NEW | 2024-09-14 | 2024-09-14 | 4000 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-109 | OPEN | C000015869 | R055 | P.S. 55 - STATEN ISLAND | 1205516 | xxxx516 | 89819 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-10-27 | 2023-10-27 | 7875 | 2023-10-27 | 2023-10-28 | 1 | 0 | 216 | 2025-06-25 | 6603.4 | -1271.6 | 0 | -6603.4 |  |  | UNPAID
23S-096 | OPEN | C000015869 | R057 | P.S. 57 - STATEN ISLAND | 1199112 | xxxx112 | 89511 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-10-07 | 2023-10-07 | 10375 | 2023-10-06 | 2023-10-10 | 4 | -1 | 238 | 2025-07-24 | 9467.37 | -907.63 | 0 | -9467.37 |  |  | UNPAID
24S-065 | OPEN | C000015869 | R059 | THE HARBOR VIEW SCHOOL - STATEN ISLAND | 1300413 | xxxx413 | 92564 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-07-24 | 2024-07-24 | 4000 | 2024-07-26 | 2024-07-27 | 1 | 2 | 175 | 2025-06-03 | 4437.13 | 437.13 | 0 | -4437.13 |  |  | UNPAID
23S-021 | OPEN | C000015869 | R061 | I.S. 61 - STATEN ISLAND | 1172020 | xxxx020 | 87748 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-03-27 | 2023-03-27 | 9075 | 2023-04-28 | 2023-04-29 | 1 | 32 | 196 | 2025-06-16 | 4501.55 | -4573.45 | 4501.55 | 0 | 855117 | 2025-06-23 | PAID | CHECK 23S-021 R061
24S-021 | OPEN | C000015869 | R075 | I.S. 75 - STATEN ISLAND | 1224929 | xxxx929 | 91329 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | NEW | 2024-03-27 | 2024-03-27 | 17575 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-001 | OPEN | C000015869 | R435 | NEW DORP HS (NEW) - STATEN ISLAND | 1116702 | xxxx702 | 84575 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | RFA | Closed | 2022-03-16 | 2022-03-16 |  | 2022-03-16 | 2022-04-03 | 18 | 0 | 4 | 2022-11-14 | 12189.08 | 12189.08 | 12189.08 | 0 | 784612 | 2022-12-13 | PAID
23S-116 | OPEN | C000015869 | R435 | NEW DORP HS (NEW) - STATEN ISLAND | 1206985 | xxxx985 | 90061 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-11-26 | 2023-11-26 | 3850 | 2023-11-26 | 2023-11-27 | 1 | 0 | 182 | 2025-06-03 | 2346.04 | -1503.96 | 2346.04 | 0 | 854345 | 2025-06-16 | PAID | CHECK 23S-116 R435
24S-005 | OPEN | C000015869 | R435 | NEW DORP HS (NEW) - STATEN ISLAND | 1213180 | xxxx180 | 90083 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2024-01-04 | 2024-01-04 | 14000 | 2024-02-05 | 2024-11-17 | 286 | 32 | 215 | 2025-06-25 | 8436.98 | -5563.02 | 0 | -8436.98 |  |  | UNPAID
| Not Started | C000015869 | R435 | NEW DORP HS (NEW) - STATEN ISLAND | 1304869 | xxxx869 | 92950 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | NEW | 2024-08-16 | 2024-08-16 | 4000 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
24S-099 | OPEN | C000015869 | R440 | STATEN ISLAND TECHNIAL HS - STATEN ISLAND | 1312305 | xxxx305 | 93263 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2024-09-14 | 2024-09-14 | 10200 | 2024-09-14 | 2024-09-22 | 8 | 0 | 146 | 2025-01-27 | 10352.63 | 152.63 | 10352.63 | 0 |  | 2025-02-11 | PAID
23S-056 | OPEN | C000015869 | R455 | TOTTENVILLE HS - STATEN ISLAND | 1187909 | xxxx909 | 88731 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-07-13 | 2023-07-13 | 7875 | 2023-07-13 | 2023-07-14 | 1 | 0 | 224 | 2025-07-07 | 2628.23 | -5246.77 | 0 | -2628.23 |  |  | UNPAID
| Not Started | C000015869 | R455 | TOTTENVILLE HS - STATEN ISLAND | 1304791 | xxxx791 | 92921 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | NEW | 2024-08-10 | 2024-08-10 | 4000 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-024 | OPEN | C000015869 | R460 | SUSAN R. WAGNER HS - STATEN ISLAND | 1173054 | xxxx054 | 87850 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2023-04-10 | 2023-04-10 | 21520 | 2023-04-06 | 2023-06-18 | 73 | -4 | 46 | 2023-10-16 | 8225.58 | -13294.42 | 8225.58 | 0 | 807653 | 2023-11-08 | PAID
24S-091 | OPEN | C000015869 | R825 | P.S. 25 (MOUNT LORETTO) - STATEN ISLAND | 1311251 | xxxx251 | 93259 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2024-09-08 | 2024-09-08 | 4121.58 | 2024-09-08 | 2024-09-09 | 1 | 0 | 169 | 2025-05-22 | 3502.58 | -619 | 3502.58 | 0 | 854346 | 2025-06-16 | PAID | CHECK 24S-091 R825
24S-067 | OPEN | C000015869 | R831 | P.S. 74 - STATEN ISLAND | 1301196 | xxxx196 | 92576 | CIP | Bracamonte, Jesus | Hygienist 14 | Special Program | Initial | Closed | 2024-07-24 | 2024-07-24 | 4000 | 2024-08-01 | 2024-08-01 | 0 | 8 | 145 | 2024-12-31 | 2338.38 | -1661.62 | 2338.38 | 0 | 841785 | 2025-01-22 | PAID
22S-048 | OPEN | C000015869 | R880 | P.S. 80 (PETR COMPL-BLDG B) - STATEN ISLAND | 1137953 | xxxx953 | 85984 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2022-08-25 | 2022-08-25 | 10500 | 2022-09-14 | 2022-10-16 | 32 | 20 | 75 | 2024-04-18 | 5623.4 | -4876.6 | 5623.4 | 0 | 819831 | 2024-05-10 | PAID
19S-277 | OPEN | C000015869 | R880 | P.S. 80 (PETR COMPL-BLDG B) - STATEN ISLAND | 1002367 | xxxx367 | 73232 | CIP | Scott, Richard | Hygienist 05 | PO 18 Asbestos Service | Initial | Closed | 2019-12-12 | 2019-12-12 | 500 | 2022-08-11 | 2022-08-17 | 6 | 973 | 4186 | 2023-07-20 | 12270.54 | 11770.54 | 12270.54 | 0 | 800187 | 2023-07-25 | PAID
24S-142 | OPEN | C000015869 | R883 | P.S. 80 AX (PETR COMPL-BLDG K) - STATEN ISLAND | 1327776 | xxxx776 | 94296 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2024-12-19 | 2024-12-19 | 4100 | 2024-12-26 | 2024-12-26 | 0 | 7 | 212 | 2025-06-24 | 2344.06 | -1755.94 | 0 |  |  |  | UNPAID
23S-085 | OPEN | C000015869 | X005 | P.S. 5 - BRONX | 1196035 | xxxx035 | 89249 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-09-15 | 2023-09-15 | 575 | 2023-09-14 | 2023-09-16 | 2 | -1 | 84 | 2024-05-01 | 11013.5 | 10438.5 | 11013.5 | 0 | 824038 | 2024-07-01 | PAID
24S-057 | OPEN | C000015869 | X005 | P.S. 5 - BRONX | 1243687 | xxxx687 | 92195 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-06-28 | 2024-06-28 | 16700 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-064 | OPEN | C000015869 | X011 | P.S. 19 - BRONX | 1188192 | xxxx192 | 88729 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Amendment | Closed | 2023-07-24 | 2023-07-24 | 575 | 2023-08-07 | 2023-08-08 | 1 | 14 | 94 | 2024-05-24 | 5219.18 | 4644.18 | 5219.18 | 0 | 824528 | 2024-07-05 | PAID
23S-038 | OPEN | C000015869 | X019 | P.S. 19 - BRONX | 1183897 | xxxx897 | 88212 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Initial | Closed | 2023-07-14 | 2023-07-14 | 54580.5 | 2023-08-17 | 2023-08-20 | 3 | 34 | 133 | 2024-09-19 | 13225.51 | -41354.99 | 13225.51 | 0 | 835019 | 2024-11-06 | PAID
23S-018 | OPEN | C000015869 | X027 | P.S. 277 - BRONX | 1169734 | xxxx734 | 87524 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-03-02 | 2023-03-02 | 575 | 2023-07-07 | 2023-07-09 | 2 | 127 | 88 | 2024-05-06 | 8304.05 | 7729.05 | 8304.05 | 0 | 824040 | 2024-07-01 | PAID
24S-097 | OPEN | C000015869 | X028 | P.S. 28 - BRONX | 1308103 | xxxx103 | 93164 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Initial | Closed | 2024-08-30 | 2024-08-30 | 575 | 2024-10-17 | 2024-10-19 | 2 | 48 | 230 | 2025-07-16 | 6034.19 | 5459.19 | 0 | -6034.19 |  |  | UNPAID
23S-138 | OPEN | C000015869 | X039 | NEW SCH FOR ARTS AND SCIENCE - BRONX | 1196307 | xxxx307 | 89315 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-09-19 | 2023-09-19 | 14932.72 | 2024-08-23 | 2024-08-25 | 2 | 339 | 168 | 2025-05-22 | 13332.72 | -1600 | 0 | -13332.72 |  |  | UNPAID
23S-025 | OPEN | C000015869 | X041 | P.S. 41 - BRONX | 1174668 | xxxx668 | 87890 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Initial | WIP | 2023-04-11 | 2023-04-11 | 575 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
23S-014 | OPEN | C000015869 | X049 | P.S. 49 - BRONX | 1167051 | xxxx051 | 87395 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-02-14 | 2023-02-14 | 575 | 2023-02-09 | 2023-02-12 | 3 | -5 | 91 | 2024-05-07 | 6073.75 | 5498.75 | 6073.75 | 0 | 824042 | 2024-07-01 | PAID
24S-055 | OPEN | C000015869 | X065 | P.S. 65 - BRONX | 1244229 | xxxx229 | 92350 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2024-07-12 | 2024-07-12 | 575 | 2024-10-24 | 2024-11-16 | 23 | 104 | 170 | 2025-05-22 | 17971.61 | 17396.61 | 17971.61 | 0 | 855124 | 2025-06-23 | PAID | CHECK 24S-055 X065
24S-044 | OPEN | C000015869 | X074 | I.S. 201 - BRONX | 1234316 | xxxx316 | 91863 | CIP |  | #N/A | LAP Construction Phase Services | Initial | NEW | 2024-05-28 | 2024-05-28 | 300 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
23S-114 | OPEN | C000015869 | X075 | P.S. 75 - BRONX | 1205150 | xxxx150 | 89840 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-11-14 | 2023-11-14 | 575 | 2024-08-02 | 2024-08-26 | 24 | 262 | 201 | 2025-06-16 | 47383.26 | 46808.26 | 47383.26 | 0 | 855120 | 2025-06-23 | PAID | CHECK 23S-114 X075
23S-034 | OPEN | C000015869 | X080 | P.S. 80 - BRONX | 1171504 | xxxx504 | 87691 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Initial | Closed | 2023-05-12 | 2023-05-12 | 575 | 2023-07-31 | 2023-08-10 | 10 | 80 | 79 | 2024-04-22 | 20602.27 | 20027.27 | 20602.27 | 0 | 823201 | 2024-06-20 | PAID
23S-065 | OPEN | C000015869 | X085 | P.S. 85 - BRONX | 1188698 | xxxx698 | 88845 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Amendment | Closed | 2023-07-25 | 2023-07-25 | 3075 | 2023-07-24 | 2023-08-17 | 24 | -1 | 92 | 2024-05-13 | 4410.05 | 1335.05 | 4410.05 | 0 | 823610 | 2024-06-25 | PAID
23S-111 | OPEN | C000015869 | X085 | P.S. 85 - BRONX | 1202987 | xxxx987 | 89844 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Initial | Closed | 2023-10-30 | 2023-10-30 | 6575 | 2024-01-25 | 2024-01-28 | 3 | 87 | 117 | 2024-07-31 | 7352.25 | 777.25 | 7352.25 | 0 | 829477 | 2024-09-12 | PAID
23S-059 | OPEN | C000015869 | X085 | P.S. 85 - BRONX | 1188194 | xxxx194 | 88763 | CIP | Zarrabi, Abdi | Hygienist 10 | PO 18 Asbestos Service | Amendment | Closed | 2023-07-19 | 2023-07-19 | 41521 | 2023-07-24 | 2023-08-24 | 31 | 5 | 158 | 2025-05-06 | 20155.11 | -21365.89 | 20155.11 | 0 | 855125 | 2025-06-23 | PAID | CHECK 23S-059 X085
24S-088 | OPEN | C000015869 | X086 | P.S. 86 - BRONX | 1304685 | xxxx685 | 92919 | CIP | Bracamonte, Jesus | Hygienist 14 | PO 18 Asbestos Service | Initial | Closed | 2024-08-19 | 2024-08-19 | 575 | 2024-09-05 | 2024-09-07 | 2 | 17 | 243 | 2025-07-24 | 6706.86 | 6131.86 | 0 | -6706.86 |  |  | UNPAID
22S-024 | OPEN | C000015869 | X093 | P.S. 93 - BRONX | 1131990 | xxxx990 | 85532 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | RFA | Closed | 2022-06-30 | 2022-06-30 | 575 | 2022-06-30 | 2022-07-02 | 2 | 0 | 6 | 2022-12-28 | 6339.9 | 5764.9 | 6339.9 | 0 | 790648 | 2023-03-08 | PAID
23S-053 | OPEN | C000015869 | X101 | I.S. 101 - BRONX | 1183976 | xxxx976 | 88398 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-06-15 | 2023-06-15 | 575 | 2023-09-21 | 2023-09-24 | 3 | 98 | 58 | 2024-02-21 | 6284.13 | 5709.13 | 6284.13 | 0 | 819689 | 2024-05-09 | PAID
23S-058 | OPEN | C000015869 | X101 | I.S. 101 - BRONX | 1186918 | xxxx918 | 88631 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2023-07-19 | 2023-07-19 | 9020 | 2023-12-15 | 2023-12-17 | 2 | 149 | 100 | 2024-06-05 | 6341.5 | -2678.5 | 6341.5 | 0 | 822987 | 2024-06-17 | PAID
23S-003 | OPEN | C000015869 | X101 | I.S. 101 - BRONX | 1163449 | xxxx449 | 87019 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | Closed | 2023-02-03 | 2023-02-03 | 38500 | 2023-02-24 | 2023-12-15 | 294 | 21 | 132 | 2024-08-23 | 37718.95 | -781.05 | 37718.95 | 0 | 831360 | 2024-10-01 | PAID
| Not Started | C000015869 | X102 | P.S. 102 - BRONX | 1328013 | xxxx013 | 93969 | CIP | Bracamonte, Jesus | Hygienist 14 | LAP Construction Phase Services | Initial | NEW | 2024-12-26 | 2024-12-26 | 15045 |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
23S-052 | OPEN | C000015869 | X107 | I.S. 107 - BRONX | 1185462 | xxxx462 | 88307 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | WIP | 2023-06-21 | 2023-06-21 |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | UNPAID
22S-036 | OPEN | C000015869 | X127 | I.S. 127 - BRONX | 1135064 | xxxx064 | 85704 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | RFA | Closed | 2022-07-22 | 2022-07-22 | 8875 | 2022-07-22 | 2022-07-25 | 3 | 0 | 24 | 2023-07-05 | 11811.36 | 2936.36 | 11811.36 | 0 | 804163 | 2023-09-22 | PAID
| Not Started | C000015869 | X131 | I.S. 131 - BRONX | 1335358 | xxxx358 | 94778 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | NEW | 2025-02-14 | 2025-02-14 | 575 |  |  | 0 | 0 | [8 empty] | UNPAID
23S-082 | OPEN | C000015869 | X146 | P.S. 146 - BRONX | 1195355 | xxxx355 | 89316 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | WIP | 2023-09-11 | 2023-09-11 | 575 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
24S-058 | OPEN | C000015869 | X149 | J.H.S. 149 - BRONX | 1243686 | xxxx686 | 92199 | CIP |  | #N/A | LAP Construction Phase Services | Initial | NEW | 2024-06-28 | 2024-06-28 | 16700 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
| Not Started | C000015869 | X161 | P.S. 161 - BRONX | 1335270 | xxxx270 | 94786 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | NEW | 2025-02-19 | 2025-02-19 | 575 |  |  | 0 | 0 | [8 empty] | UNPAID
23S-013 | OPEN | C000015869 | X401 | BRONX REGIONAL HS (OLD 133) - BRONX | 1165246 | xxxx246 | 87286 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Initial | Closed | 2023-02-06 | 2023-02-06 | 575 | 2023-03-23 | 2023-03-25 | 2 | 45 | 51 | 2024-02-07 | 7268.63 | 6693.63 | 7268.63 | 0 | 815948 | 2024-03-18 | PAID
22S-028 | OPEN | C000015869 | X425 | EVANDER CHILDS HS - BRONX | 1130024 | xxxx024 | 85491 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | RFA | Closed | 2022-07-06 | 2022-07-06 | 575 | 2022-08-11 | 2022-08-13 | 2 | 36 | 14 | 2023-06-20 | 6187.21 | 5612.21 | 6187.21 | 0 | 799215 | 2023-07-11 | PAID
22S-061 | OPEN | C000015869 | X455 | HARRY S TRUMAN HS - BRONX | 1146848 | xxxx848 | 85699 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | RFA | Closed | 2022-09-29 | 2022-09-29 | 575 | 2023-02-21 | 2023-02-24 | 3 | 145 | 34 | 2023-09-06 | 8454.45 | 7879.45 | 8454.45 | 0 | 805729 | 2023-10-13 | PAID
22S-023 | OPEN | C000015869 | X470 | SOUTH BRONX EDUCATIONAL CAMPUS (OLD 38) - BRONX | 1128873 | xxxx873 | 85247 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2022-06-23 | 2022-06-23 | 575 | 2023-02-16 | 2023-04-08 | 51 | 238 | 45 | 2023-10-11 | 26283.31 | 25708.31 | 26283.31 | 0 | 820910 | 2024-05-21 | PAID
23S-035 | OPEN | C000015869 | X470 | SOUTH BRONX EDUCATIONAL CAMPUS (OLD 38) - BRONX | 1175547 | xxxx547 | 87938 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2023-05-10 | 2023-05-10 | 575 | 2023-08-17 | 2023-08-19 | 2 | 99 | 64 | 2024-03-20 | 7061.55 | 6486.55 | 7061.55 | 0 | 849822 | 2025-04-28 | PAID
22S-026 | OPEN | C000015869 | X470 | SOUTH BRONX EDUCATIONAL CAMPUS (OLD 38) - BRONX | 1131033 | xxxx033 | 85485 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | Closed | 2022-07-08 | 2022-07-08 | 575 | 2022-07-07 | 2022-07-09 | 2 | -1 | 67 | 2024-03-26 | 7124.33 | 6549.33 | 7124.33 | 0 | 821671 | 2024-05-29 | PAID
23S-041 | OPEN | C000015869 | X807 | DISTRICT OFFICE #7 (OLD 18) - BRONX | 1180607 | xxxx607 | 88248 | CIP | Alawamleh, Eman | Hygienist 11 | PO 18 Asbestos Service | Initial | WIP | 2023-05-24 | 2023-05-24 | 575 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
22S-081 | OPEN | C000015869 | X843 | P.S. 246 (POE CENTER) - BRONX | 1158558 | xxxx558 | 86979 | CIP | Kowalski, Zbigniew | Hygienist 12 | PO 18 Asbestos Service | Initial | WIP | 2022-12-21 | 2022-12-21 | 8575 |  |  | 0 | 0 | [5 empty] | 0 |  |  | UNPAID
Formulas:
Column2 = IF([Initiation Date (WA)]="", [Actual Start Date (RFP)], [Initiation Date (WA)])

## DASH DICTIONARY
ANONYMIZE DATA
Hygienist Name
"Hygienist " & TEXT(MATCH( I2, UNIQUE($I$2:$I$362), 0), "00") | Concatentate Hygienist with
UNIQUE - returns a list of values from a range or array, it works with any type of data
UNIQUE(array, [by_col], [exactly_once])
Dynamic array, automatically spills into neighboring cells vertically or horizontally
MATCH returns a number
Finds where in the cell I2 appears in that unique list, and returns the number of where it appears in the unique list
TEXT changes the format of a single digit into a two digit
Then concatenate Hygienist with that double digit number
Work Authorization #
("xxxx" & RIGHT(E2, 3))
ADD HELPER COLUMNS
New Column Name | Formula Example | Purpose
Job Age (Days) | =TODAY()-[Start Date] | Shows how many days a job is open
Cost Variance ($) | =[Actual Cost] - [Estimated Cost] | Over/under budget in dollars | Actual Cost - Estimated Cost
Cost Variance (%) | =IF([Estimated Cost]=0, 0, ([Actual Cost] - [Estimated Cost]) / [Estimated Cost]) | Over/under budget as a percentage
Paid Flag | =IF([Paid/Unpaid]="Paid", 1, 0) | For calculating % paid jobs

## DASH PLAN
Plan for Your Excel Dashboard
Goal:
A professional, interactive dashboard that tracks asbestos/lead/mold inspection projects, showing KPIs, trends, and status in a visually appealing way.
Data Source:
Your real SAI project data (WA #, Service ID, Hygienist, Estimated/Actual Cost, Paid/Unpaid, etc.)
Step 1 – Prepare & Clean Data
Remove/Anonymize sensitive info for public portfolio use (e.g., replace names with placeholders like “Hygienist A”).
Standardize column names and formats (dates, currency, text case).
Add any missing helper columns for dashboard logic (e.g., Job Age in Days, Payment Status Flag, Open vs Closed).
Step 2 – Identify KPIs
Some ideas:
Total Projects (count)
Total Estimated vs Actual Cost (with variance %)
Average Project Duration
% Paid vs Unpaid Jobs
Jobs by Type (asbestos, lead, mold)
Workload by Hygienist
Step 3 – Build Pivot Tables
Create pivot tables to feed the dashboard:
Projects by Status
Cost breakdown (Estimated vs Actual)
Jobs per Hygienist
Monthly trends
Step 4 – Dashboard Layout
Top row: KPI cards (Total Projects, Total Costs, % Paid)
Middle section: Charts (bar for jobs per hygienist, line for monthly trends)
Bottom section: Project table with slicers for filtering
Step 5 – Interactivity
Slicers for:
Date Range
Hygienist
Job Type
Payment Status
Timeline for start/close dates
Step 6 – Portfolio Polish
Consistent color theme (aligned with your branding or clean neutral palette)
Clear labels and chart titles
Remove gridlines & unnecessary clutter
Add a short dashboard description for your GitHub README
If you want, we can start right now by:
Reviewing your latest dataset
Deciding on which KPIs to display
Creating the first pivot table to feed the dashboard
Do you want me to start by helping you anonymize and prep your current dataset so it’s safe to share in your portfolio? That’s the first step before we touch the visuals.

## RAW_DATA
SAI FILE NO | Contract # | Building | School Name | WA # | Service ID | Project Type | Primary Hygienist | Service Name | WA Type | WA Status | Initiation Date (WA) | Estimated Cost (WA) | Actual Start Date (RFP) | Actual Date of Completion (RFP) | RFP No | Date of RFP | Amount Invoiced (RFP) | Amount Received | Amount Outstanding | CHECK NO. | DATE ON CHECK | PAID / UNPAID | NOTES
17SD-136 | C000013440 | M470 | LOUIS D. BRANDEIS HS - MANHATTAN | 888431 | 68127 | CIP | Langlois, Bret | LAP Design Review & Specification | Amendment | Closed | 2017-11-07 | 3575 | 2017-11-19 | 2018-01-26 | 230 | 2019-06-10 | 7470.5 | 0 | -7470.5 |  |  | UNPAID
19S-261 | C000015128 | K011 | P.S. 11 - BROOKLYN | 999593 | 74734 | CIP | Walsh, Joseph | LAP Construction Phase Services | RFA | Closed | 2019-11-14 | 22300 | 2020-02-08 | 2022-07-22 | 4200 | 2024-03-27 | 43264.55 | 43264.55 | 0 | 819088 | 2024-05-02 | PAID
21S-102 | C000015128 | K061 | I.S. 61 - BROOKLYN | 1096267 | 83439 | CIP | Palermo, Albert | LAP Construction Phase Services | RFA | Closed | 2021-11-01 | 500 | 2022-01-23 | 2022-12-15 | 4196 | 2023-10-25 | 20190.01 | 20190.01 | 0 | 813482 | 2024-08-24 | PAID
19S-010 | C000015128 | K110 | P.S. 110 - BROOKLYN | 967469 | 72073 | CIP | Towers, Daniel | PO 18 Asbestos Service | RFA | Closed | 2019-04-11 | 500 | 2020-07-23 | 2020-08-02 | 4184 | 2023-07-20 | 18196.52 | 18196.52 | 0 | 800185 | 2023-07-25 | PAID
22S-083 | C000015128 | K163 | P.S. 163 - BROOKLYN | 1062263 | 81072 | CIP | Scott, Richard | LAP Construction Phase Services | Initial | WIP | 2021-02-12 | 3500 | [6 empty] | 0 |  |  | UNPAID
21S-100 | C000015128 | K186 | P.S. 186 - BROOKLYN | 1097498 | 82916 | CIP | Scott, Richard | PO 18 Asbestos Service | Amendment | WIP | 2021-11-05 | 10700 | [6 empty] | 0 |  |  | UNPAID
19S-001 | C000015128 | K480 | BUSHWICK EDUCATIONAL CAMPUS - BROOKLYN | 958748 | 68455 | CIP | Walsh, Joseph | LAP Construction Phase Services | RFA | WIP | 2018-01-16 | 93000 | [6 empty] | 0 |  |  | UNPAID
19SD- | C000015128 | K540 | JOHN DEWEY HS - BROOKLYN | 992170 | 74401 | CIP | Kordes, Kristin | LAP Design Review & Specification | Amendment | WIP | 2019-10-08 | 1750 | [6 empty] | 0 |  |  | UNPAID
21S-026 | C000015128 | M015 | P.S. 15 - MANHATTAN | 1067993 | 81283 | CIP | Lazicki, Rafal | LAP Construction Phase Services | RFA | Closed | 2021-03-17 | 28500 | 2021-06-03 | 2022-09-07 | 4201 | 2024-04-01 | 167322.32 | 167322.32 | 0 | 817916 | 2024-04-17 | PAID
20S-064 | C000015128 | M110 | P.S. 110 - MANHATTAN | 1053130 | 80200 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | RFA | Closed | 2020-11-13 | 6000 | 2020-11-13 | 2020-11-14 | 4205 | 2024-04-05 | 4097.91 | 4097.91 | 0 | 848655 | 2025-04-15 | PAID
19S-276 | C000015128 | M165 | P.S. 165 - MANHATTAN | 1002890 | 74984 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | RFA | Closed |  | 500 | 2020-01-16 | 2022-05-18 | 4180 | 2023-06-15 | 2003.42 | 2003.42 | 0 | 799179 | 2023-07-11 | PAID
19S-273 | C000015128 | M620 | NORMAN THOMAS HS (ECF) - MANHATTAN | 983314 | 73197 | CIP | Lazicki, Rafal | LAP Construction Phase Services | RFA | Closed | 2019-08-09 | 5500 | 2019-12-18 | 2021-10-30 | 4179 | 2023-06-06 | 11228.81 | 11228.81 | 0 | 798708 | 2023-07-03 | PAID
21S-059 | C000015128 | Q021 | P.S. 21 - QUEENS | 1081024 | 82138 | CIP | Kondilis, Milton | LAP Construction Phase Services | RFA | Closed | 2021-06-29 | 27000 | 2021-08-30 | 2023-08-10 | 4198 | 2023-11-08 | 40541.88 | 40541.88 | 0 | 811654 | 2024-01-11 | PAID
23S-091 | C000015128 | Q041 | P.S. 41 - QUEENS | 1199787 | 89442 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-10-06 | 7700 | 2023-10-07 | 2023-10-08 | 69 | 2024-03-29 | 3864.83 | 3864.83 | 0 | 820024 | 2024-05-13 | PAID
21S-037 | C000015128 | Q060 | P.S. 60 - QUEENS | 1071623 | 81514 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Amendment | Closed | 2021-04-22 | 500 | 2021-05-13 | 2021-05-16 | 4183 | 2023-07-14 | 5286.62 | 5286.62 | 0 | 800186 | 2023-07-25 | PAID
21S-106 | C000015128 | Q081 | P.S. 81 - QUEENS | 1098684 | 83571 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2021-11-16 | 500 | 2023-08-01 | 2023-08-01 | 4188 | 2023-08-01 | 500 | 500 | 0 | 800966 | 2020-08-04 | PAID
24S-077 | C000015128 | Q089 | P.S. 89 - QUEENS | 1302817 | 91977 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | NEW | 2024-08-09 | 575 | [6 empty] | 0 |  |  | UNPAID
19S-002 | C000015128 | Q094 | P.S. 94 - QUEENS | 962451 | 71734 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2019-03-15 | 500 | 2019-03-20 | 2020-08-17 | 4185 | 2023-07-20 | 12150.12 | 12150.12 | 0 | 804162 | 2023-09-22 | PAID
21S-057 | C000015128 | Q192 | I.S. 192 - QUEENS | 1080851 | 82009 | CIP | Zarrabi, Abdi | PO 18 Asbestos Service | RFA | Closed | 2021-06-22 |  | 2021-10-28 | 2022-04-19 | 4155 | 2022-09-01 | 30791.17 | 30791.17 | 0 | 798794 | 2023-07-05 | PAID
21S-019 | C000015128 | Q192 | I.S. 192 - QUEENS | 1065824 | 81133 | CIP | Kondilis, Milton | PO 18 Asbestos Service | RFA | Closed | 2021-03-02 | 900 | 2021-04-15 | 2021-04-15 | 4203 | 2024-04-04 | 1226.11 | 1226.11 | 0 | 819962 | 2024-05-13 | PAID
21S-070 | C000015128 | Q216 | J.H.S. 216 - QUEENS | 1084164 | 82491 | CIP | Kondilis, Milton | PO 18 Asbestos Service | RFA | Closed | 2021-08-03 | 500 | 2021-12-02 | 2022-04-03 | 4187 | 2023-07-31 | 14987.36 | 14987.36 | 0 | 803144 | 2023-09-08 | PAID
20S-052 | C000015128 | Q450 | NEWCOMERS HIGH SCHOOL (OLD LIC) - QUEENS | 1048150 | 80036 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2020-10-22 | 500 | 2020-10-22 | 2020-10-25 | 4189 | 2023-08-01 | 8330.37 | 8330.37 | 0 | 801177 | 2023-08-08 | PAID
19S-280 | C000015128 | X040 | P.S. 40 - QUEENS | 1006948 | 75115 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2019-12-27 | 500 | 2019-12-27 | 2019-12-30 | 4191 | 2023-09-29 | 7569.4 | 7569.4 | 0 | 808702 | 2023-11-27 | PAID
21S-056 | C000015128 | X050 | P.S. 50 - BRONX | 1080758 | 82026 | CIP | Kowalski, Zbigniew | LAP Construction Phase Services | RFA | Closed | 2021-06-21 | 2900 | 2022-02-04 | 2022-04-02 | 4181 | 2023-06-28 | 7742.94 | 7742.94 | 0 | 799844 | 2023-07-19 | PAID
19S-281 | C000015128 | X062 | P.S. 62 - BRONX | 1003970 | 75093 | CIP | Zarrabi, Abdi | PO 18 Asbestos Service | RFA | Closed | 2019-12-27 | 500 | 2020-08-11 | 2020-08-19 | 4190 | 2023-09-06 | 22411.43 | 22411.43 | 0 | 805306 | 2023-10-06 | PAID
20S-063 | C000015128 | X066 | P.S. 66 - BRONX | 1052226 | 80086 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Amendment | Closed | 2020-11-23 | 500 | 2021-01-01 | 2021-01-16 | 4204 | 2024-04-05 | 18887.1 | 18887.1 | 0 | 821670 | 2024-05-29 | PAID
20S-019 | C000015128 | X074 | I.S. 201 - BRONX | 1034251 | 77151 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2020-06-25 | 250 | 2020-06-25 | 2020-06-29 | 4197 | 2023-10-31 | 11356.93 | 11356.93 | 0 | 813195 | 2024-02-02 | PAID
21S-107 | C000015128 | X132 | P.S. 132 - BRONX | 1099356 | 82902 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Amendment | Closed | 2021-11-19 |  | 2023-07-19 | 2023-07-21 | 4199 | 2024-02-01 | 5354.41 | 5354.41 | 0 | 826308 | 2024-07-30 | PAID
21S-109 | C000015128 | X151 | I.S. 151 - BRONX | 1097816 | 83513 | CIP | Alawamleh, Eman | LAP Construction Phase Services | RFA | Closed |  | 500 | 2022-01-27 | 2022-10-10 | 4176 | 2022-12-27 | 15437.96 | 15437.96 | 0 | 798123 | 2023-06-22 | PAID
21S-105 | C000015128 | X405 | HERBERT H. LEHMAN HS - BRONX | 1098818 | 83582 | CIP | Alawamleh, Eman | LAP Construction Phase Services | Initial | WIP | 2021-11-16 | 500 | [6 empty] | 0 |  |  | UNPAID
| C000015869 | K014 | I.S. 14 - BROOKLYN | 1129904 | 85451 | CIP | Clyne, Sean | LAP Construction Phase Services | Initial | WIP | 2022-07-12 | 9700 | [6 empty] | 0 |  |  | UNPAID
22S-057 | C000015869 | K016 | P.S. 16 - BROOKLYN | 1141526 | 86136 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | Closed | 2022-09-12 | 575 | 2022-11-03 | 2022-11-12 | 43 | 2023-10-11 | 17026.88 | 17026.88 | 0 | 806701 | 2023-10-25 | PAID
24S-012 | C000015869 | K017 | P.S. 17 - BROOKLYN | 1218759 | 90624 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | NEW | 2024-02-08 | 575 | [6 empty] | 0 |  |  | UNPAID
23S-093 | C000015869 | K019 | P.S. 19 - BROOKLYN | 1196510 | 89478 | CIP | Walsh, Joseph | LAP Construction Phase Services | Initial | Closed | 2023-09-22 | 90000 | 2023-10-06 | 2024-07-26 | 163 | 2025-05-12 | 70574.1 | 0 | -70574.1 |  |  | UNPAID
24S-108 | C000015869 | K027 | P.S. 27 - BROOKLYN | 1314173 | 93452 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-09-30 | 4000 | 2024-11-22 | 2024-11-23 | 245 | 2025-07-28 | 3552.53 | 0 | -3552.53 |  |  | UNPAID
| C000015869 | K043 | I.S. 98 - BROOKLYN | 1320962 | 93925 | CIP | Bracamonte, Jesus | Special Program | Initial | NEW | 2024-11-13 | 4100 | [6 empty] | 0 |  |  | UNPAID
24S-004 | C000015869 | K050 | J.H.S. 50 - BROOKLYN | 1219382 | 90587 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-02-16 | 18700 | [6 empty] | 0 |  |  | UNPAID
22S-075 | C000015869 | K051 | I.S. 51 - BROOKLYN | 1154680 | 86753 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | Closed | 2022-12-05 | 575 | 2023-07-14 | 2023-07-21 | 197 | 2025-06-16 | 12748.05 | 0 | -12748.05 |  |  | UNPAID
24S-072 | C000015869 | K051 | I.S. 51 - BROOKLYN | 1302806 | 92774 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-08-04 | 4000 | 2024-08-20 | 2024-08-21 | 156 | 2025-05-06 | 2236.93 | 2236.93 | 0 | 854005 | 2025-06-12 | PAID | CHECK 24S-072 K051
23S-016 | C000015869 | K054 | P.S. 54 - BROOKLYN | 1166957 | 87386 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | Closed | 2023-02-10 | 575 | 2023-03-23 | 2023-03-25 | 28 | 2023-07-11 | 6616.23 | 6616.23 | 0 | 799845 | 2023-07-19 | PAID
22S-055 | C000015869 | K055 | I.S. 55 - BROOKLYN | 1138365 | 86018 | CIP | Palermo, Albert | PO 18 Asbestos Service | RFA | Closed | 2022-09-06 | 19775 | 2022-09-20 | 2022-11-13 | 15 | 2022-06-21 | 27095.76 | 27095.76 | 0 | 807815 | 2023-11-09 | PAID
22S-027 | C000015869 | K055 | I.S. 55 - BROOKLYN | 1130690 | 85488 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2022-07-07 | 6075 | 2022-08-11 | 2022-08-14 | 80 | 2024-07-17 | 7902.2 | 7902.2 | 0 | 831865 | 2024-10-04 | PAID
23S-134 | C000015869 | K055 | I.S. 55 - BROOKLYN | 1208358 | 89203 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2023-12-05 | 21075 | 2024-04-04 | 2024-04-20 | 239 | 2025-07-24 | 25778.76 | 0 | -25778.76 |  |  | UNPAID
24S-090 | C000015869 | K061 | I.S. 61 - BROOKLYN | 1310278 | 93260 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2024-09-06 | 5575 | 2024-09-07 | 2024-09-07 | 213 | 2025-06-24 | 2905.59 | 0 | -2905.59 |  |  | UNPAID
23S-133 | C000015869 | K061 | I.S. 61 - BROOKLYN | 1211600 | 90221 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2023-12-27 | 575 | 2024-01-12 | 2024-01-13 | 78 | 2024-04-22 | 2731 | 2731 | 0 | 824707 | 2024-07-09 | PAID
24S-068 | C000015869 | K085 | P.S. 73 (OLD P85/STERLING HS) | 1301194 | 92638 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-07-24 | 4000 | 2024-08-01 | 2024-08-02 | 185 | 2025-06-05 | 2123.08 | 0 | -2123.08 |  |  | UNPAID
23S-017 | C000015869 | K086 | P.S. 86 - BROOKLYN | 1168027 | 87459 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | WIP | 2023-02-22 | 575 | [6 empty] | 0 |  |  | UNPAID
24S-063 | C000015869 | K095 | P.S. 95 - BROOKLYN | 1300411 | 92557 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-07-21 | 4000 | 2024-08-24 | 2024-10-13 | 154 | 2025-05-06 | 3574.99 | 3574.99 | 0 | 854006 | 2025-06-12 | PAID | CHECK 24S-063 K095
| C000015869 | K102 | P.S. 102 - BROOKLYN | 1306782 | 92043 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | NEW | 2024-08-29 | 575 | [6 empty] | 0 |  |  | UNPAID
24S-038 | C000015869 | K104 | P.S. 104 - BROOKLYN | 1237242 | 91880 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | NEW | 2024-05-23 | 9075 | [6 empty] | 0 |  |  | UNPAID
23S-087 | C000015869 | K110 | P.S. 110 - BROOKLYN | 1196133 | 89196 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | Closed | 2023-09-15 | 575 | 2023-10-03 | 2023-12-02 | 222 | 2025-06-27 | 37770.33 | 0 | -37770.33 |  |  | UNPAID
23S-067 | C000015869 | K111 | I.S. 111 - BROOKLYN | 1188750 | 88871 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | WIP | 2023-07-26 | [7 empty] | 0 |  |  | UNPAID
24S-079 | C000015869 | K114 | P.S. 114 - BROOKLYN | 1304841 | 92925 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-08-13 | 4000 | 2024-08-24 | 2024-08-25 | 166 | 2025-05-16 | 2454.75 | 2454.75 | 0 | 855119 | 2025-06-23 | PAID | CHECK 24S-079 K114
22S-085 | C000015869 | K127 | P.S. 127 - BROOKLYN | 1160020 | 86987 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | Closed | 2022-12-19 | 5175 | 2022-12-17 | 2022-12-31 | 97 | 2024-05-28 | 7813.38 | 7813.38 | 0 | 824627 | 2024-07-08 | PAID
22S-072 | C000015869 | K127 | P.S. 127 - BROOKLYN | 1156790 | 86876 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | Closed | 2022-12-07 | 15575 | 2022-12-08 | 2022-12-19 | 233 | 2025-07-24 | 28177.26 | 0 | -28177.26 |  |  | UNPAID
23S-029 | C000015869 | K128 | P.S. 128 - BROOKLYN | 1177163 | 88004 | CIP | Clyne, Sean | PO 18 Asbestos Service | Initial | Closed | 2023-04-25 | 7975 | 2023-07-06 | 2023-07-09 | 210 | 2025-06-20 | 9672.08 | 0 | -9672.08 |  |  | UNPAID
23S-049 | C000015869 | K128 | P.S. 128 - BROOKLYN | 1184671 | 88464 | CIP | Clyne, Sean | PO 18 Asbestos Service | Initial | Closed | 2023-06-21 | 8075 | 2023-06-23 | 2023-06-25 | 217 | 2025-06-26 | 6220.81 | 0 | -6220.81 |  |  | UNPAID
23S-104 | C000015869 | K136 | I.S. 136 - BROOKLYN | 1201696 | 89448 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | Closed | 2023-10-24 | 1575 | 2024-01-11 | 2024-02-17 | 128 | 2024-08-16 | 24419.64 | 24419.64 | 0 | 830191 | 2024-09-19 | PAID
| C000015869 | K138 | P.S. 138 - BROOKLYN | 1335922 | 94843 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | NEW | 2025-02-13 | 6275 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-066 | C000015869 | K142 | J.H.S. 142 - BROOKLYN | 1187574 | 88679 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | WIP | 2023-07-24 | [6 empty] | 0 | 0 |  |  | UNPAID
24S-103 | C000015869 | K145 | P.S. 145 - BROOKLYN | 1311813 | 93324 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | Closed | 2024-09-20 | 575 | 2024-11-27 | 2024-12-23 | 190 | 2025-06-05 | 20442.88 | 0 | -20442.88 |  |  | UNPAID
22S-054 | C000015869 | K149 | P.S. 149 - BROOKLYN | 1139236 | 85940 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2022-09-06 | 8975 | 2022-10-28 | 2022-11-19 | 52 | 2024-02-01 | 11479.15 | 11479.15 | 0 | 817450 | 2024-04-15 | PAID
23S-084 | C000015869 | K150 | P.S. 150 - BROOKLYN | 1195461 | 89302 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | WIP | 2023-09-12 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-061 | C000015869 | K151 | P.S. 151 - BROOKLYN | 1302568 | 92321 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | NEW | 2024-08-05 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-046 | C000015869 | K159 | P.S. 159 - BROOKLYN | 1136527 | 85893 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2022-08-15 | 5175 | 2022-10-06 | 2022-10-08 | 81 | 2024-04-29 | 6613.85 | 6613.85 | 0 | 825164 | 2024-07-15 | PAID
24S-014 | C000015869 | K160 | P.S. 160 - BROOKLYN | 1222094 | 90892 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | NEW | 2024-02-28 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-054 | C000015869 | K162 | I.S. 162 - BROOKLYN | 1244202 | 92352 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | NEW | 2024-07-02 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-064 | C000015869 | K162 | I.S. 162 - BROOKLYN | 1300412 | 92561 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-07-21 | 4000 | 2024-08-04 | 2024-08-04 | 150 | 2025-03-18 | 2284.61 | 2284.61 | 0 | 851724 | 2025-05-19 | PAID | CHECK 24S-064 K162
24S-136 | C000015869 | K164 | P.S. 164 - BROOKLYN | 1320983 | 93856 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | Closed | 2024-11-19 | 10000 | 2024-12-06 | 2024-12-08 | 228 | 2025-07-15 | 6517.93 | 0 | -6517.93 |  |  | UNPAID
24S-092 | C000015869 | K166 | I.S. 166 - BROOKLYN | 1308220 | 93184 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-09-04 | 4000 | 2024-09-22 | 2024-09-22 | 191 | 2025-06-13 | 2309 | 0 | -2309 |  |  | UNPAID
| C000015869 | K171 | I.S. 171 - BROOKLYN | 1320958 | 93926 | CIP |  | Special Program | Initial | NEW | 2024-11-13 | 4100 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-081 | C000015869 | K174 | P.S. 174 - BROOKLYN | 1304843 | 92927 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-08-13 | 4000 | 2024-08-25 | 2024-08-25 | 165 | 2025-05-16 | 2732.08 | 2732.08 | 0 | 855116 | 2025-06-23 | PAID | CHECK 24S-081 K174
23S-005 | C000015869 | K183 | P.S. 183 - BROOKLYN | 1160059 | 87043 | CIP | Palermo, Albert | PO 18 Asbestos Service | Amendment | WIP | 2023-01-10 | 5575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-077 | C000015869 | K183 | P.S. 183 - BROOKLYN | 1141523 | 86004 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2022-12-12 | 8575 | 2023-02-16 | 2023-02-20 | 121 | 2024-07-31 | 10543.6 | 10543.6 | 0 | 832141 | 2024-10-08 | PAID
24S-080 | C000015869 | K184 | P.S. 184 - BROOKLYN | 1304844 | 92928 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-08-13 | 4000 | 2024-08-31 | 2024-08-31 | 167 | 2025-05-16 | 3285.06 | 3285.06 | 0 | 855118 | 2025-06-23 | PAID | CHECK 24S-080 K184
| C000015869 | K224 | P.S. 224 - BROOKLYN | 1212815 | 90349 | CIP | Vafiadis, Jon | Special Program | Initial | NEW | 2024-01-12 | 1500 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-120 | C000015869 | K224 | P.S. 224 - BROOKLYN |  |  |  |  | SAFE ACCESS | Initial | [8 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | K226 | P.S. 126 - BROOKLYN | 1317417 | 93720 | CIP | Bracamonte, Jesus | Special Program | Initial | NEW | 2024-10-22 | 4100 | [5 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | K226 | P.S. 226 - BROOKLYN | 1317422 | 93720 | CIP | Bracamonte, Jesus | Special Program | Initial | NEW | 2024-10-22 | 7800.06 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-074 | C000015869 | K231 | P.S. 231 - BROOKLYN | 1302808 | 92767 | CIP | Bracamonte, Jesus | SAFE ACCESS | Initial | Closed | 2024-08-04 | 4000 | 2024-08-14 | 2024-08-14 | 141 | 2025-01-09 | 2483.03 | 2483.03 | 0 | 842240 | 2025-01-28 | PAID
24S-016 | C000015869 | K232 | I.S. 232 - BROOKLYN | 1223724 | 89776 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-03-13 | 13900 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-018 | C000015869 | K232 | I.S. 232 - BROOKLYN | 1223723 | 89768 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-03-14 | 13900 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-017 | C000015869 | K232 | I.S. 232 - BROOKLYN | 1223722 | 89766 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-03-14 | 13900 | [5 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | K233 | P.S. 233 - BROOKLYN | 1212811 | 90339 | CIP | Vafiadis, Jon | Special Program | Initial | NEW | 2024-01-11 | 1500 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-121 | C000015869 | K233 | P.S. 233 - BROOKLYN |  |  |  |  | SAFE ACCESS | Initial | [8 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | K244 | P.S. 244 - BROOKLYN | 1212812 | 90338 | CIP | Vafiadis, Jon | Special Program | Initial | NEW | 2024-01-11 | 1500 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-122 | C000015869 | K244 | P.S. 244 - BROOKLYN |  |  |  |  | SAFE ACCESS | Initial | [8 empty] | 0 | 0 |  |  | UNPAID
24S-082 | C000015869 | K246 | I.S. 246 - BROOKLYN | 1304840 | 92924 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-08-13 | 4000 | 2024-08-23 | 2024-08-24 | 159 | 2025-05-07 | 2629.78 | 2629.78 | 0 | 854350 | 2025-06-16 | PAID | CHECK 24S-082 K246
| C000015869 | K250 | P.S. 250 - BROOKLYN | 1212797 | 90325 | CIP | Vafiadis, Jon | Special Program | Initial | NEW | 2024-01-11 | 1500 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-131 | C000015869 | K250 | P.S. 250 - BROOKLYN |  |  |  |  | SAFE ACCESS | Initial | [8 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | K260 | P.S. 260 - BROOKLYN | 1212816 | 90348 | CIP | Vafiadis, Jon | Special Program | Initial | NEW | 2024-01-12 | 1500 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-123 | C000015869 | K260 | P.S. 260 - BROOKLYN |  |  |  |  | SAFE ACCESS | Initial | [8 empty] | 0 | 0 |  |  | UNPAID
24S-007 | C000015869 | K261 | P.S. 261 - BROOKLYN | 1220932 | 90763 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-02-21 | 14900 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-009 | C000015869 | K263 | P.S./I.S. 323 - BROOKLYN | 1162471 | 87190 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2023-01-26 | 10175 | 2023-04-27 | 2023-05-06 | 111 | 2024-06-24 | 10960.83 | 10960.83 | 0 | 829476 | 2024-09-12 | PAID
24S-066 | C000015869 | K265 | I.S. 265 - BROOKLYN | 1301193 | 92598 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-07-24 | 4000 | 2024-08-08 | 2024-08-09 | 225 | 2025-07-07 | 2562.91 | 0 | -2562.91 |  |  | UNPAID
| C000015869 | K273 | P.S. 273 - BROOKLYN | 1212817 | 90347 | CIP | Vafiadis, Jon | Special Program | Initial | NEW | 2024-01-12 | 1500 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-124 | C000015869 | K273 | P.S. 273 - BROOKLYN |  |  |  |  | SAFE ACCESS | Initial | [8 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | K276 | P.S. 276 - BROOKLYN | 1212812 | 90337 | CIP | Vafiadis, Jon | Special Program | Initial | NEW | 2024-01-12 | 1500 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-125 | C000015869 | K276 | P.S. 276 - BROOKLYN |  |  |  |  | SAFE ACCESS | Initial | [8 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | K279 | P.S. 279 - BROOKLYN | 1212814 | 90336 | CIP | Vafiadis, Jon | Special Program | Initial | NEW | 2024-01-12 | 1500 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-126 | C000015869 | K279 | P.S. 279 - BROOKLYN |  |  |  |  | SAFE ACCESS | Initial | [8 empty] | 0 | 0 |  |  | UNPAID
23S-079 | C000015869 | K287 | P.S. 287 - BROOKLYN | 1191864 | 89110 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | Closed | 2023-08-16 | 575 | 2024-03-21 | 2024-08-23 | 157 | 2025-05-06 | 24201.38 | 24201.38 | 0 | 852980 | 24201.38 | PAID | CHECK 23S-079 K287
| C000015869 | K287 | P.S. 287 - BROOKLYN | 1212544 | 90316 | CIP | Vafiadis, Jon | Special Program | Initial | NEW | 2024-01-11 | 1500 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-130 | C000015869 | K287 | P.S. 287 - BROOKLYN |  |  |  |  | SAFE ACCESS | Initial | [8 empty] | 0 | 0 |  |  | UNPAID
23S-050 | C000015869 | K289 | P.S. 289 - BROOKLYN | 1183304 | 88347 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2023-06-16 | 7575 | 2023-07-27 | 2023-07-29 | 123 | 2024-08-01 | 7078.33 | 7078.33 | 0 | 832411 | 2024-10-10 | PAID
24S-045 | C000015869 | K316 | P.S. 16 - BROOKLYN | 1238681 | 91953 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2024-05-30 | 15400 | 2024-06-19 | 2024-07-20 | 199 | 2025-06-16 | 5530.33 | 5530.33 | 0 | 855121 | 2025-06-23 | PAID | CHECK 24S-045 K316
24S-126 | C000015869 | K316 | P.S. 16 - BROOKLYN | 1323387 | 94073 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2024-11-27 | 5275 | 2024-11-23 | 2024-11-24 | 206 | 2025-06-17 | 3276.11 | 0 | -3276.11 |  |  | UNPAID
22S-035 | C000015869 | K324 | I.S. 324 - BROOKLYN | 1132555 | 85598 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2022-07-20 | 26020 | 2022-07-15 | 2024-06-09 | 232 | 2025-07-24 | 28774.67 | 0 | -28774.67 |  |  | UNPAID
23S-075 | C000015869 | K335 | P.S. 335 - BROOKLYN | 1189823 | 88936 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | WIP | 2023-08-14 | [6 empty] | 0 | 0 |  |  | UNPAID
23S-072 | C000015869 | K335 | P.S. 335 - BROOKLYN | 1189824 | 88935 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2023-08-11 | 575 | 2023-10-05 | 2023-10-14 | 73 | 2024-04-16 | 20514.03 | 20514.03 | 0 | 824531 | 2024-07-05 | PAID
23S-042 | C000015869 | K364 | P.S. 364 - BROOKLYN | 1184787 | 88107 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2023-07-12 | 11575 | 2023-07-24 | 2023-07-26 | 47 | 2023-10-17 | 7578.28 | 7578.28 | 0 | 813787 | 2024-02-13 | PAID
| C000015869 | K370 | P.S. 370 - BROOKLYN | 1317423 |  | CIP | Bracamonte, Jesus | Special Program | Initial | NEW | 2024-10-22 | 7800.06 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-121 | C000015869 | K370 | P.S. 370 - BROOKLYN | 1317418 | 93721 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-10-22 | 4100 | 2024-10-29 | 2024-10-30 | 193 | 2025-07-07 | 2211.51 | 0 | -2211.51 |  |  | UNPAID
| C000015869 | K384 | P.S. 384 - BROOKLYN | 1334321 | 94618 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | NEW | 2025-02-04 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
24s-109 | C000015869 | K425 | JAMES MADISON HS - BROOKLYN | 1314171 | 93480 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-09-30 | 4000 | 2024-11-01 | 2024-12-23 | 194 | 2025-06-16 | 4725.83 | 0 | -4725.83 |  |  | UNPAID
23S-069 | C000015869 | K445 | NEW UTRECHT HS - BROOKLYN | 1187087 | 88602 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | Closed | 2023-07-13 | 575 | 2023-08-08 | 2024-02-22 | 107 | 2024-06-12 | 29861.89 | 29861.89 | 0 | 827033 | 2024-08-12 | PAID
24S-107 | C000015869 | K445 | NEW UTRECHT HS - BROOKLYN | 1314172 | 93454 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-09-30 | 4000 | 2024-11-29 | 2024-11-29 | 177 | 2025-06-03 | 2849.88 | 0 | -2849.88 |  |  | UNPAID
| C000015869 | K455 | BOYS & GIRLS HS - BROOKLYN | 1302807 | 92773 | CIP | Bracamonte, Jesus | Special Program | Initial | NEW | 2024-08-04 | 4000 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-124 | C000015869 | K486 | I.S. 187 - BROOKLYN | 1319899 | 93871 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2024-11-27 | 5275 | 2024-11-30 | 2024-11-30 | 204 | 2025-06-17 | 2747.64 | 0 | -2747.64 |  |  | UNPAID
| C000015869 | K495 | FRANK J MACCHIAROLA EDU COMPLEX | 1310002 | 93224 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-09-25 | 16345 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-110 | C000015869 | K505 | FRANKLIN D ROOSEVELT HS - BROOKLYN | 1314174 | 93451 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-09-30 | 4000 | 2024-10-14 | 2024-10-14 | 178 | 2025-06-03 | 2720.1 | 0 | -2720.1 |  |  | UNPAID
24S-119 | C000015869 | K515 | SOUTH SHORE EDU COMPLEX - BROOKLYN | 1317424 | 93750 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-10-22 | 7800.06 | 2024-11-30 | 2024-12-28 | 244 | 2025-07-24 | 5128.76 | 0 | -5128.76 |  |  | UNPAID
| C000015869 | K515 | SOUTH SHORE EDU COMPLEX - BROOKLYN | 1317419 | 93750 | CIP |  | Special Program | Initial | NEW | 2024-10-22 | 4100 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-064 | C000015869 | K600 | CLARA BARTON HS - BROOKLYN | 1148840 | 85963 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2022-10-20 | 5475 | 2023-02-02 | 1900-01-22 | 54 | 2024-02-06 | 6733.25 | 6733.25 | 0 | 819514 | 2024-05-08 | PAID
24S-030 | C000015869 | K600 | CLARA BARTON HS - BROOKLYN | 1231082 | 91760 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2024-05-03 | 9675 | 2024-06-20 | 2024-06-23 | 209 | 2025-06-20 | 16741.46 | 0 | -16741.46 |  |  | UNPAID
23S-008 | C000015869 | K600 | CLARA BARTON HS - BROOKLYN | 1160045 | 87001 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-01-24 | 21345 | 2023-09-28 | 2023-10-01 | 120 | 2024-07-31 | 11247.98 | 11247.98 | 0 | 828331 | 2024-08-28 | PAID
22S-051 | C000015869 | K600 | CLARA BARTON HS - BROOKLYN | 1138802 | 86052 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2022-08-26 | 29462.38 | 2022-12-20 | 2024-02-04 | 171 | 2025-05-28 | 23934.9 | 23934.9 | 0 | 854348 | 2025-06-16 | PAID | CHECK 22S-051 K600
| C000015869 | K615 | E NY VOC HS OF TRANSIT TECH - BROOKLYN | 1210691 | 90158 | CIP | Palermo, Albert | PO 18 Asbestos Service | Amend 1 | NEW | 2023-12-19 | 5375 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-026 | C000015869 | K620 | WILLIAM E GRADY VOC HS - BROOKLYN | 1224928 | 91352 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-03-27 | 12400 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-062 | C000015869 | K650 | HARRY VANARSDALE VOC HS(WHITNEY) - BROOKLYN | 1245092 | 92439 | CIP | Walsh, Joseph | PO 18 Asbestos Service | Initial | Closed | 2024-07-10 | 575 | 2024-09-28 | 2024-09-29 | 246 | 2025-07-28 | 4484.75 | 0 | -4484.75 |  |  | UNPAID
24S-141 | C000015869 | K799 | BKLYN EAST ALT LEARNING CENTER - BROOKLYN | 1326820 | 94278 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2024-12-17 | 4100 | 2024-12-27 | 2024-12-27 | 183 | 2025-06-04 | 2354.13 | 0 | -2354.13 |  |  | UNPAID
23S-081 | C000015869 | K804 | COBBLE HILL SCL OF AMR STD (OL6) - BROOKLYN | 1194796 | 88907 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | WIP | 2023-09-05 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-037 | C000015869 | K845 | P.S. 295 - BROOKLYN | 1138182 | 85820 | CIP | Scott, Richard | PO 18 Asbestos Service | RFA | Closed | 2022-07-28 | 6375 | 2022-08-04 | 2022-08-07 | 17 | 2023-06-22 | 9715.23 | 9715.23 | 0 | 800027 | 2023-07-24 | PAID
| C000015869 | K851 | P.S. 159 MINI SCHOOL - BROOKLYN | 1320959 | 93959 | CIP | Bracamonte, Jesus | SAFE ACCESS | Initial | NEW | 2024-11-13 | 4100 | [5 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | K854 | P.S. 178 AX (BED STUY ECC 1) - BROOKLYN | 1327986 | 94350 | CIP |  | PO 18 Asbestos Service | Initial | NEW | 2024-12-26 | 4100 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-056 | C000015869 | K872 | I.S. 364 ANNEX - BROOKLYN | 1140683 | 86135 | CIP | Palermo, Albert | PO 18 Asbestos Service | Initial | Closed | 2022-09-12 | 11575 | 2022-10-27 | 2022-11-26 | 53 | 2024-02-01 | 15829.9 | 15829.9 | 0 | 819271 | 2024-05-08 | PAID
24S-069 | C000015869 | K874 | I.S. 340 (OLD 249 AX) - BROOKLYN | 1301195 | 92644 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-07-24 | 4000 | 2024-08-11 | 2024-08-11 | 208 | 2025-06-20 | 2830.21 | 0 | -2830.21 |  |  | UNPAID
24S-087 | C000015869 | K932 | HIGH SCHOOL SUSPENSION CENTER - BROOKLYN | 1305383 | 92976 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | NEW | 2024-08-16 | 4000 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-037 | C000015869 | M001 | P.S. 1 - MANHATTAN | 1182354 | 74694 | CIP |  | LAP Construction Phase Services | Initial | WIP | 2023-06-05 | 19000 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-094 | C000015869 | M022 | M022 N.E.S.T (OLD J22) - MANHATTAN | 1200324 | 89727 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2024-10-03 | 5500 | 2023-10-03 | 2023-10-04 | 66 | 2024-03-26 | 2511.13 | 2511.13 | 0 | 820328 | 2024-05-15 | PAID
24S-022 | C000015869 | M028 | P.S. 28 - MANHATTAN | 1224747 | 91258 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2024-03-20 | 575 | 2024-08-01 | 2024-08-03 | 240 | 2025-07-24 | 6730.39 | 0 | -6730.39 |  |  | UNPAID
24S-078 | C000015869 | M028 | P.S. 28 - MANHATTAN | 1305847 | 93050 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2024-08-16 | 575 | 2024-08-15 | 2024-08-18 | 214 | 2025-06-24 | 9069.99 | 0 | -9069.99 |  |  | UNPAID
22S-047 | C000015869 | M046 | P.S. 46 - MANHATTAN | 1142123 | 86125 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | RFA | Closed | 2022-08-23 | 300 | 2022-08-23 | 2022-08-26 | 41 | 2023-09-15 | 5954.03 | 5954.03 | 0 | 807569 | 2023-11-08 | PAID
24S-048 | C000015869 | M050 | P.S. 50 (UDC) - MANHATTAN | 1240803 | 91997 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | NEW | 2024-06-10 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | M061 | P.S. 61 - MANHATTAN | 1301457 | 92654 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | NEW | 2024-07-25 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-042 | C000015869 | M064 | P.S. 64 (OLD 71) - MANHATTAN | 1301470 | 91998 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2024-06-07 | 24375 | 2024-06-06 | 2024-07-07 | 200 | 2025-06-16 | 30605.65 | 0 | -30605.65 |  |  | UNPAID
23S-033 | C000015869 | M066 | RICHARD R GREEN HS OF TEACHING - MANHATTAN | 1169343 | 87470 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2023-05-04 | 16575 | 2024-04-11 | 2024-04-21 | 236 | 2025-07-24 | 19912.42 | 19912.42 | 0 |  |  | UNPAID
22S-017 | C000015869 | M070 | I.S. 70 - MANHATTAN | 1126983 | 85293 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | RFA | Closed | 2022-06-08 | 575 | 2022-07-24 | 2022-08-02 | 20 | 2023-06-23 | 21497.37 | 21497.37 | 0 |  | 2023-08-08 | PAID
23S-100 | C000015869 | M081 | MID MAN ADULT LRNG CTR (81) - MANHATTAN | 1193755 | 89109 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2023-08-23 | 575 | 2024-04-22 | 2024-04-24 | 143 | 2025-01-09 | 6575.51 | 6575.51 | 0 |  | 2025-02-11 | PAID
22S-043 | C000015869 | M098 | P.S. 98 - MANHATTAN | 1136220 | 85864 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2022-08-10 | 575 | 2023-01-12 | 2023-01-28 | 48 | 2023-10-17 | 17824.18 | 17824.18 | 0 | 808704 | 2023-11-27 | PAID
| C000015869 | M099 | I.S. 99 - MANHATTAN | 1327637 | 94204 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | NEW | 2024-12-13 | 7575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-011 | C000015869 | M110 | P.S. 110 - MANHATTAN | 1129736 | 85354 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2022-06-03 | 9575 | 2022-06-03 | 2022-06-04 | 151 | 2025-05-05 | 5589.53 | 5589.53 | 0 | 852979 | 2025-06-03 | PAID | CHECK 22S-011 M110
24S-049 | C000015869 | M115 | P.S. 115 - MANHATTAN | 1241224 | 92097 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-06-12 | 20200 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-095 | C000015869 | M115 | P.S. 115 - MANHATTAN | 1197647 | 89597 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-10-04 | 575 | 2023-10-05 | 2023-10-07 | 138 | 2024-08-21 | 6672.58 | 6672.58 | 0 | 841880 | 2025-01-23 | PAID
23S-045 | C000015869 | M115 | P.S. 115 - MANHATTAN | 1182352 | 88295 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-06-08 | 575 | 2023-07-20 | 2023-10-07 | 181 | 2025-06-03 | 60014.45 | 60014.45 | 0 | 855122 | 2025-06-23 | PAID | CHECK 23S-045 M115
| C000015869 | M124 | P.S. 124 (ECF) - MANHATTAN | 1316025 | 93166 | CIP |  | PO 18 Asbestos Service | Initial | NEW | 2024-10-10 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | M125 | P.S. 125 - MANHATTAN | 1303172 | 92796 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-08-06 | 15445 | [5 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | M125 | P.S. 125 - MANHATTAN | 1335879 | 94453 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2025-02-20 | 16200 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-054 | C000015869 | M128 | P.S. 128 - MANHATTAN | 1186684 | 88621 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-07-06 | 575 | 2023-09-20 | 2023-09-30 | 106 | 2024-06-12 | 17521.67 | 17521.67 | 0 | 826173 | 2024-07-29 | PAID
23S-136 | C000015869 | M128 | P.S. 128 - MANHATTAN | 1211273 | 90120 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-12-19 | 575 | 2024-10-01 | 2024-10-04 | 231 | 2025-07-16 | 9659.2 | 0 | -9659.2 |  |  | UNPAID
22S-019 | C000015869 | M129 | P.S. 129 - MANHATTAN | 1127850 | 85282 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | RFA | Closed | 2022-06-10 | 575 | 2022-07-28 | 2022-07-31 | 13 | 2023-06-20 | 8548.59 | 8548.59 | 0 | 802867 | 2023-09-05 | PAID
22S-065 | C000015869 | M129 | P.S. 129 - MANHATTAN | 1149690 | 86609 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | RFA | Closed | 2022-10-29 | 575 | 2022-10-29 | 2022-11-05 | 40 | 2023-09-15 | 15915.63 | 15915.63 | 0 | 808703 | 2023-11-27 | PAID
23S-036 | C000015869 | M133 | P.S. 133 - MANHATTAN | 1179854 | 88183 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-05-17 | 575 | 2023-05-19 | 2023-05-21 | 87 | 2024-05-06 | 6212.43 | 6212.43 | 0 | 824039 | 2024-07-01 | PAID
22S-066 | C000015869 | M136 | I.S. 136 - MANHATTAN | 1149650 | 86514 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2022-11-07 | 25000 | 2023-02-16 | 2023-02-25 | 95 | 2024-05-24 | 11844.74 | 11844.74 | 0 | 824629 | 2024-07-08 | PAID
22S-068 | C000015869 | M137 | P.S. 137 - MANHATTAN | 1150094 | 86602 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Amendment | Closed | 2022-11-09 | 575 | 2023-01-12 | 2023-01-21 | 38 | 2023-08-01 | 16393.86 | 16393.86 | 0 | 803195 | 2023-09-11 | PAID
22S-018 | C000015869 | M137 | P.S. 137 - MANHATTAN | 1126982 | 85286 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2022-06-08 | 575 | 2022-12-22 | 2022-12-28 | 140 | 2024-12-19 | 19983.26 | 19983.26 | 0 | 841881 | 2025-01-23 | PAID
23S-015 | C000015869 | M144 | P.S. 242 (OLD 144) - MANHATTAN | 1166775 | 87340 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2023-02-08 | 575 | 2023-10-26 | 2023-10-28 | 109 | 2024-06-17 | 7130.58 | 7130.58 | 0 | 826174 | 2024-07-29 | PAID
24S-053 | C000015869 | M152 | P.S. 152 - MANHATTAN | 1243709 | 92223 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | NEW | 2024-02-21 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-039 | C000015869 | M155 | I.S. 155 - MANHATTAN | 1180534 | 88234 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2023-05-23 | 575 | 2023-06-09 | 2023-06-10 | 61 | 2024-03-08 | 5751.75 | 5751.75 | 0 | 819023 | 2024-05-02 | PAID
24S-023 | C000015869 | M163 | P.S. 163 - MANHATTAN | 1225180 | 91391 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | NEW | 2024-03-26 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-050 | C000015869 | M164 | I.S. 164 - MANHATTAN | 1138190 | 85906 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | RFA | Closed | 2022-08-09 | 20345 | 2022-11-13 | 2023-04-11 | 19 | 2023-06-22 | 25350.54 | 25350.54 | 0 | 799865 | 2023-07-20 | PAID
22S-014 | C000015869 | M165 | P.S. 165 - MANHATTAN | 1131052 | 85304 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | RFA | Closed | 2022-06-11 | 10575 | 2022-06-11 | 2022-08-30 | 22 | 2023-06-27 | 7140.93 | 7140.93 | 0 | 800530 | 2023-07-31 | PAID
23S-078 | C000015869 | M169 | P.S. 169 (ECF) - MANHATTAN | 1191264 | 88870 | CIP | Lazicki, Rafal | LAP Construction Phase Services | Initial | WIP | 2023-08-15 | 11190 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-114 | C000015869 | M180 | P.S. 180 - MANHATTAN | 1315970 | 93632 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2024-10-10 | 575 | 2024-10-18 | 2024-10-19 | 202 | 2025-06-17 | 4759.59 | 0 | -4759.59 |  |  | UNPAID
22S-053 | C000015869 | M185 | P.S. 185 (TANDEM M208) - MANHATTAN | 1141636 | 86051 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2022-09-01 | 9300 | 2022-09-01 | 2022-09-03 | 23 | 2023-06-27 | 7033.25 | 7033.25 | 0 | 800529 | 2023-07-31 | PAID
24S-003 | C000015869 | M187 | P.S./I.S 187 - MANHATTAN | 1216944 | 90610 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2024-02-05 | 575 | 2024-01-23 | 2024-02-18 | 131 | 2024-08-23 | 17848.38 | 17848.38 | 0 | 834096 | 2024-10-25 | PAID
24S-006 | C000015869 | M192 | P.S. 192 - MANHATTAN | 1218023 | 90701 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | NEW | 2024-02-05 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | M192 | P.S. 192 - MANHATTAN | 1322940 | 94022 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | NEW | 2024-11-18 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-101 | C000015869 | M197 | P.S. 197 - MANHATTAN | 137330 | 89611 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-10-12 | 575 | 2024-04-12 | 2024-04-14 | 139 | 2024-12-03 | 8303.85 | 8303.85 | 0 | 842154 | 2025-01-24 | PAID
22S-045 | C000015869 | M435 | MANHTN CT FOR MATH & SCI. HS - MANHATTAN | 1135506 | 85822 | CIP | Lazicki, Rafal | LAP Construction Phase Services | Initial | Closed | 2022-08-04 | 7000 | 2022-12-28 | 2023-06-08 | 108 | 2024-06-12 | 13333.61 | 13333.61 | 0 | 826175 | 2024-07-29 | PAID
24S-002 | C000015869 | M440 | BAYARD RUSTIN EDUCATIONAL COMPLEX - MANHATTAN | 1213594 | 90375 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | NEW | 2024-01-10 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-028 | C000015869 | M440 | BAYARD RUSTIN EDUCATIONAL COMPLEX - MANHATTAN | 1177691 | 88001 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2023-04-28 | 6075 | 2023-04-21 | 2023-04-21 | 124 | 2024-08-05 | 2603.21 | 2603.21 | 0 | 828521 | 2024-08-30 | PAID
24S-024 | C000015869 | M465 | G. WASHINGTON HS EDUC. CAMPUS - M465 | 1225222 | 91363 | CIP |  | PO 18 Asbestos Service | Initial | NEW | 2024-02-11 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-113 | C000015869 | M465 | G. WASHINGTON HS EDUC. CAMPUS - M465 | 1204463 | 89908 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-11-09 | 575 | 2023-11-09 | 2023-11-12 | 101 | 2024-06-05 | 7865.63 | 7865.63 | 0 | 824708 | 2024-07-09 | PAID
| C000015869 | M470 | LOUIS D. BRANDEIS HS - MANHATTAN | 1198033 | 89608 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Initial | 2023-10-03 | 19020 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-076 | C000015869 | M470 | LOUIS D. BRANDEIS HS - MANHATTAN | 1156228 | 86844 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2022-12-08 | 20220 | 2022-12-19 | 2023-12-27 | 110 | 2024-06-19 | 26234.98 | 26234.98 | 0 | 825055 | 2024-07-12 | PAID
24S-134 | C000015869 | M480 | JULIA RICHMAN ED. COMPLEX - M480 | 1334563 | 94196 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2025-01-25 | 6575 | 2025-01-25 | 2025-01-26 | 155 | 2025-05-06 | 2437.03 | 2437.03 | 0 | 853126 | 2025-06-04 | PAID | CHECK 24S-134 M480
23S-019 | C000015869 | M490 | MARTIN LUTHER KING, JR. HS - MANHATTAN | 1167441 | 87398 | CIP | Lazicki, Rafal | LAP Construction Phase Services | Initial | Closed | 2023-02-16 | 8035 | 2023-03-02 | 2023-07-29 | 72 | 2024-04-09 | 18216.88 | 18216.88 | 0 | 829815 | 2024-09-17 | PAID
22S-063 | C000015869 | M490 | MARTIN LUTHER KING, JR. HS - MANHATTAN | 1147501 | 86372 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2022-10-19 | 14345 | 2023-02-17 | 2023-02-19 | 76 | 2024-04-18 | 6509.07 | 6509.07 | 0 | 819831 | 2024-05-10 | PAID
22S-002 | C000015869 | M512 | 3 K CENTER @ 163-165 EAST 84TH STREET - MANHATTAN | 1118075 | 84666 | CIP | Lazicki, Rafal | LAP Construction Phase Services | RFA | Closed | 2022-04-01 | 22000 | 2022-04-05 | 2022-09-03 | 3 | 2022-11-09 | 38819.14 | 38819.14 | 0 | 787514 | 2022-11-09 | PAID
23S-048 | C000015869 | M520 | MURRAY BERGTRAUM HS (ECF) - MANHATTAN | 1186758 | 87328 | CIP | Lazicki, Rafal | LAP Construction Phase Services | Initial | Closed | 2023-07-19 | 19000 | 2023-05-17 | 2023-12-19 | 113 | 2024-07-05 | 31267.67 | 31267.67 | 0 | 827383 | 2024-08-15 | PAID
23S-060 | C000015869 | M520 | MURRAY BERGTRAUM HS (ECF) - MANHATTAN | 1186745 | 87777 | CIP | Lazicki, Rafal | LAP Construction Phase Services | Initial | Closed | 2023-07-19 | 500 | 2023-08-04 | 2023-08-05 | 149 | 2025-03-13 | 2131.98 | 2131.98 | 0 | 852978 | 2025-06-03 | PAID | CHECK 23S-060 M520
| C000015869 | M528 | I.S. 528 - MANHATTAN | 1126308 | 85125 | CIP | Alawamleh, Eman | LAP Construction Phase Services | Initial | WIP | 2022-05-31 | 500 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-049 | C000015869 | M600 | FASHION INDUSTRIES VOC HS - MANHATTAN | 1138188 | 85959 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2022-08-26 | 19845 | 2022-10-27 | 2023-12-11 | 82 | 2024-05-01 | 30284.62 | 30284.62 | 0 | 820909 | 2024-05-21 | PAID
22S-070 | C000015869 | M615 | CHELSEA VOC HS - MANHATTAN | 1158465 | 86969 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2022-12-02 | 9075 | 2022-12-02 | 2022-12-05 | 25 | 2023-07-06 | 12766 | 12766 | 0 | 800963 | 2023-08-04 | PAID
24S-071 | C000015869 | M615 | CHELSEA VOC HS - MANHATTAN | 1301468 | 92332 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2024-07-25 | 575 | 2024-10-31 | 2024-11-02 | 164 | 2025-05-15 | 6586.68 | 6586.68 | 0 | 853439 | 2025-06-06 | PAID | CHECK 24S-071 M615
22S-005 | C000015869 | M620 | NORMAN THOMAS HS (ECF) - MANHATTAN | 1123363 | 84986 | CIP | Lazicki, Rafal | LAP Construction Phase Services | RFA | Closed | 2022-06-06 | 500 | 2022-07-14 | 2022-07-18 | 21 | 2023-06-23 | 21825.8 | 21825.8 | 0 | 800470 | 2023-07-28 | PAID
24S-140 | C000015869 | M660 | SCHL OF THE FUTURE (OLD BACON) - MANHATTAN | 1333677 | 94298 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2024-12-20 | 5000 | 2024-12-20 | 2024-12-21 | 205 | 2025-06-17 | 2243.94 | 0 | -2243.94 |  |  | UNPAID
23S-119 | C000015869 | M844 | P.S. 138 ANNEX (OLD M047 AX) | 1214485 | 89905 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2023-12-08 | 7800 | 2023-12-08 | 2023-12-09 | 198 | 2025-06-16 | 2131.98 | 0 | -2131.98 |  |  | UNPAID
23S-031 | C000015869 | Q014 | P.S. 14 - QUEENS | 1179823 | 88171 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-05-16 | 4400 | 2023-05-13 | 2023-05-14 | 104 | 2024-06-11 | 4293.03 | 4293.03 | 0 | 824043 | 2024-07-01 | PAID
22S-030 | C000015869 | Q015 | P.S. 15 - QUEENS | 1133898 | 85649 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-07-13 | 9375 | 2022-07-13 | 2022-07-16 | 99 | 2024-05-30 | 8999.02 | 8999.02 | 0 | 824628 | 2024-07-08 | PAID
24S-025 | C000015869 | Q021 | P.S. 21 - QUEENS | 1224438 | 91310 | CIP |  | PO 18 Asbestos Service | Initial | NEW | 2024-03-27 | 4100 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-073 | C000015869 | Q022 | P.S. 22 - QUEENS | 1189469 | 88744 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-08-02 | 575 | 2024-10-30 | 2024-11-09 | 219 | 2025-06-26 | 13872.14 | 0 | -13872.14 |  |  | UNPAID
24S-031 | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1243757 | 92210 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2024-06-21 | 4100 | 2024-05-04 | 2024-05-05 | 135 | 2024-10-10 | 4933.3 | 4933.3 | 0 | 835020 | 2024-11-06 | PAID
24S-060 | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1243867 | 92257 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2024-07-02 | 575 | 2024-07-11 | 2024-07-12 | 153 | 2025-05-06 | 6963.25 | 6963.25 | 0 | 853127 | 2025-06-04 | PAID | CHECK 24S-060 Q023
24S-051 | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1233398 | 91807 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2024-05-04 | 4400 | 2024-06-22 | 2024-06-22 | 174 | 2025-06-03 | 1901 | 1901 | 0 | 854823 | 2025-06-20 | PAID | CHECK 24S-051 Q023
24S-047 | C000015869 | Q024 | P.S. 24 - QUEENS | 1239285 | 91978 | CIP |  | PO 18 Asbestos Service | Initial | NEW | 2024-06-05 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-070 | C000015869 | Q029 | P.S. 29 - QUEENS | 1187894 | 88759 | CIP | Kondilis, Milton | LAP Construction Phase Services | Initial | Closed | 2023-07-25 | 14735 | 2023-09-07 | 2024-07-25 | 237 | 2025-07-24 | 16573.38 | 0 | -16573.38 |  |  | UNPAID
23S-062 | C000015869 | Q030 | P.S. 30 - QUEENS | 1186771 | 88617 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-07-19 | 575 | 2024-02-01 | 2024-02-18 | 125 | 2024-08-09 | 20699.7 | 20699.7 | 0 | 829475 | 2024-09-12 | PAID
23S-011 | C000015869 | Q035 | P.S. 35 - QUEENS | 1163182 | 87037 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-01-31 | 575 | 2023-08-03 | 2023-10-09 | 102 | 2024-06-10 | 71368.5 | 71368.5 | 0 | 826307 | 2024-07-30 | PAID
24S-036 | C000015869 | Q037 | P.S. 37 - QUEENS | 1232763 | 91803 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-05-10 | 15400 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-035 | C000015869 | Q037 | P.S. 37 - QUEENS | 1232764 | 91801 | CIP |  | LAP Construction Phase Services | Initial | NEW | 2024-05-10 | 11700 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-077 | C000015869 | Q038 | P.S. 38 - QUEENS | 1190869 | 88352 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-08-14 | 27418.09 | 2024-09-12 | 2024-09-28 | 152 | 2025-05-06 | 27200.01 | 27200.01 | 0 | 853280 | 2025-06-05 | PAID | CHECK 23S-077 Q038
22S-038 | C000015869 | Q059 | I.S. 59 - QUEENS | 1133896 | 85646 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-07-28 | 575 | 2022-10-07 | 2022-12-30 | 137 | 2024-10-28 | 32571.72 | 32571.72 | 0 | 839873 | 2024-12-30 | PAID
23S-089 | C000015869 | Q060 | P.S.60 - QUEENS | 1197103 | 89472 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-09-22 | 4375 | 2023-09-22 | 2023-09-23 | 60 | 2024-03-04 | 3397.18 | 3397.18 | 0 | 816891 | 2024-04-02 | PAID
| C000015869 | Q061 | I.S. 61 - QUEENS | 1124663 | 85105 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | WIP | 2022-05-24 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-027 | C000015869 | Q067 | J.H.S. 67 - QUEENS | 1225935 | 90816 | CIP |  | PO 18 Asbestos Service | Initial | NEW | 2024-04-02 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-047 | C000015869 | Q079 | I.S. 79 - QUEENS | 1182975 | 88112 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | WIP | 2023-06-07 | [6 empty] | 0 | 0 |  |  | UNPAID
22S-074 | C000015869 | Q085 | P.S. 85 - QUEENS | 1157266 | 86894 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | RFA | Closed | 2022-12-10 | 5000 | 2022-12-10 | 2022-12-11 | 27 | 2023-07-11 | 5249.18 | 5249.18 | 0 | 799711 | 2023-07-18 | PAID
24S-076 | C000015869 | Q089 | P.S. 89 - QUEENS | 1302817 | 91977 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2024-08-09 | 575 | 2025-04-10 | 2025-04-15 | 184 | 2025-06-04 | 11142.81 | 11142.81 | 0 | 854143 | 2025-06-13 | PAID | CHECK 24S-076 Q089
22S-025 | C000015869 | Q112 | P.S. 112 - QUEENS | 1129728 | 84939 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2022-06-30 | 575 | 2022-12-15 | 2023-12-18 | 116 | 2024-07-31 | 23786.87 | 23786.87 | 0 | 828151 | 2024-08-27 | PAID
23S-088 | C000015869 | Q116 | P.S. 116 - QUEENS | 1196944 | 89473 | CIP | Kondilis, Milton | PO 18 Asbestos Service | RFA | Closed | 2023-09-25 | 6400 | 2023-09-21 | 2023-09-26 | 63 | 2024-03-18 | 5116.55 | 5116.55 | 0 | 819272 | 2024-05-08 | PAID
| C000015869 | Q122 | P.S. 122 - QUEENS | 1125492 | 85171 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | WIP | 2022-05-25 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-108 | C000015869 | Q122 | P.S. 122 - QUEENS | 1203131 | 89849 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-10-27 | 3775 | 2023-10-27 | 2023-10-28 | 220 | 2025-06-26 | 2244.92 | 0 | -2244.92 |  |  | UNPAID
23S-004 | C000015869 | Q126 | I.S. 126 - QUEENS | 1158587 | 86983 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-01-04 | 575 | 2023-08-05 | 2023-08-22 | 68 | 2024-03-29 | 25616.36 | 25616.36 | 0 | 819270 | 2024-05-08 | PAID
24S-112 | C000015869 | Q126 | I.S. 126 - QUEENS | 1315213 | 93426 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2024-10-04 | 4000 | 2024-10-04 | 2024-10-05 | 242 | 2025-07-24 | 3821.05 | 0 | -3821.05 |  |  | UNPAID
24S-028 | C000015869 | Q141 | I.S. 141 - QUEENS | 1229285 | 91394 | CIP |  | PO 18 Asbestos Service | Initial | NEW | 2024-04-12 | 5575 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-015 | C000015869 | Q165 | P.S. 165 - QUEENS | 1223510 | 88306 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | NEW | 2024-03-08 | [6 empty] | 0 | 0 |  |  | UNPAID
25S-001 | C000015869 | Q165 | P.S. 165 - QUEENS | 1330550 | 94416 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2025-01-03 | 4100 | 2025-01-04 | 2025-01-05 | 186 | 2025-06-05 | 3943.88 | 3943.88 | 0 | 855123 | 2025-06-23 | PAID | CHECK 25S-001 Q165
| C000015869 | Q166 | P.S. 166 - QUEENS | 1314909 | 93419 | CIP |  | PO 18 Asbestos Service | Initial | NEW | 2024-10-03 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-058 | C000015869 | Q168 | J.H.S. 168 - QUEENS | 1144603 | 86289 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-09-16 | 4840.73 | 2022-10-16 | 2022-10-17 | 85 | 2024-05-01 | 4040.73 | 4040.73 | 0 | 822747 | 2024-06-13 | PAID
22S-073 | C000015869 | Q168 | J.H.S. 168 - QUEENS | 1160261 | 86877 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-12-11 | 3900 | 2022-12-11 | 2022-12-11 | 227 | 2025-07-11 | 2384.13 | 0 | -2384.13 |  |  | UNPAID
23S-086 | C000015869 | Q173 | P.S. 173 - QUEENS | 1196148 | 89297 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-09-19 | 5100 | 2023-09-16 | 2023-09-17 | 229 | 2025-07-15 | 3363.57 | 0 | -3363.57 |  |  | UNPAID
23S-063 | C000015869 | Q176 | P.S. 176 - QUEENS | 1188566 | 88205 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | WIP | 2023-07-24 | [6 empty] | 0 | 0 |  |  | UNPAID
24S-139 | C000015869 | Q185 | J.H.S. 185 - QUEENS | 1329981 | 94438 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2024-12-18 | 16800 | 2024-12-18 | 2024-12-23 | 173 | 2025-06-03 | 9674.83 | 9674.83 | 0 | 854824 | 2025-06-20 | PAID | CHECK 24S-139 Q185
| C000015869 | Q188 | P.S. 188 - QUEENS | 1301654 | 92693 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | NEW | 2024-07-29 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-016 | C000015869 | Q189 | J.H.S. 189 - QUEENS | 1126762 | 85253 | CIP | Kondilis, Milton | PO 18 Asbestos Service | RFA | Closed | 2022-06-09 | 575 | 2022-08-11 | 2022-08-14 | 18 | 2023-06-22 | 9012.85 | 9012.85 | 0 | 799332 | 2023-07-12 | PAID
23S-102 | C000015869 | Q189 | J.H.S. 189 - QUEENS | 1197401 | 89542 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-10-03 | 29538.65 | 2024-12-19 | 2025-02-23 | 218 | 2025-06-26 | 27816.65 | 0 | -27816.65 |  |  | UNPAID
22S-004 | C000015869 | Q191 | P.S. 191 - QUEENS | 1123683 | 84992 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-04-29 | 3500 | 2022-04-29 | 2022-05-01 | 96 | 2024-05-24 | 5171.03 | 5171.03 | 0 | 824530 | 2024-07-05 | PAID
22S-013 | C000015869 | Q192 | I.S. 192 - QUEENS | 1117713 | 84478 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-06-08 | 1075 | 2022-09-23 | 2022-09-25 | 42 | 2023-09-29 | 8661.09 | 8661.09 | 0 | 806700 | 2023-10-25 | PAID
22S-012 | C000015869 | Q192 | I.S. 192 - QUEENS | 1126399 | 84618 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-06-06 | 575 | 2022-07-28 | 2022-08-14 | 50 | 2023-10-31 | 20556.68 | 20556.68 | 0 | 809817 | 2023-12-11 | PAID
22S-052 | C000015869 | Q192 | I.S. 192 - QUEENS | 1139744 | 86129 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-08-30 | 5775 | 2022-08-30 | 2022-09-01 | 118 | 2024-07-31 | 4911.53 | 4911.53 | 0 | 828522 | 2024-08-30 | PAID
22S-042 | C000015869 | Q192 | I.S. 192 - QUEENS | 1134708 | 85703 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-08-02 | 575 | 2023-08-11 | 2023-08-26 | 127 | 2024-08-13 | 16413.17 | 16413.17 | 0 | 832021 | 2024-10-07 | PAID
| C000015869 | Q192 | I.S. 192 - QUEENS | 1140015 | 86082 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | WIP | 2022-09-07 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-033 | C000015869 | Q192 | I.S. 192 - QUEENS | 1131965 | 85545 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-07-12 | 575 | 2023-07-12 | 2023-07-29 | 148 | 2025-03-18 | 14183.93 | 14183.93 | 0 | 852349 | 2025-05-22 | PAID | CHECK 22S-033 Q192
23S-112 | C000015869 | Q193 | P.S. 193 - QUEENS | 1204825 | 89737 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-11-03 | 4200 | 2023-11-02 | 2023-11-05 | 98 | 2024-05-30 | 5440.93 | 5440.93 | 0 | 824527 | 2024-07-05 | PAID
23S-076 | C000015869 | Q193 | I.S. 193 - QUEENS | 1191451 | 88616 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | WIP | 2023-08-14 | [6 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | Q196 | P.S. 196 - QUEENS | 1192028 | 88590 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | WIP | 2023-08-23 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-041 | C000015869 | Q203 | P.S. 203 - QUEENS | 1243762 | 92007 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2024-05-31 | 4100 | 2024-06-01 | 2024-06-02 | 136 | 2024-10-10 | 3557.55 | 3557.55 | 0 | 835021 | 2024-11-06 | PAID
23S-006 | C000015869 | Q205 | P.S. 205 - QUEENS | 1161238 | 86946 | CIP | Bracamonte, Jesus | CTF | Initial | Closed | 2023-01-11 | 25845 | 2023-02-15 | 2023-09-06 | 235 | 2025-07-24 | 23289.08 | 0 | -23289.08 |  |  | UNPAID
23S-007 | C000015869 | Q210 | I.S. 210 - QUEENS | 1160021 | 87036 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-01-13 | 575 | 2023-04-12 | 2023-08-05 | 115 | 2024-07-31 | 48501.86 | 48501.86 | 0 | 828152 | 2024-08-27 | PAID
22S-069 | C000015869 | Q216 | J.H.S. 216 - QUEENS | 1153592 | 86738 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2022-11-22 | 15045 | 2023-07-21 | 2023-07-23 | 86 | 2024-05-03 | 6607.2 | 6607.2 | 0 | 820793 | 2024-05-20 | PAID
23S-071 | C000015869 | Q217 | I.S. 217 - QUEENS | 1188339 | 88787 | CIP | Poskrobko, Lukasz | LAP Construction Phase Services | Initial | WIP | 2023-07-26 | [6 empty] | 0 | 0 |  |  | UNPAID
23S-010 | C000015869 | Q221 | P.S. 221 - QUEENS | 1162079 | 87060 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-01-27 | 575 | 2023-08-24 | 2023-11-04 | 90 | 2024-05-07 | 39716.84 | 39716.84 | 0 | 824529 | 2024-07-05 | PAID
23S-026 | C000015869 | Q223 | P.S. 223 - QUEENS | 1170969 | 87623 | CIP | Bracamonte, Jesus | CTF | Initial | Closed | 2023-04-12 | 21520 | 2023-04-19 | 2023-08-13 | 207 | 2025-06-18 | 25507.87 | 0 | -25507.87 |  |  | UNPAID
24S-020 | C000015869 | Q225 | P.S. 225 - QUEENS | 1223718 | 89963 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-03-14 | 13900 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-019 | C000015869 | Q225 | P.S. 225 - QUEENS | 1223719 | 89359 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-03-14 | 13900 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-071 | C000015869 | Q231 | I.S. 231 (TANDEM Q251) - QUEENS | 1152671 | 86707 | CIP | Kondilis, Milton | LAP Construction Phase Services | Initial | Closed | 2022-12-02 | 13200 | 2023-10-08 | 2023-10-09 | 93 | 2024-05-21 | 5505.39 | 5505.39 | 0 | 824041 | 2024-07-01 | PAID
22S-039 | C000015869 | Q231 | I.S. 231 (TANDEM Q251) - QUEENS | 1135183 | 85777 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2022-07-29 | 3900 | 2022-07-29 | 2022-07-30 | 192 | 2025-06-16 | 2079.2 | 0 | -2079.2 |  |  | UNPAID
22S-022 | C000015869 | Q397 | PRE-K CENTER @ 32-52 37TH STREET - QUEENS | 1129932 | 85470 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | RFA | Closed | 2022-06-24 | 4100 | 2022-06-25 | 2022-06-26 | 5 | 2022-12-15 | 3300.38 | 3300.38 | 0 | 788350 | 2023-02-09 | PAID
23S-044 | C000015869 | Q397 | PRE-K CENTER @ 32-52 37TH STREET - QUEENS | 1183628 | 88349 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-06-09 | 6175 | 2023-06-09 | 2023-06-10 | 49 | 2023-10-17 | 7665.88 | 7665.88 | 0 | 807569 | 2023-11-08 | PAID
22S-021 | C000015869 | Q400 | AUGUST MARTIN HS - QUEENS | 1134593 | 85622 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | RFA | Closed | 2022-07-22 | 6575 | 2022-07-22 | 2022-08-14 | 16 | 2023-06-22 | 15635.03 | 15635.03 | 0 | 799300 | 2023-07-12 | PAID
| C000015869 | Q400 | AUGUST MARTIN HS - QUEENS | 1323411 | 94004 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-11-26 | 14100 | [5 empty] | 0 |  |  |  | UNPAID
22S-008 | C000015869 | Q405 | BAYSIDE HS - QUEENS | 1120169 | 67089 | CIP | Kondilis, Milton | LAP Construction Phase Services | RFA | Closed | 2022-04-08 | 4100 | 2022-04-08 | 2023-07-02 | 162 | 2025-05-07 | 9949.73 | 9949.73 | 0 | 853438 | 2025-06-06 | PAID | CHECK 22S-008 Q405
23S-099 | C000015869 | Q425 | JOHN BOWNE HS, INC - QUEENS | 1200347 | 89726 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-10-18 | 5700 | 2023-10-13 | 2023-10-15 | 74 | 2024-04-18 | 5378.1 | 5378.1 | 0 | 822278 | 2024-06-07 | PAID
24S-052 | C000015869 | Q438 | P.S. 256 ANNEX - QUEENS | 1300385 | 92209 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | NEW | 2024-07-18 | 6198.04 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-032 | C000015869 | Q442 | DISTRICT 29 PRE-K CENTER - QUEENS | 1233875 | 91854 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | NEW | 2024-05-17 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-037 | C000015869 | Q442 | DISTRICT 29 PRE-K CENTER - QUEENS | 1233397 | 91832 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | NEW | 2024-05-14 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-023 | C000015869 | Q450 | NEWCOMERS HIGH SCHOOL (OLD LIC) - QUEENS | 1174986 | 87897 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-04-12 | 5575 | 2023-04-07 | 2023-04-13 | 59 | 2024-02-07 | 7810.55 | 7810.55 | 0 | 816890 | 2024-04-02 | PAID
23S-002 | C000015869 | Q450 | NEWCOMERS HIGH SCHOOL (OLD LIC) - QUEENS | 1159967 | 87016 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2023-01-04 | 4500 | 2023-01-30 | 2024-09-22 | 234 | 2025-07-24 | 64978.59 | 0 | -64978.59 |  |  | UNPAID
23S-068 | C000015869 | Q456 | HS FOR ARTS AND BUS. (OLNUTN X) - QUEENS | 1189784 | 88945 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-07-31 | 6575 | 2023-07-31 | 2023-08-01 | 56 | 2024-02-07 | 5992.9 | 5992.9 | 0 | 818439 | 2024-04-24 | PAID
24S-009 | C000015869 | Q460 | FLUSHING HS - QUEENS | 1216051 | 90480 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | NEW | 2024-01-30 | 1575 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-013 | C000015869 | Q460 | FLUSHING HS - QUEENS | 1218989 | 90784 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | NEW | 2024-02-28 | 1775 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-040 | C000015869 | Q475 | RICHMOND HILLS HS - QUEENS | 1181631 | 88287 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-05-26 | 5600 | 2023-05-25 | 2023-05-28 | 62 | 2024-02-20 | 5783.81 | 5783.81 | 0 | 817321 | 2024-04-08 | PAID
24S-056 | C000015869 | Q480 | JOHN ADAMS HS - QUEENS | 1243886 | 92299 | CIP |  | Special Program | Initial | Closed | 2024-06-27 | 4400 | 2024-07-13 | 2024-07-14 | 142 | 2024-12-31 | 2273.91 | 2273.91 | 0 |  | 2025-02-08 | PAID
22S-062 | C000015869 | Q593 | P.S. @ 140 BEACH 112 STREET - QUEENS | 1149305 | 86549 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | RFA | Closed | 2022-10-19 | 4800 | 2022-10-19 | 2022-10-21 | 39 | 2023-08-01 | 4742.45 | 4742.45 | 0 | 800965 | 2023-08-04 | PAID
22S-084 | C000015869 | Q593 | P.S. @ 140 BEACH 112 STREET - QUEENS | 1159686 | 86999 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-01-03 | 3575 | 2022-12-29 | 2022-12-30 | 147 | 2025-05-05 | 2762.41 | 2762.41 | 0 | 851186 | 2025-05-13 | PAID | CHECK 22S-084 Q593
23S-020 | C000015869 | Q725 | HS FOR INFORMATION TECH - QUEENS | 1170402 | 87585 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2023-03-09 | 21520 | 2023-03-30 | 2023-10-14 | 119 | 2024-07-31 | 10752.68 | 10752.68 | 0 | 827289 | 2024-08-14 | PAID
23S-001 | C000015869 | Q800 | DOE ADMINISTRATIVE / STUDENT SERVICES - QUEENS | 1147905 | 86152 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | WIP | 2023-01-03 | 575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-044 | C000015869 | Q801 | OSSS / DSF - QUEENS | 1137231 | 85867 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2022-09-01 | 575 | 2023-01-05 | 2023-02-04 | 29 | 2023-07-11 | 12701.34 | 12701.34 | 0 | 799843 | 2023-07-25 | PAID
23S-012 | C000015869 | Q801 | OSSS / DSF - QUEENS | 1163723 | 87297 | CIP | Poskrobko, Lukasz | PO 18 Asbestos Service | Initial | Closed | 2023-02-06 | 575 | 2023-03-23 | 2023-04-01 | 31 | 2023-07-20 | 11664.66 | 11664.66 | 0 | 800964 | 2023-08-04 | PAID
23S-043 | C000015869 | R002 | I.S. 2 - STATEN ISLAND | 1183983 | 88353 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-06-09 | 875 | 2023-06-09 | 2023-06-10 | 44 | 2023-10-11 | 8535.7 | 8535.7 | 0 | 806509 | 2023-10-24 | PAID
24S-008 | C000015869 | R002 | I.S. 2 - STATEN ISLAND | 1224066 | 91184 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | NEW | 2024-03-01 | 4200 | [5 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | R002 | I.S. 2 - STATEN ISLAND | 1305317 | 92968 | CIP | Bracamonte, Jesus | Special Program | Initial | NEW | 2024-08-15 | 4000 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-059 | C000015869 | R007 | I.S. 7 - STATEN ISLAND | 1142107 | 86217 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Amendment | Closed | 2022-09-14 | 13000 | 2022-11-09 | 2022-11-19 | 172 | 2025-05-29 | 11726.56 | 11726.56 | 0 | 854347 | 2025-06-16 | PAID | CHECK 22S-059 R007
24S-043 | C000015869 | R008 | P.S. 8 - STATEN ISLAND | 1243679 | 92211 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2024-06-07 | 4000 | 2024-06-07 | 2024-06-08 | 160 | 2025-05-07 | 2152.98 | 2152.98 | 0 | 851064 | 2025-05-12 | PAID | CHECK 24S-043 R008
24S-033 | C000015869 | R013 | P.S. 13 - STATEN ISLAND | 1232533 | 91809 | CIP |  | LAP Construction Phase Services | Initial | NEW | 2024-05-09 | 15400 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-034 | C000015869 | R013 | P.S. 13 - STATEN ISLAND | 1232548 | 91836 | CIP |  | LAP Construction Phase Services | Initial | NEW | 2024-05-10 | 11200 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-092 | C000015869 | R014 | P.S. 14 - STATEN ISLAND | 1198180 | 89628 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-09-30 | 7875 | 2023-09-30 | 2023-10-01 | 65 | 2024-03-20 | 5413.73 | 5413.73 | 0 | 819024 | 2024-05-02 | PAID
22s-082 | C000015869 | R018 | P.S. 18 - STATEN ISLAND | 1158460 | 86961 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-01-23 | 190287.5 | 2023-02-16 | 2023-07-18 | 211 | 2025-06-24 | 37545.44 | 0 | -37545.44 |  |  | UNPAID
24S-011 | C000015869 | R022 | P.S. 22 - STATEN ISLAND | 1213407 | 82742 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-01-09 | 5500 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-083 | C000015869 | R024 | I.S. 24 - STATEN ISLAND | 1304867 | 92944 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-08-15 | 4000 | 2024-08-20 | 2025-08-21 | 161 | 2025-05-07 | 2032.9 | 2032.9 | 0 | 854349 | 2025-06-16 | PAID | CHECK 24S-083 R024
22S-034 | C000015869 | R026 | P.S. 26 - STATEN ISLAND | 1132987 | 85620 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | RFA | Closed | 2022-04-28 | 21075 | 2022-07-21 | 2022-07-27 | 2 | 2022-10-06 | 29313.56 | 29313.56 | 0 | 780525 | 2022-10-06 | PAID
23S-027 | C000015869 | R026 | P.S. 26 - STATEN ISLAND | 1177420 | 87998 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-04-20 |  | 2023-04-20 | 2023-04-21 | 36 | 2023-08-01 | 6062.8 | 6062.8 | 0 | 800921 | 2023-08-04 | PAID
23S-107 | C000015869 | R026 | P.S. 26 - STATEN ISLAND | 1202649 | 89785 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-11-13 | 3875 | 2023-10-28 | 2023-10-28 | 122 | 2024-07-31 | 2523.58 | 2523.58 | 0 | 827896 | 2024-08-23 | PAID
24S-089 | C000015869 | R026 | P.S. 26 - STATEN ISLAND | 1310116 | 93264 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | NEW | 2024-09-06 | [6 empty] | 0 | 0 |  |  | UNPAID
23S-115 | C000015869 | R030 | P.S 30 - STATEN ISLAND | 1205691 | 90030 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-11-17 | 11375 | 2023-11-17 | 2023-11-18 | 70 | 2024-04-02 | 6029.25 | 6029.25 | 0 | 818641 | 2024-04-26 | PAID
| C000015869 | R032 | P.S. 32 - STATEN ISLAND | 1132984 | 85600 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | WIP | 2022-07-20 | 6000 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-003 | C000015869 | R034 | P.S 34 - STATEN ISLAND | 1123686 | 84927 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | RFA | Closed | 2022-04-28 | 8300 | 2022-04-28 | 2022-04-30 | 1 | 2022-10-06 | 6453.9 | 6453.9 | 0 | 780524 | 2022-10-06 | PAID
23S-030 | C000015869 | R034 | P.S 34 - STATEN ISLAND | 1179156 | 88108 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-05-12 |  | 2023-05-05 | 2023-05-06 | 37 | 2023-08-01 | 5264.23 | 5264.23 | 0 | 800922 | 2023-08-04 | PAID
24S-086 | C000015869 | R034 | P.S 34 - STATEN ISLAND | 1305386 | 92969 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-08-16 | 4000 | 2024-09-01 | 2024-09-01 | 180 | 2025-06-03 | 3166.68 | 0 | -3166.68 |  |  | UNPAID
23S-080 | C000015869 | R040 | P.S. 373 (OLD P40) - STATEN ISLAND | 1194257 | 89229 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2024-06-03 |  | 2023-09-01 | 2023-09-02 | 126 | 2024-08-12 | 2964.88 | 2964.88 | 0 | 828332 | 2024-08-28 | PAID
24S-046 | C000015869 | R040 | P.S. 373 (OLD P40) - STATEN ISLAND | 1194257 | 89229 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | NEW | 2024-08-30 | 5575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-015 | C000015869 | R045 | P.S. 45 - STATEN ISLAND | 1129757 | 85321 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | RFA | Closed | 2022-06-08 | 8275 | 2022-06-08 | 2022-06-12 | 12 | 2023-06-14 | 7579.36 | 7579.36 | 0 | 798454 | 2023-06-25 | PAID
| C000015869 | R049 | I.S. 49 - STATEN ISLAND | 1212835 | 90300 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | NEW | 2024-01-09 | 3100 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-074 | C000015869 | R053 | P.S. 53 - STATEN ISLAND | 1189854 | 88746 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-08-07 | [6 empty] | 0 | 0 |  |  | UNPAID
| C000015869 | R055 | P.S. 55 - STATEN ISLAND | 1311249 | 93283 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | NEW | 2024-09-14 | 4000 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-109 | C000015869 | R055 | P.S. 55 - STATEN ISLAND | 1205516 | 89819 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-10-27 | 7875 | 2023-10-27 | 2023-10-28 | 216 | 2025-06-25 | 6603.4 | 0 | -6603.4 |  |  | UNPAID
23S-096 | C000015869 | R057 | P.S. 57 - STATEN ISLAND | 1199112 | 89511 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-10-07 | 10375 | 2023-10-06 | 2023-10-10 | 238 | 2025-07-24 | 9467.37 | 0 | -9467.37 |  |  | UNPAID
24S-065 | C000015869 | R059 | THE HARBOR VIEW SCHOOL - STATEN ISLAND | 1300413 | 92564 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-07-24 | 4000 | 2024-07-26 | 2024-07-27 | 175 | 2025-06-03 | 4437.13 | 0 | -4437.13 |  |  | UNPAID
23S-021 | C000015869 | R061 | I.S. 61 - STATEN ISLAND | 1172020 | 87748 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-03-27 | 9075 | 2023-04-28 | 2023-04-29 | 196 | 2025-06-16 | 4501.55 | 4501.55 | 0 | 855117 | 2025-06-23 | PAID | CHECK 23S-021 R061
24S-021 | C000015869 | R075 | I.S. 75 - STATEN ISLAND | 1224929 | 91329 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | NEW | 2024-03-27 | 17575 | [5 empty] | 0 | 0 |  |  | UNPAID
22S-001 | C000015869 | R435 | NEW DORP HS (NEW) - STATEN ISLAND | 1116702 | 84575 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | RFA | Closed |  |  | 2022-03-16 | 2022-04-03 | 4 | 2022-11-14 | 12189.08 | 12189.08 | 0 | 784612 | 2022-12-13 | PAID
23S-116 | C000015869 | R435 | NEW DORP HS (NEW) - STATEN ISLAND | 1206985 | 90061 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-11-26 | 3850 | 2023-11-26 | 2023-11-27 | 182 | 2025-06-03 | 2346.04 | 2346.04 | 0 | 854345 | 2025-06-16 | PAID | CHECK 23S-116 R435
24S-005 | C000015869 | R435 | NEW DORP HS (NEW) - STATEN ISLAND | 1213180 | 90083 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2024-01-04 | 14000 | 2024-02-05 | 2024-11-17 | 215 | 2025-06-25 | 8436.98 | 0 | -8436.98 |  |  | UNPAID
| C000015869 | R435 | NEW DORP HS (NEW) - STATEN ISLAND | 1304869 | 92950 | CIP | Bracamonte, Jesus | Special Program | Initial | NEW | 2024-08-16 | 4000 | [5 empty] | 0 | 0 |  |  | UNPAID
24S-099 | C000015869 | R440 | STATEN ISLAND TECHNIAL HS - STATEN ISLAND | 1312305 | 93263 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2024-09-14 | 10200 | 2024-09-14 | 2024-09-22 | 146 | 2025-01-27 | 10352.63 | 10352.63 | 0 |  | 2025-02-11 | PAID
23S-056 | C000015869 | R455 | TOTTENVILLE HS - STATEN ISLAND | 1187909 | 88731 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-07-13 | 7875 | 2023-07-13 | 2023-07-14 | 224 | 2025-07-07 | 2628.23 | 0 | -2628.23 |  |  | UNPAID
| C000015869 | R455 | TOTTENVILLE HS - STATEN ISLAND | 1304791 | 92921 | CIP | Bracamonte, Jesus | Special Program | Initial | NEW | 2024-08-10 | 4000 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-024 | C000015869 | R460 | SUSAN R. WAGNER HS - STATEN ISLAND | 1173054 | 87850 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-04-10 | 21520 | 2023-04-06 | 2023-06-18 | 46 | 2023-10-16 | 8225.58 | 8225.58 | 0 | 807653 | 2023-11-08 | PAID
24S-091 | C000015869 | R825 | P.S. 25 (MOUNT LORETTO) - STATEN ISLAND | 1311251 | 93259 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2024-09-08 | 4121.58 | 2024-09-08 | 2024-09-09 | 169 | 2025-05-22 | 3502.58 | 3502.58 | 0 | 854346 | 2025-06-16 | PAID | CHECK 24S-091 R825
24S-067 | C000015869 | R831 | P.S. 74 - STATEN ISLAND | 1301196 | 92576 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-07-24 | 4000 | 2024-08-01 | 2024-08-01 | 145 | 2024-12-31 | 2338.38 | 2338.38 | 0 | 841785 | 2025-01-22 | PAID
22S-048 | C000015869 | R880 | P.S. 80 (PETR COMPL-BLDG B) - STATEN ISLAND | 1137953 | 85984 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2022-08-25 | 10500 | 2022-09-14 | 2022-10-16 | 75 | 2024-04-18 | 5623.4 | 5623.4 | 0 | 819831 | 2024-05-10 | PAID
19S-277 | C000015869 | R880 | P.S. 80 (PETR COMPL-BLDG B) - STATEN ISLAND | 1002367 | 73232 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | Closed | 2019-12-12 | 500 | 2022-08-11 | 2022-08-17 | 4186 | 2023-07-20 | 12270.54 | 12270.54 | 0 | 800187 | 2023-07-25 | PAID
24S-142 | C000015869 | R883 | P.S. 80 AX (PETR COMPL-BLDG K) - STATEN ISLAND | 1327776 | 94296 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2024-12-19 | 4100 | 2024-12-26 | 2024-12-26 | 212 | 2025-06-24 | 2344.06 | 0 |  |  |  | UNPAID
23S-085 | C000015869 | X005 | P.S. 5 - BRONX | 1196035 | 89249 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-09-15 | 575 | 2023-09-14 | 2023-09-16 | 84 | 2024-05-01 | 11013.5 | 11013.5 | 0 | 824038 | 2024-07-01 | PAID
24S-057 | C000015869 | X005 | P.S. 5 - BRONX | 1243687 | 92195 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-06-28 | 16700 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-064 | C000015869 | X011 | P.S. 19 - BRONX | 1188192 | 88729 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Amendment | Closed | 2023-07-24 | 575 | 2023-08-07 | 2023-08-08 | 94 | 2024-05-24 | 5219.18 | 5219.18 | 0 | 824528 | 2024-07-05 | PAID
23S-038 | C000015869 | X019 | P.S. 19 - BRONX | 1183897 | 88212 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Initial | Closed | 2023-07-14 | 54580.5 | 2023-08-17 | 2023-08-20 | 133 | 2024-09-19 | 13225.51 | 13225.51 | 0 | 835019 | 2024-11-06 | PAID
23S-018 | C000015869 | X027 | P.S. 277 - BRONX | 1169734 | 87524 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-03-02 | 575 | 2023-07-07 | 2023-07-09 | 88 | 2024-05-06 | 8304.05 | 8304.05 | 0 | 824040 | 2024-07-01 | PAID
24S-097 | C000015869 | X028 | P.S. 28 - BRONX | 1308103 | 93164 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Initial | Closed | 2024-08-30 | 575 | 2024-10-17 | 2024-10-19 | 230 | 2025-07-16 | 6034.19 | 0 | -6034.19 |  |  | UNPAID
23S-138 | C000015869 | X039 | NEW SCH FOR ARTS AND SCIENCE - BRONX | 1196307 | 89315 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-09-19 | 14932.72 | 2024-08-23 | 2024-08-25 | 168 | 2025-05-22 | 13332.72 | 0 | -13332.72 |  |  | UNPAID
23S-025 | C000015869 | X041 | P.S. 41 - BRONX | 1174668 | 87890 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Initial | WIP | 2023-04-11 | 575 | [6 empty] | 0 |  |  | UNPAID
23S-014 | C000015869 | X049 | P.S. 49 - BRONX | 1167051 | 87395 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-02-14 | 575 | 2023-02-09 | 2023-02-12 | 91 | 2024-05-07 | 6073.75 | 6073.75 | 0 | 824042 | 2024-07-01 | PAID
24S-055 | C000015869 | X065 | P.S. 65 - BRONX | 1244229 | 92350 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2024-07-12 | 575 | 2024-10-24 | 2024-11-16 | 170 | 2025-05-22 | 17971.61 | 17971.61 | 0 | 855124 | 2025-06-23 | PAID | CHECK 24S-055 X065
24S-044 | C000015869 | X074 | I.S. 201 - BRONX | 1234316 | 91863 | CIP |  | LAP Construction Phase Services | Initial | NEW | 2024-05-28 | 300 | [6 empty] | 0 |  |  | UNPAID
23S-114 | C000015869 | X075 | P.S. 75 - BRONX | 1205150 | 89840 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-11-14 | 575 | 2024-08-02 | 2024-08-26 | 201 | 2025-06-16 | 47383.26 | 47383.26 | 0 | 855120 | 2025-06-23 | PAID | CHECK 23S-114 X075
23S-034 | C000015869 | X080 | P.S. 80 - BRONX | 1171504 | 87691 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Initial | Closed | 2023-05-12 | 575 | 2023-07-31 | 2023-08-10 | 79 | 2024-04-22 | 20602.27 | 20602.27 | 0 | 823201 | 2024-06-20 | PAID
23S-065 | C000015869 | X085 | P.S. 85 - BRONX | 1188698 | 88845 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Amendment | Closed | 2023-07-25 | 3075 | 2023-07-24 | 2023-08-17 | 92 | 2024-05-13 | 4410.05 | 4410.05 | 0 | 823610 | 2024-06-25 | PAID
23S-111 | C000015869 | X085 | P.S. 85 - BRONX | 1202987 | 89844 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Initial | Closed | 2023-10-30 | 6575 | 2024-01-25 | 2024-01-28 | 117 | 2024-07-31 | 7352.25 | 7352.25 | 0 | 829477 | 2024-09-12 | PAID
23S-059 | C000015869 | X085 | P.S. 85 - BRONX | 1188194 | 88763 | CIP | Zarrabi, Abdi | PO 18 Asbestos Service | Amendment | Closed | 2023-07-19 | 41521 | 2023-07-24 | 2023-08-24 | 158 | 2025-05-06 | 20155.11 | 20155.11 | 0 | 855125 | 2025-06-23 | PAID | CHECK 23S-059 X085
24S-088 | C000015869 | X086 | P.S. 86 - BRONX | 1304685 | 92919 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2024-08-19 | 575 | 2024-09-05 | 2024-09-07 | 243 | 2025-07-24 | 6706.86 | 0 | -6706.86 |  |  | UNPAID
22S-024 | C000015869 | X093 | P.S. 93 - BRONX | 1131990 | 85532 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | RFA | Closed |  | 575 | 2022-06-30 | 2022-07-02 | 6 | 2022-12-28 | 6339.9 | 6339.9 | 0 | 790648 | 2023-03-08 | PAID
23S-053 | C000015869 | X101 | I.S. 101 - BRONX | 1183976 | 88398 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-06-15 | 575 | 2023-09-21 | 2023-09-24 | 58 | 2024-02-21 | 6284.13 | 6284.13 | 0 | 819689 | 2024-05-09 | PAID
23S-058 | C000015869 | X101 | I.S. 101 - BRONX | 1186918 | 88631 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2023-07-19 | 9020 | 2023-12-15 | 2023-12-17 | 100 | 2024-06-05 | 6341.5 | 6341.5 | 0 | 822987 | 2024-06-17 | PAID
23S-003 | C000015869 | X101 | I.S. 101 - BRONX | 1163449 | 87019 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | Closed | 2023-02-03 | 38500 | 2023-02-24 | 2023-12-15 | 132 | 2024-08-23 | 37718.95 | 37718.95 | 0 | 831360 | 2024-10-01 | PAID
| C000015869 | X102 | P.S. 102 - BRONX | 1328013 | 93969 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial | NEW | 2024-12-26 | 15045 | [5 empty] | 0 | 0 |  |  | UNPAID
23S-052 | C000015869 | X107 | I.S. 107 - BRONX | 1185462 | 88307 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | WIP | 2023-06-21 | [6 empty] | 0 | 0 |  |  | UNPAID
22S-036 | C000015869 | X127 | I.S. 127 - BRONX | 1135064 | 85704 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | RFA | Closed | 2022-07-22 | 8875 | 2022-07-22 | 2022-07-25 | 24 | 2023-07-05 | 11811.36 | 11811.36 | 0 | 804163 | 2023-09-22 | PAID
| C000015869 | X131 | I.S. 131 - BRONX | 1335358 | 94778 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | NEW | 2025-02-14 | 575 | [9 empty] | UNPAID
23S-082 | C000015869 | X146 | P.S. 146 - BRONX | 1195355 | 89316 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | WIP | 2023-09-11 | 575 | [6 empty] | 0 |  |  | UNPAID
24S-058 | C000015869 | X149 | J.H.S. 149 - BRONX | 1243686 | 92199 | CIP |  | LAP Construction Phase Services | Initial | NEW | 2024-06-28 | 16700 | [6 empty] | 0 |  |  | UNPAID
| C000015869 | X161 | P.S. 161 - BRONX | 1335270 | 94786 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | NEW | 2025-02-19 | 575 | [9 empty] | UNPAID
23S-013 | C000015869 | X401 | BRONX REGIONAL HS (OLD 133) - BRONX | 1165246 | 87286 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Initial | Closed | 2023-02-06 | 575 | 2023-03-23 | 2023-03-25 | 51 | 2024-02-07 | 7268.63 | 7268.63 | 0 | 815948 | 2024-03-18 | PAID
22S-028 | C000015869 | X425 | EVANDER CHILDS HS - BRONX | 1130024 | 85491 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | RFA | Closed | 2022-07-06 | 575 | 2022-08-11 | 2022-08-13 | 14 | 2023-06-20 | 6187.21 | 6187.21 | 0 | 799215 | 2023-07-11 | PAID
22S-061 | C000015869 | X455 | HARRY S TRUMAN HS - BRONX | 1146848 | 85699 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | RFA | Closed | 2022-09-29 | 575 | 2023-02-21 | 2023-02-24 | 34 | 2023-09-06 | 8454.45 | 8454.45 | 0 | 805729 | 2023-10-13 | PAID
22S-023 | C000015869 | X470 | SOUTH BRONX EDUCATIONAL CAMPUS (OLD 38) - BRONX | 1128873 | 85247 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2022-06-23 | 575 | 2023-02-16 | 2023-04-08 | 45 | 2023-10-11 | 26283.31 | 26283.31 | 0 | 820910 | 2024-05-21 | PAID
23S-035 | C000015869 | X470 | SOUTH BRONX EDUCATIONAL CAMPUS (OLD 38) - BRONX | 1175547 | 87938 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-05-10 | 575 | 2023-08-17 | 2023-08-19 | 64 | 2024-03-20 | 7061.55 | 7061.55 | 0 | 849822 | 2025-04-28 | PAID
22S-026 | C000015869 | X470 | SOUTH BRONX EDUCATIONAL CAMPUS (OLD 38) - BRONX | 1131033 | 85485 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2022-07-08 | 575 | 2022-07-07 | 2022-07-09 | 67 | 2024-03-26 | 7124.33 | 7124.33 | 0 | 821671 | 2024-05-29 | PAID
23S-041 | C000015869 | X807 | DISTRICT OFFICE #7 (OLD 18) - BRONX | 1180607 | 88248 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | WIP | 2023-05-24 | 575 | [6 empty] | 0 |  |  | UNPAID
22S-081 | C000015869 | X843 | P.S. 246 (POE CENTER) - BRONX | 1158558 | 86979 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Initial | WIP | 2022-12-21 | 8575 | [6 empty] | 0 |  |  | UNPAID

## SAMPLE DATASET
SAI FILE NO | Contract # | Building | School Name | WA # | Service ID | Project Type | Primary Hygienist | Column1 | Service Name | WA Type | WA Status | Initiation Date (WA) | Estimated Cost (WA) | Actual Start Date (RFP) | Actual Date of Completion (RFP) | RFP No | Date of RFP | Amount Invoiced (RFP) | Amount Received | Amount Outstanding | CHECK NO. | DATE ON CHECK | PAID / UNPAID | NOTES | HAS DATA | HAS DATA 2
24S-079 | C000015869 | K114 | P.S. 114 - BROOKLYN | 1304841 | 92925 | CIP | Bracamonte, Jesus |  | Special Program | Initial | Closed | 2024-08-13 | 4000 | 2024-08-24 | 2024-08-25 | 166 | 2025-05-16 | 2454.75 | 2454.75 | -7470.5 | 855119 | 2025-06-23 | PAID | CHECK 24S-079 K114 | Has Data | 1
22S-085 | C000015869 | K127 | P.S. 127 - BROOKLYN | 1160020 | 86987 | CIP | Scott, Richard |  | PO 18 Asbestos Service | Initial | Closed | 2022-12-19 | 5175 | 2022-12-17 | 2022-12-31 | 97 | 2024-05-28 | 7813.38 | 7813.38 | 0 | 824627 | 2024-07-08 | PAID |  | Has Data | 1
22S-072 | C000015869 | K127 | P.S. 127 - BROOKLYN | 1156790 | 86876 | CIP | Scott, Richard |  | PO 18 Asbestos Service | Initial | Closed | 2022-12-07 | 15575 | 2022-12-08 | 2022-12-19 | 233 | 2025-07-24 | 28177.26 | 0 | 0 |  |  | UNPAID |  | Blank | 1
23S-073 | C000015869 | Q022 | P.S. 22 - QUEENS | 1189469 | 88744 | CIP | Kondilis, Milton |  | PO 18 Asbestos Service | Initial | Closed | 2023-08-02 | 575 | 2024-10-30 | 2024-11-09 | 219 | 2025-06-26 | 13872.14 | 0 | 0 |  |  | UNPAID |  | Blank | 1
24S-031 | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1243757 | 92210 | CIP | Kondilis, Milton |  | PO 18 Asbestos Service | Initial | Closed | 2024-06-21 | 4100 | 2024-05-04 | 2024-05-05 | 135 | 2024-10-10 | 4933.3 | 4933.3 | 0 | 835020 | 2024-11-06 | PAID |  | Has Data | 1
24S-060 | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1243867 | 92257 | CIP | Kondilis, Milton |  | PO 18 Asbestos Service | Initial | Closed | 2024-07-02 | 575 | 2024-07-11 | 2024-07-12 | 153 | 2025-05-06 | 6963.25 | 6963.25 | 0 | 853127 | 2025-06-04 | PAID | CHECK 24S-060 Q023 | Has Data | 1
22S-005 | C000015869 | M620 | NORMAN THOMAS HS (ECF) - MANHATTAN | 1123363 | 84986 | CIP | Lazicki, Rafal |  | LAP Construction Phase Services | RFA | Closed | 2022-06-06 | 500 | 2022-07-14 | 2022-07-18 | 21 | 2023-06-23 | 21825.8 | 21825.8 | 0 | 800470 | 2023-07-28 | PAID |  | Has Data | 1
24S-140 | C000015869 | M660 | SCHL OF THE FUTURE (OLD BACON) - MANHATTAN | 1333677 | 94298 | CIP | Lazicki, Rafal |  | PO 18 Asbestos Service | Initial | Closed | 2024-12-20 | 5000 | 2024-12-20 | 2024-12-21 | 205 | 2025-06-17 | 2243.94 | 0 | 0 |  |  | UNPAID |  | Blank | 1
23S-119 | C000015869 | M844 | P.S. 138 ANNEX (OLD M047 AX) | 1214485 | 89905 | CIP | Lazicki, Rafal |  | PO 18 Asbestos Service | Initial | Closed | 2023-12-08 | 7800 | 2023-12-08 | 2023-12-09 | 198 | 2025-06-16 | 2131.98 | 0 | 0 |  |  | UNPAID |  | Blank | 1
22s-082 | C000015869 | R018 | P.S. 18 - STATEN ISLAND | 1158460 | 86961 | CIP | Bracamonte, Jesus |  | PO 18 Asbestos Service | Initial | Closed | 2023-01-23 | 190287.5 | 2023-02-16 | 2023-07-18 | 211 | 2025-06-24 | 37545.44 | 0 | 0 |  |  | UNPAID |  | Blank | 1
24S-011 | C000015869 | R022 | P.S. 22 - STATEN ISLAND | 1213407 | 82742 | CIP | Bracamonte, Jesus |  | LAP Construction Phase Services | Initial |  | 2024-01-09 | 5500 | [5 empty] | 0 | 0 |  |  | UNPAID |  | Blank | 0
24S-083 | C000015869 | R024 | I.S. 24 - STATEN ISLAND | 1304867 | 92944 | CIP | Bracamonte, Jesus |  | Special Program | Initial | Closed | 2024-08-15 | 4000 | 2024-08-20 | 2025-08-21 | 161 | 2025-05-07 | 2032.9 | 2032.9 | 0 | 854349 | 2025-06-16 | PAID | CHECK 24S-083 R024 | Has Data | 1
23S-138 | C000015869 | X039 | NEW SCH FOR ARTS AND SCIENCE - BRONX | 1196307 | 89315 | CIP | Alawamleh, Eman |  | PO 18 Asbestos Service | Initial | Closed | 2023-09-19 | 14932.72 | 2024-08-23 | 2024-08-25 | 168 | 2025-05-22 | 13332.72 | 0 | 0 |  |  | UNPAID |  | Blank | 1
23S-025 | C000015869 | X041 | P.S. 41 - BRONX | 1174668 | 87890 | CIP | Kowalski, Zbigniew |  | PO 18 Asbestos Service | Initial | WIP | 2023-04-11 | 575 | [6 empty] | 0 |  |  | UNPAID |  | Blank | 0
23S-014 | C000015869 | X049 | P.S. 49 - BRONX | 1167051 | 87395 | CIP | Alawamleh, Eman |  | PO 18 Asbestos Service | Initial | Closed | 2023-02-14 | 575 | 2023-02-09 | 2023-02-12 | 91 | 2024-05-07 | 6073.75 | 6073.75 | 0 | 824042 | 2024-07-01 | PAID |  | Has Data | 1
24S-055 | C000015869 | X065 | P.S. 65 - BRONX | 1244229 | 92350 | CIP | Bracamonte, Jesus |  | PO 18 Asbestos Service | Initial | Closed | 2024-07-12 | 575 | 2024-10-24 | 2024-11-16 | 170 | 2025-05-22 | 17971.61 | 17971.61 | 0 | 855124 | 2025-06-23 | PAID | CHECK 24S-055 X065 | Has Data | 1
[20 empty] | 0 |  |  |  |  | Blank | 0
COUNTIF-LEFT-MID-RIGHT-INDEX-MATCH
COUNT USING NAMED RANGE
Number of Rows, Complete_Dataset |  |  | 361
COUNTIF and COUNTBLANK - MONTHLY STATUS
Number of Open Jobs |  | 313
Number of Jobs Not Started |  | 48
Nesting Formulas
With IF clause
| Yes | IF(ISNUMBER(MATCH(LEFT(A2,3), {"19S","20S","21S","22S","23S","24S","25S"}, 0)), "Yes", "No")
Without IF clause
| TRUE | ISNUMBER(MATCH(LEFT(A2,3), {"19S","20S","21S","22S","23S","24S","25S"}, 0))
INDEX/MATCH
| 24S-055 | 92350 | INDEX(F2:F17, MATCH(B39, A2:A17, 0))
|  | 24S-055 | INDEX(A2:A17, MATCH(C39, F2:F17, 0))
F2:F362 - look in this range, and match it to "24S-055" which is found in range A2:A17. Find the exact match.
LEFT - MID - RIGHT
SCHL OF THE FUTURE (OLD BACON) - MANHATTAN
|  | NEW S | LEFT(D14, 5)
D14 -> NEW SCHOOL FOR ARTS AND SCIENCE
|  | SCH FOR | MID(D14, 5, 7)
In D14, pull 7 characters starting at the 5th character
RIGHT(B49, 7)
| P.S. 65 - BRONX | - BRONX | Start from the right of B50 and return 7 character substring
COUNT-COUNTIF-COUNTIFS
|  | 12 | COUNT(FIND("PO 18",I2:I17))
First find PO 18 in this range, column I, count
|  | 12 | COUNTIF(I2:I17,"PO 18*")
|  | 2 | COUNTIFS(I2:I17, "PO 18*", H2:H17, "*Jesus")
ISNUMBER |  |  | ISNUMBER(C36)
|  | TRUE | If there is a number in cell 36, return TRUE, else FALSE
SEARCH
| BRONX |  | SEARCH(substring, cell)
| P.S. 65 - BRONX | 11 | Search for "BRONX" IN "P.S. 65 - BRONX" and return the position of where "BRONX" starts
FIND |  |  | FIND("S-", B49)
| 24S-079 | 3 | Find returns the position (a number) of a specific character or substring within a text string
Find "S-" in B47
Total Rows | 17
Completed Jobs | 14

## LOOKUP
SAI FILE NO | Contract # | Building | School Name | WA # | Service ID | Project Type | Primary Hygienist | Service Name | WA Type | WA Status | Initiation Date (WA) | Estimated Cost (WA) | Actual Start Date (RFP) | Actual Date of Completion (RFP) | RFP No | Date of RFP | Amount Invoiced (RFP) | Amount Received | Amount Outstanding | CHECK NO. | DATE ON CHECK | PAID / UNPAID | NOTES | HAS DATA | HAS DATA 2
24S-079 | C000015869 | K114 | P.S. 114 - BROOKLYN | 1304841 | 92925 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-08-13 | 4000 | 2024-08-24 | 2024-08-25 | 166 | 2025-05-16 | 2454.75 | 2454.75 | -7470.5 | 855119 | 2025-06-23 | PAID | CHECK 24S-079 K114 | Has Data | 1
22S-085 | C000015869 | K127 | P.S. 127 - BROOKLYN | 1160020 | 86987 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | Closed | 2022-12-19 | 5175 | 2022-12-17 | 2022-12-31 | 97 | 2024-05-28 | 7813.38 | 7813.38 | 0 | 824627 | 2024-07-08 | PAID |  | Has Data | 1
22S-072 | C000015869 | K127 | P.S. 127 - BROOKLYN | 1156790 | 86876 | CIP | Scott, Richard | PO 18 Asbestos Service | Initial | Closed | 2022-12-07 | 15575 | 2022-12-08 | 2022-12-19 | 233 | 2025-07-24 | 28177.26 | 0 | 0 |  |  | UNPAID |  | Blank | 1
23S-073 | C000015869 | Q022 | P.S. 22 - QUEENS | 1189469 | 88744 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2023-08-02 | 575 | 2024-10-30 | 2024-11-09 | 219 | 2025-06-26 | 13872.14 | 0 | 0 |  |  | UNPAID |  | Blank | 1
24S-031 | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1243757 | 92210 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2024-06-21 | 4100 | 2024-05-04 | 2024-05-05 | 135 | 2024-10-10 | 4933.3 | 4933.3 | 0 | 835020 | 2024-11-06 | PAID |  | Has Data | 1
24S-060 | C000015869 | Q023 | QUEENS ACADEMY HS - QUEENS | 1243867 | 92257 | CIP | Kondilis, Milton | PO 18 Asbestos Service | Initial | Closed | 2024-07-02 | 575 | 2024-07-11 | 2024-07-12 | 153 | 2025-05-06 | 6963.25 | 6963.25 | 0 | 853127 | 2025-06-04 | PAID | CHECK 24S-060 Q023 | Has Data | 1
22S-005 | C000015869 | M620 | NORMAN THOMAS HS (ECF) - MANHATTAN | 1123363 | 84986 | CIP | Lazicki, Rafal | LAP Construction Phase Services | RFA | Closed | 2022-06-06 | 500 | 2022-07-14 | 2022-07-18 | 21 | 2023-06-23 | 21825.8 | 21825.8 | 0 | 800470 | 2023-07-28 | PAID |  | Has Data | 1
24S-140 | C000015869 | M660 | SCHL OF THE FUTURE (OLD BACON) - MANHATTAN | 1333677 | 94298 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2024-12-20 | 5000 | 2024-12-20 | 2024-12-21 | 205 | 2025-06-17 | 2243.94 | 0 | 0 |  |  | UNPAID |  | Blank | 1
23S-119 | C000015869 | M844 | P.S. 138 ANNEX (OLD M047 AX) | 1214485 | 89905 | CIP | Lazicki, Rafal | PO 18 Asbestos Service | Initial | Closed | 2023-12-08 | 7800 | 2023-12-08 | 2023-12-09 | 198 | 2025-06-16 | 2131.98 | 0 | 0 |  |  | UNPAID |  | Blank | 1
22s-082 | C000015869 | R018 | P.S. 18 - STATEN ISLAND | 1158460 | 86961 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2023-01-23 | 190287.5 | 2023-02-16 | 2023-07-18 | 211 | 2025-06-24 | 37545.44 | 0 | 0 |  |  | UNPAID |  | Blank | 1
24S-011 | C000015869 | R022 | P.S. 22 - STATEN ISLAND | 1213407 | 82742 | CIP | Bracamonte, Jesus | LAP Construction Phase Services | Initial |  | 2024-01-09 | 5500 | [5 empty] | 0 | 0 |  |  | UNPAID |  | Blank | 0
24S-083 | C000015869 | R024 | I.S. 24 - STATEN ISLAND | 1304867 | 92944 | CIP | Bracamonte, Jesus | Special Program | Initial | Closed | 2024-08-15 | 4000 | 2024-08-20 | 2025-08-21 | 161 | 2025-05-07 | 2032.9 | 2032.9 | 0 | 854349 | 2025-06-16 | PAID | CHECK 24S-083 R024 | Has Data | 1
23S-138 | C000015869 | X039 | NEW SCH FOR ARTS AND SCIENCE - BRONX | 1196307 | 89315 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-09-19 | 14932.72 | 2024-08-23 | 2024-08-25 | 168 | 2025-05-22 | 13332.72 | 0 | 0 |  |  | UNPAID |  | Blank | 1
23S-025 | C000015869 | X041 | P.S. 41 - BRONX | 1174668 | 87890 | CIP | Kowalski, Zbigniew | PO 18 Asbestos Service | Initial | WIP | 2023-04-11 | 575 | [6 empty] | 0 |  |  | UNPAID |  | Blank | 0
23S-014 | C000015869 | X049 | P.S. 49 - BRONX | 1167051 | 87395 | CIP | Alawamleh, Eman | PO 18 Asbestos Service | Initial | Closed | 2023-02-14 | 575 | 2023-02-09 | 2023-02-12 | 91 | 2024-05-07 | 6073.75 | 6073.75 | 0 | 824042 | 2024-07-01 | PAID |  | Has Data | 1
24S-055 | C000015869 | X065 | P.S. 65 - BRONX | 1244229 | 92350 | CIP | Bracamonte, Jesus | PO 18 Asbestos Service | Initial | Closed | 2024-07-12 | 575 | 2024-10-24 | 2024-11-16 | 170 | 2025-05-22 | 17971.61 | 17971.61 | 0 | 855124 | 2025-06-23 | PAID | CHECK 24S-055 X065 | Has Data | 1
[19 empty] | 0 |  |  |  |  | Blank | 0
SID | JOB NO
84986 | 22S-005 | VLOOKUP(A22, A2:F18, 1) | no can do bc VLOOKUP cannot look left
|  | XLOOKUP(A22, F2:F18, A2:A18) | XLOOKUP - lookup the value in A22, 84986, in F column, F2:F18, and return the corresponding value in column A, A2:A18
SID | JOB NO | BID | SERVICE NAME | HYGIENIST |  | INVOICED AMT | EST COST | OVER/UNDER FLAG
86961 | 22s-082 | R018 | PO 18 Asbestos Service | Bracamonte, Jesus |  | 37545.44 | 190287.5 | UNDER BUDGET
UNIQUE FXN | Langlois, Bret | Hygienist 01
| Walsh, Joseph | Hygienist 02
| Palermo, Albert | Hygienist 03
| Towers, Daniel | Hygienist 04
| Scott, Richard | Hygienist 05
| Kordes, Kristin | Hygienist 06
| Lazicki, Rafal | Hygienist 07
| Kondilis, Milton | Hygienist 08
| Poskrobko, Lukasz | Hygienist 09
| Zarrabi, Abdi | Hygienist 10
| Alawamleh, Eman | Hygienist 11
| Kowalski, Zbigniew | Hygienist 12
| Clyne, Sean | Hygienist 13
| Bracamonte, Jesus | Hygienist 14
| 0 | Hygienist 15
| Vafiadis, Jon | Hygienist 16

## QUIZ LOGIC
A (Job Number) | B (Status) | C (Hygienist) | D (Est. Cost) | E (Paid?) | Valid Job No
19S-112 | In Progress | Joe | 3200 | Yes | 19 | True | TRUE | Valid
25S-045 | Completed | Marina | 1850 | No |  | True |  | Valid
22S-009 | Under Review | Vasili | 2400 | Yes |  | True |  | Valid
TEST | Not Started |  |  | No |  | True |  | Invalid
24S-210 | In Progress | Aleksandr | 3750 | Yes |  | True |  | Valid
20S-080 | Completed | Joe | 1950 | Yes |  | True |  | Valid
X101X | Unknown | TBD | 2000 | No |  | FALSE |  | Invalid
Count of Jobs Started |  | #REF!
VALUE FUNCTION
| RIGHT | VALUE-RIGHT | RIGHT ONLY IS # | VALUE-RIGHT IS #
| 112 | 112 | FALSE | TRUE

## 2025 JOB LIST
SAI FILE NO | PROJECT LOCATION | PROJECT DESCRIPTION | SCA SERVICE ID NO. | SCA PROJECT ID NO. | CONTACT PERSON | RFP No | DATE ON CHECK | Amount Received | Status | DATE COMPLETED | NOTE
25S-001 | Q165 | PO18 | 94416 | 141568 | MILTON | 186 | 2025-06-23 | 3943.88 | PAID
25S-002 | X475 | PO18 |  |  | ZB |  |  |  | Not Billed
25S-003 | K273 | PO18 | 94540 | 141670 | AL |  |  |  | Not Billed |  | EMERGENCY
25S-004 | Q189 | PO18 | 94758 | 141770 | MILTON |  |  |  | Not Billed |  | EMERGENCY
25S-005 | Q465 | CTF | 94367 | 139246 | JESUS |  |  |  | Not Billed
25S-006 | Q400 | CTF |  |  | JESUS |  |  |  | Not Billed
25S-007 | R024 | PO18 |  |  | JESUS |  |  |  | Not Billed
25S-008 | Q189 | PO18 | 94587 | 141701 | MILTON |  |  |  | Not Billed
25S-009 | K384 | PO18 | 94618 | 141715 | WALSH |  |  |  | Not Billed
25S-010 | X107 | PO18 | 94758 | 141770 | EMAN |  |  |  | Not Billed |  | EMERGENCY
25S-011 | X030 | PO18 |  |  | EMAN |  |  |  | Not Billed |  | EMERGENCY
25S-012 | K138 | PO18 | [6 empty] | Not Billed |  | EMERGENCY
25S-013 | Q192 | PO18 |  |  | MILTON |  |  |  | Not Billed
25S-014 | Q420 | CTF |  |  | JESUS |  |  |  | Not Billed |  | ROOM CONV
25S-015 | X131 | PO18 | 94778 | 141789 | EMAN |  |  |  | Not Billed
25S-016 | X005 | CTF | [6 empty] | Not Billed |  | ROOM CONV
25S-017 | K209 | CTF | [6 empty] | Not Billed
25S-018 | K495 | CTF | 95250 | [5 empty] | Not Billed
25S-019 | Q400 | CTF | [6 empty] | Not Billed |  | WA 1139042
25S-020 | M183 | CIP | 50159 | 77931 |  |  |  |  | Not Billed |  | OLD CIP 14S-195
25S-021 | Q465 | CTF Path of Travel |  |  | JESUS |  |  |  | Not Billed
25S-022 | [8 empty] | Not Billed
25S-023 | [8 empty] | Not Billed
25S-024 | [8 empty] | Not Billed
25S-025 | [8 empty] | Not Billed
25S-026 | [8 empty] | Not Billed
25S-027 | [8 empty] | Not Billed
25S-028 | [8 empty] | Not Billed
25S-029 | [8 empty] | Not Billed
25S-030 | [8 empty] | Not Billed
25S-031 | [8 empty] | Not Billed
25S-032 | [8 empty] | Not Billed
25S-033 | [8 empty] | Not Billed
25S-034 | [8 empty] | Not Billed
25S-035 | [8 empty] | Not Billed
25S-036 | [8 empty] | Not Billed
25S-037 | [8 empty] | Not Billed
25S-038 | [8 empty] | Not Billed
25S-039 | [8 empty] | Not Billed
25S-040 | [8 empty] | Not Billed
25S-041 | [8 empty] | Not Billed
25S-042 | [8 empty] | Not Billed
25S-043 | [8 empty] | Not Billed
25S-044 | [8 empty] | Not Billed
25S-045 | [8 empty] | Not Billed
25S-046 | [8 empty] | Not Billed
25S-047 | [8 empty] | Not Billed
25S-048 | [8 empty] | Not Billed
25S-049 | [8 empty] | Not Billed
25S-050 | [8 empty] | Not Billed
25S-051 | [8 empty] | Not Billed
25S-052 | [8 empty] | Not Billed
25S-053 | [8 empty] | Not Billed
25S-054 | [8 empty] | Not Billed
25S-055 | [8 empty] | Not Billed
25S-056 | [8 empty] | Not Billed
25S-057 | [8 empty] | Not Billed
25S-058 | [8 empty] | Not Billed
25S-059 | [8 empty] | Not Billed
25S-060 | [8 empty] | Not Billed
25S-061 | [8 empty] | Not Billed
25S-062 | [8 empty] | Not Billed
25S-063 | [8 empty] | Not Billed
25S-064 | [8 empty] | Not Billed
25S-065 | [8 empty] | Not Billed
25S-066 | [8 empty] | Not Billed
25S-067 | [8 empty] | Not Billed
25S-068 | [8 empty] | Not Billed
25S-069 | [8 empty] | Not Billed
25S-070 | [8 empty] | Not Billed
25S-071 | [8 empty] | Not Billed
25S-072 | [8 empty] | Not Billed
25S-073 | [8 empty] | Not Billed
25S-074 | [8 empty] | Not Billed
25S-075 | [8 empty] | Not Billed
25S-076 | [8 empty] | Not Billed
25S-077 | [8 empty] | Not Billed
25S-078 | [8 empty] | Not Billed
25S-079 | [8 empty] | Not Billed
25S-080 | [8 empty] | Not Billed
25S-081 | [8 empty] | Not Billed
25S-082 | [8 empty] | Not Billed
25S-083 | [8 empty] | Not Billed
25S-084 | [8 empty] | Not Billed
25S-085 | [8 empty] | Not Billed
25S-086 | [8 empty] | Not Billed
25S-087 | [8 empty] | Not Billed
25S-088 | [8 empty] | Not Billed
25S-089 | [8 empty] | Not Billed
25S-090 | [8 empty] | Not Billed
25S-091 | [8 empty] | Not Billed
25S-092 | [8 empty] | Not Billed
25S-093 | [8 empty] | Not Billed
25S-094 | [8 empty] | Not Billed
25S-095 | [8 empty] | Not Billed
25S-096 | [8 empty] | Not Billed
25S-097 | [8 empty] | Not Billed
25S-098 | [8 empty] | Not Billed
25S-099 | [8 empty] | Not Billed
25S-100 | [8 empty] | Not Billed
25S-101 | [8 empty] | Not Billed
25S-102 | [8 empty] | Not Billed
25S-103 | [8 empty] | Not Billed
25S-104 | [8 empty] | Not Billed
25S-105 | [8 empty] | Not Billed
25S-106 | [8 empty] | Not Billed
25S-107 | [8 empty] | Not Billed
25S-108 | [8 empty] | Not Billed
25S-109 | [8 empty] | Not Billed
25S-110 | [8 empty] | Not Billed
25S-111 | [8 empty] | Not Billed
25S-112 | [8 empty] | Not Billed
25S-113 | [8 empty] | Not Billed
25S-114 | [8 empty] | Not Billed
25S-115 | [8 empty] | Not Billed
25S-116 | [8 empty] | Not Billed
25S-117 | [8 empty] | Not Billed
25S-118 | [8 empty] | Not Billed
25S-119 | [8 empty] | Not Billed
25S-120 | [8 empty] | Not Billed
25S-121 | [8 empty] | Not Billed
25S-122 | [8 empty] | Not Billed
25S-123 | [8 empty] | Not Billed
25S-124 | [8 empty] | Not Billed
25S-125 | [8 empty] | Not Billed
25S-126 | [8 empty] | Not Billed
25S-127 | [8 empty] | Not Billed
25S-128 | [8 empty] | Not Billed
25S-129 | [8 empty] | Not Billed
25S-130 | [8 empty] | Not Billed
25S-131 | [8 empty] | Not Billed
25S-132 | [8 empty] | Not Billed
25S-133 | [8 empty] | Not Billed
25S-134 | [8 empty] | Not Billed
25S-135 | [8 empty] | Not Billed
25S-136 | [8 empty] | Not Billed
25S-137 | [8 empty] | Not Billed
25S-138 | [8 empty] | Not Billed
25S-139 | [8 empty] | Not Billed
25S-140 | [8 empty] | Not Billed
25S-141 | [8 empty] | Not Billed
25S-142 | [8 empty] | Not Billed

## 2024 JOB LIST
SAI FILE NO. | PROJECT LOCATION | PROJECT DESCRIPTION | SCA SERVICE ID NO. | SCA PROJECT ID NO. | CONTACT PERSON | RFP No | Date On Check | Amount Received | Status | SAI PROJECT MGR | DATE ASSIGNED | DATE COMPLETED | NOTE
24S-001 | R060 | [7 empty] | Not Billed |  |  |  | ext sign by AUD walls
24S-002 | M440 | PO 18 | 90375 | 138341 | Rafal |  |  |  | Not Billed | DB | 2024-01-10
24S-003 | M187 | PO 18 | 90610 | 138462 | Eman | 131 | 2024-10-25 | 17848.38 | PAID | DB | 2024-02-05 |  | Emergency
24S-004 | K050 | CTF | 90587 | 138375 | Jesus |  |  |  | Not Billed | DB | 2024-02-16
24S-005 | R435 | CIP | 90083 | 130440 | Jesus | 215 |  |  | UNPAID | DB | 2024-01-04
24S-006 | M192 | PO 18 | 90701 | 138488 | Eman |  |  |  | Not Billed | DB | 2024-02-05
24S-007 | K261 | CIP / CTF | 90763 | P026332 | Jesus |  |  |  | Not Billed | DB | 2024-02-21
24S-008 | R002 | PO 18 | 91184 | 138746 | Jesus |  |  |  | Not Billed | DB | 2024-03-13
24S-009 | Q460 | PO 18 | 90480 | 138411 | Milton |  |  |  | Not Billed | DB | 2024-01-30
24S-010 | Q021 | PO 18 |  |  | Milton |  |  |  | Not Billed | DB | 2024-03-14 |  | Emergency
24S-011 | R022 | CIP | 82742 | D019615 | Jesus |  |  |  | Not Billed | DB | 2024-01-09
24S-012 | K017 | PO 18 | 90624 | 138470 | Walsh |  |  |  | Not Billed | DB | 2024-02-08
24S-013 | Q460 | PO 18 | 90784 | 138614 | Milton |  |  |  | Not Billed | DB | 2024-02-28
24S-014 | K160 | PO 18 | 90892 | 138638 | Scott |  |  |  | Not Billed | DB | 2024-02-28
24S-015 | Q165 | PO 18 | 88306 | 135518 | Milton |  |  |  | Not Billed | DB | 3/08/20224
24S-016 | K232 | CTF | 89776 | 126994 | Jesus |  |  |  | Not Billed | DB | 2024-03-13
24S-017 | K232 | CTF | 89766 | 126993 | Jesus |  |  |  | Not Billed | DB | 2024-03-14
24S-018 | K232 | CTF | 89768 | 126995 | Jesus |  |  |  | Not Billed | DB | 2024-03-14
24S-019 | Q225 | CTF | 89359 | 133978 | Jesus |  |  |  | Not Billed | DB | 2024-03-14
24S-020 | Q225 | CTF | 89963 | 133979 | Jesus |  |  |  | Not Billed | DB | 2024-03-14
24S-021 | R075 | PO 18 | 91329 | 138795 | Jesus |  |  |  | Not Billed | DB | 2024-03-21
24S-022 | M028 | PO18 | 91258 | 138763 | Eman | 240 |  |  | UNPAID | DB | 2024-03-20
24S-023 | M163 | PO18 | 91391 | 138821 | Rafal |  |  |  | Not Billed | DB | 2024-03-26
24S-024 | M465 | PO18 | 91363 | 138803 | Eman |  |  |  | Not Billed | DB | 2024-02-11 |  | ?
24S-025 | Q021 | PO18 | 91310 | 138782 | Milton |  |  |  | Not Billed | DB | 2024-03-27 |  | ?
24S-026 | K620 | CTF | 91352 | 125571 | Jesus |  |  |  | Not Billed | DB | 2024-03-27
24S-027 | Q067 | PO18 | 90816 | 138625 | Milton |  |  |  | Not Billed | DB | 2024-04-02
24S-028 | Q141 | PO18 | 91394 | 138818 | Lukasz |  |  |  | Not Billed | DB | 2024-04-17
24S-029 | Q442 | PO18 |  |  | Milton |  |  |  | Not Billed | DB
24S-030 | K600 | PO18 | 91760 | 139066 | Al | 209 |  |  | UNPAID | DB | 2024-05-03
24S-031 | Q023 | PO18 | 91807 | 139091 | Milton | 135 | 2024-11-06 | 4933.3 | PAID | DB | 2024-05-04 | Emergency
24S-032 | Q442 | PO18 | 91854 | 139110 | Milton |  |  |  | Not Billed | DB | 2024-05-14 | Crawl Space
24S-033 | R013 | CTF | 91809 | 138991 | Jesus |  |  |  | Not Billed | DB | 2024-05-09 | Room Conversion
24S-034 | R013 | CTF | 91836 | 138990 | Jesus |  |  |  | Not Billed | DB | 2024-05-10 | Path of Travel
24S-035 | Q037 | CTF | 91801 | 138692 | Jesus |  |  |  | Not Billed | DB | 2024-05-10 | Path of Travel
24S-036 | Q037 | CTF | 91803 | 138669 | Jesus |  |  |  | Not Billed | DB | 2024-05-10 | Room Conversion
24S-037 | Q442 | PO18 | 91832 | 139100 | Milton |  |  |  | Not Billed | DB | 2024-05-14 | Gym Entire
24S-038 | K104 | PO18 | 91880 | 139122 | Scott |  |  |  | Not Billed | DB | 2024-05-23
24S-039 | X049 | PO18 |  |  | Eman |  |  |  | Not Billed | DB | 2024-05-31 | Emergency
24S-040 | Q231 | Special Program |  |  | Milton |  |  |  | Not Billed | DB
24S-041 | Q203 | PO18 |  |  | Milton | 136 | 2024-11-06 | 3557.55 | PAID | DB |  | Emergency
24S-042 | M064 | PO18 |  |  | Rafal | 200 |  |  | UNPAID | DB
24S-043 | R008 | PO18 | 92211 | 139298 | Jesus | 160 | 2025-05-12 | 2152.98 | PAID | DB
24S-044 | X074 | CIP | 91863 | 137129 | Eman |  |  |  | Not Billed | DB | 2024-05-28
24S-045 | K316 | CTF | 91953 | 135593 | Jesus | 199 | 2025-06-23 | 5530.33 | PAID | DB | 2024-05-30
24S-046 | R040 | PO18 | 89229 | 136104 | Jesus |  |  |  | Not Billed | DB | 2024-06-03
24S-047 | Q024 | PO18 | 91978 | 139172 | Milton |  |  |  | Not Billed | DB | 2024-06-05
24S-048 | M050 | PO18 | 91997 | 139182 | Rafal |  |  |  | Not Billed | DB | 2024-06-10
24S-049 | M115 | CTF | 92097 | 138655 | Jesus |  |  |  | Not Billed | DB | 2024-06-12 |  | PATH OF TRAVEL
24S-050 | R455 | PO18 |  |  | Jesus |  |  |  | Not Billed | DB | 2024-06-14 | Emergency
24S-051 | Q023 |  | 92210 | 139296 | Milton | 174 | 2025-06-20 | 1901 | PAID | DB | 2024-06-21
24S-052 | Q438 | PO18 | 92209 | 139297 | Milton |  |  |  | Not Billed | DB | 2024-06-21 |  | Safe Access
24S-053 | M152 | PO18 | 92223 | 139302 | Eman |  |  |  | Not Billed | DB | 2024-06-21
24S-054 | K162 | PO18 | 92352 | 139348 | Walsh |  |  |  | Not Billed | DB | 2024-07-02
24S-055 | X065 | PO18 | 92350 | 139346 | Eman | 170 | 2025-06-23 | 17971.61 | PAID | DB | 2024-07-12
24S-056 | Q480 | Special Program | 92299 | 134515 | Milton | 142 | 2025-02-08 | 2273.91 | PAID | DB | 2024-06-27
24S-057 | X005 | CTF | 92195 | 138646 | Jesus |  |  |  | Not Billed | DB | 2024-06-28
24S-058 | X149 | CTF | 92199 | 138999 | Jesus |  |  |  | Not Billed | DB | 2024-06-28
24S-059 | Q203 | PO18 | 92007 | 139199 | Milton |  |  |  | Not Billed | DB | 2024-07-01
24S-060 | Q023 | PO18 | 92257 | 139321 | Milton | 153 | 2025-06-04 | 6963.25 | PAID | DB | 2024-07-02
24S-061 | K151 | PO18 | 92321 | 139327 | Walsh |  |  |  | Not Billed | DB
24S-062 | K650 | PO18 | 92439 | 139398 | Walsh | 246 |  |  | UNPAID | DB | 2024-07-10
24S-063 | K095 | Special Program | 92557 | 134178 | Jesus | 154 | 2025-06-12 | 3574.99 | PAID | DB | 2024-07-21
24S-064 | K162 | Special Program | 92561 | 134192 | Jesus | 150 | 2025-05-19 | 2284.61 | PAID | DB | 2024-07-21
24S-065 | R059 | Special Program | 92564 | 135804 | Jesus | 175 |  |  | UNPAID | DB | 2024-07-24
24S-066 | K265 | Special Program | 92598 | 134232 | Jesus | 225 |  |  | UNPAID | DB | 2024-07-24
24S-067 | R831 | Special Program | 92576 | 135143 | Jesus | 145 | 2025-01-22 | 2338.38 | PAID | DB | 2024-07-24
24S-068 | K085 | Special Program | 92638 | 134176 | Jesus | 185 |  |  | UNPAID | DB | 2024-07-24
24S-069 | K874 | Special Program | 92644 | 134311 | Jesus | 208 |  |  | UNPAID | DB | 2024-07-24
24S-070 | X470 | PO18 | 85247 | 131479 | Eman |  |  |  | Not Billed | DB |  |  | Trio
24S-071 | M615 | PO18 | 92332 | 139333 | Rafal | 164 | 2025-06-06 | 6586.68 | PAID | DB | 2024-07-25
24S-072 | K051 | Special Program | 92774 | 134166 | Jesus | 156 | 2025-06-12 | 2236.93 | PAID | DB | 2024-08-04
24S-073 | K455 | Special Program | 92773 | 134275 | Jesus |  |  |  | Not Billed | DB | 2024-08-04
24S-074 | K231 | Special Program | 92767 | 139519 | Jesus | 141 | 2025-01-28 | 2483.03 | PAID | DB | 2024-08-04
24S-075 | M125 | CTF | 92796 | 138657 | Jesus |  |  |  | Not Billed | DB | 2024-08-06
24S-076 | Q089 | PO18 | 91977 | 139171 | Lukasz | 184 | 2025-06-13 | 11142.81 | PAID | DB | 2024-08-09
24S-077 | R455 | PO18 | 92921 | 139697 | Jesus |  |  |  | Not Billed | DB | 2024-08-10 |  | Emergency
24S-078 | M028 | PO18 |  |  | Eman | 214 |  |  | UNPAID | DB |  |  | Emergency
24S-079 | K114 | Special Program | 92925 | 134183 | Jesus | 166 | 2025-06-23 | 2454.75 | PAID | DB | 2024-08-13 |  | ABC
24S-080 | K184 | Special Program | 92928 | 134201 | Jesus | 167 | 2025-06-23 | 3285.06 | PAID | DB | 2024-08-13 |  | ABC
24S-081 | K174 | Special Program | 92927 | 134195 | Jesus | 165 | 2025-06-23 | 2732.08 | PAID | DB | 2024-08-13 |  | ABC
24S-082 | K246 | Special Program | 92924 | 134227 | Jesus | 159 | 2025-06-16 | 2629.78 | PAID | DB | 2024-08-13 |  | ABC
24S-083 | R024 | Special Program | 92944 | 134539 | Jesus | 161 | 2025-06-16 | 2032.9 | PAID | DB | 2024-08-15 |  | D&S
24S-084 | R002 | Special Program | 93968 | 134573 | Jesus |  |  |  | Not Billed | DB | 2024-08-15
24S-085 | R435 | Special Program | 92950 | 134552 | Jesus |  |  |  | Not Billed | DB | 2024-08-16 |  | ABC
24S-086 | R034 | Special Program | 92969 | 134541 | Jesus | 180 |  |  | UNPAID | DB | 2024-08-16 |  | ABC
24S-087 | K932 | Special Program | 92976 | 139711 | Jesus |  |  |  | Not Billed | DB | 2024-08-16 |  | ABC
24S-088 | X086 | PO18 | 92919 | 139699 |  | 243 |  |  | UNPAID | DB | 2024-08-19
24S-089 | R026 | PO18 | 93264 | 140876 | Jesus |  |  |  | Not Billed | DB | 2024-09-04 |  | Emergency
24S-090 | K061 | PO18 | 93260 | 140886 |  | 213 |  |  | UNPAID | DB | 2024-09-06 |  | Emergency
24S-091 | R825 | PO18 | 93259 | 140887 | Jesus | 169 | 2025-06-16 | 3502.58 | PAID | DB |  |  | Emergency
24S-092 | K166 | Special Program | 93184 | 134193 | Jesus | 191 |  |  | UNPAID | DB | 2024-09-04
24S-093 | R450 | Special Program | 93188 | 134555 | Jesus |  |  |  | Not Billed | DB | 2024-09-04
24S-094 | K285 | Special Program | 93226 | 134237 | Jesus |  |  |  | Not Billed | DB | 2024-09-05
24S-095 | K804 | Special Program | 93227 | 134307 | Jesus |  |  |  | Not Billed | DB | 2024-09-05
24S-096 | K207 | Special Program | 93230 | 134208 | Jesus |  |  |  | Not Billed | DB | 2024-09-05
24S-097 | X028 | PO18 | 93164 | 140851 |  | 230 |  |  | UNPAID | DB | 2024-08-30
24S-098 | R055 | PO18 | 93283 | 140895 | Jesus |  |  |  | Not Billed | DB | 2024-09-13
24S-099 | R440 | PO18 |  |  | Jesus | 146 | 2025-02-11 | 10352.63 | PAID | DB | 2024-09-13
24S-100 | M052 | CTF | 93321 | D016339 | Jesus |  |  |  | Not Billed | DB | 2024-09-17
24S-101 | Q188 | PO18 | 92693 | 139494 | Milton |  |  |  | Not Billed | DB | 2024-07-29
24S-102 | K495 | CTF | 93224 | 138887 | Jesus |  |  |  | Not Billed | DB | 2024-09-25
24S-103 | K145 | PO18 | 93324 | 140906 | Walsh | 190 |  |  | UNPAID | DB | 2024-09-20
24S-104 | M152 | PO18 | 93137 | 140831 | Eman |  |  |  | Not Billed |  | 2024-09-20
24S-105 | K244 | PO18 | 93485 | 141014 |  |  |  |  | Not Billed |  | 2024-09-27
24S-106 | K540 | Special Program | 93482 | 134289 | Jesus |  |  |  | Not Billed |  | 2024-09-30
24S-107 | K445 | Special Program | 93454 | 34273 | Jesus | 177 |  |  | UNPAID |  | 2024-09-30
24S-108 | K027 | Special Program | 93452 | 134159 | Jesus | 245 |  |  | UNPAID |  | 2024-09-30
24S-109 | K425 | Special Program | 93480 | 134268 | Jesus | 194 |  |  | UNPAID |  | 2024-09-30
24S-110 | K505 | Special Program | 93451 | 134286 | Jesus | 178 |  |  | UNPAID |  | 2024-09-30
24S-111 | K209 | CTF | 93439 | 139063 | Jesus |  |  |  | Not Billed |  | 2024-10-02
24S-112 | Q126 | PO18 |  |  | Lukasz | 242 |  |  | UNPAID |  | 2024-10-04 |  | Emergency
24S-113 | Q166 | PO18 | 93419 | 140946 | Lukasz |  |  |  | Not Billed |  | 2024-10-03
24S-114 | M180 | PO18 | 93632 | 141149 | Rafal | 202 |  |  | UNPAID |  | 2024-10-10
24S-115 | M124 | PO18 | 93166 | 140849 | Rafal |  |  |  | Not Billed |  | 2024-10-10
24S-116 | M615 | PO18 | 92332 | 139333 | Rafal |  |  |  | Not Billed |  | 2024-10-10
24S-117 | M115 | CTF | 91046 | 138658 | Jesus |  |  |  | Not Billed |  | 2024-10-09 |  | RM CONVERSION
24S-118 | X139 | PO18 |  |  | Eman |  |  |  | Not Billed |  | 2024-10-18
24S-119 | K515 | Special Program | 93750 | 134287 | Jesus | 244 |  |  | UNPAID |  | 2024-10-22
24S-120 | K226 | Special Program | 93720 | 134216 | Jesus |  |  |  | Not Billed |  | 2024-10-22
24S-121 | K370 | Special Program | 93721 | 134254 | Jesus | 193 |  |  | UNPAID |  | 2024-10-22
24S-122 | X107 | CIP/LSP | 93698 | P026394 | Jesus |  |  |  | Not Billed |  | 2024-10-28
24S-123 | R040 | Special Program | 93874 | 134542 | Jesus |  |  |  | Not Billed |  | 2024-11-07
24S-124 | K486 | Special Program | 93871 | 134282 | Jesus | 204 |  |  | UNPAID |  | 2024-11-07
24S-125 | K124 | CIP/CTF | 93864 | 136155 | Jesus |  |  |  | Not Billed |  | 2024-11-08
24S-126 | K316 | PO18 |  |  | Al | 206 |  |  | UNPAID |  | 2024-11-22 |  | Emergency
24S-127 | M192 | PO18 | 94022 | 141287 | Eman |  |  |  | Not Billed |  | 2024-11-18
24S-128 | K043 | Special Program | 93925 | 134162 | Jesus |  |  |  | Not Billed |  | 2024-11-13
24S-129 | K171 | Special Program | 93926 | 134194 | Jesus |  |  |  | Not Billed |  | 2024-11-13
24S-130 | K851 | Special Program | 93959 | 141265 | Jesus |  |  |  | Not Billed |  | 2024-11-13
24S-131 | Q490 | PO18 | 94153 | 141420 | Milton |  |  |  | Not Billed |  | 2024-12-02
24S-132 | Q420 | CTF | 93724 | 139250 | Jesus |  |  |  | Not Billed |  | 2024-12-02
24S-133 | Q420 | CTF Path of Travel | 93726 | 139251 | Jesus |  |  |  | Not Billed |  | 2024-12-02
24S-134 | M480 | PO18 |  |  | Rafal | 155 | 2025-06-04 | 2437.03 | PAID |  | 2024-12-04 |  | Emergency
24S-135 | M099 | PO18 |  |  | Rafal |  |  |  | Not Billed |  | 2024-12-04 |  | Emergency
24S-136 | K164 | PO18 | 93856 | 141228 | Scott | 228 |  |  | UNPAID |  | 2024-11-19 |  | 3RD FL RM 301,302
24S-137 | M501 | PO18 | 94197 | 141449 | Eman |  |  |  | Not Billed |  | 2024-12-10
24S-138 | Q200 | PO18 |  |  | Milton |  |  |  | Not Billed |  | 2024-12-11
24S-139 | Q185 | PO18 |  |  | Milton | 173 | 2025-06-20 | 9674.83 | PAID |  |  |  | Emergency
24S-140 | M660 | PO18 |  |  | Rafal | 205 |  |  | UNPAID |  | 2024-12-20
24S-141 | K799 | Special Program | 194278 | 141500 |  | 183 |  |  | UNPAID
24S-142 | R883 | Special Program |  |  |  | 212 |  |  | UNPAID
24S-143 | X101 | CTF | 94177 | 138997 | Jesus |  |  |  | Not Billed |  | 2024-12-09
24S-144 | M540 | PO18 |  |  | Eman |  |  |  | Not Billed |  | 2024-12-31 |  | Emergency
24S-145 | K854 | Special Program | 94350 | 141547 | Jesus |  |  |  | Not Billed |  | 2024-12-26
24S-146 | X142 | PO18 | 94124 | 141388 |  |  |  |  | Not Billed |  | 2024-12-30
24S-147 | X102 | CIP | 93969 | P095418 | Jesus |  |  |  | Not Billed |  | 2024-12-26
24S-148 | M061 | PO18 | 92654 | 139470 | Rafal |  |  |  | Not Billed |  | 2024-07-25
24S-149 | M125 | CTF / Path of Travel | 94453 | 138656 | Jesus |  |  |  | Not Billed |  | 2025-02-20

## 2023 JOB LIST
SAI FILE NO. | PROJECT LOCATION | PROJECT DESCRIPTION | SCA SERVICE ID NO. | SCA PROJECT ID NO. | CONTACT PERSON | RFP No | Date On Check | Amount Received | Status | SAI PROJECT MGR | DATE ASSIGNED | DATE COMPLETED | NOTE
23S-001 | Q800 - DOE Administrative | PO18 | 86152 | 131978 | Lukasz |  |  |  | Not Billed | D.B. | 2023-01-03
23S-002 | Q450 NEWCOMERS HS | CIP / CTF | 87016 | 130436 | Lukasz | 234 |  |  | UNPAID | D.B. | 2023-01-04
23S-003 | I.S. 101X | CIP / CTF | 87019 | 133271 | Jesus | 132 | 2024-10-01 | 37718.95 | PAID | D.B. | 2023-02-03
23S-004 | I.S. 126Q | PO18 | 86983 | 133506 | Lukasz | 68 | 2024-05-08 | 25616.36 | PAID | D.B. | 2023-01-04
23S-005 | P.S. 183K | PO18 | 87043 | 133573 | Alpal |  |  |  | Not Billed | D.B. | 2023-01-10
23S-006 | P.S. 205Q | CIP / CTF | 86946 | 133383 | Jesus | 235 |  |  | UNPAID | D.B. | 2023-01-11
23S-007 | I.S. 210Q | PO18 | 87036 | 133567 | Lukasz | 115 | 2024-08-27 | 48501.86 | PAID | D.B. | 2023-01-13
23S-008 | K600 CLARA BARTON | CTF | 87001 | 131441 | Jesus | 120 | 2024-08-28 | 11247.98 | PAID | D.B. | 2023-01-24
23S-009 | P.S. 263K | PO18 | 87190 | 133662 | Alpal | 111 | 2024-09-12 | 10960.83 | PAID | D.B. | 2023-01-26
23S-010 | P.S. 221Q | PO18 | 87060 | 133583 | Milton | 90 | 2024-07-05 | 39716.84 | PAID | D.B. | 2023-01-27
23S-011 | P.S. 35Q | PO18 | 87037 | 133568 | Milton | 102 | 2024-07-30 | 71368.5 | PAID | D.B. | 2023-01-31
23S-012 | Q801 | PO18 | 87297 | 133700 | Lukasz | 31 | 2023-08-04 | 11664.66 | PAID | D.B. | 2023-02-06
23S-013 | X401 | PO18 | 87286 | 133690 | ZB | 51 | 2024-03-18 | 7268.63 | PAID | D.B. | 2023-02-06
23S-014 | P.S. 49X | PO18 | 87395 | 133575 | Eman | 91 | 2024-07-01 | 6073.75 | PAID | D.B. | 2023-02-14
23S-015 | P.S. 242 - M144 | PO18 | 87340 | 133710 | Rafal | 109 | 2024-07-29 | 7130.58 | PAID | D.B. | 2023-02-08
23S-016 | P.S. 54K | PO18 | 87386 | 133746 | J. Walsh | 28 | 2023-07-19 | 6616.23 | PAID | D.B. | 2023-02-10
23S-017 | P.S. 86K | PO18 | 87459 | 133942 | J. Walsh |  |  |  | Not Billed | D.B. | 2/29/2023
23S-018 | P.S. 277X | PO18 | 87524 | 133971 | Eman | 88 | 2024-07-01 | 8304.05 | PAID | D.B. | 2023-03-02
23S-019 | M490 | CTF | 87398 | P026180 | Jesus | 72 | 2024-09-17 | 18216.88 | PAID | D.B. | 2023-02-16
23S-020 | Q725 | CTF | 87585 | 131396 | Jesus | 119 | 2024-08-14 | 10752.68 | PAID | D.B. | 2023-03-09
23S-021 | R061 | PO18 | 87748 | 134051 | Jesus | 196 | 2025-06-23 | 4501.55 | PAID | D.B. | 2023-03-27
23S-022 | P.S. 132X | PO18 | 82902 | 128159 | ZB |  |  |  | Not Billed | D.B. | 2023-03-16
23S-023 | Q450 NEWCOMERS HS | PO18 | 87897 | 134138 | Lukasz | 59 | 2024-04-02 | 7810.55 | PAID | D.B. | 2023-04-13
23S-024 | R460 | CTF | 87850 | P026163 | Jesus | 46 | 2023-11-08 | 8225.58 | PAID | D.B. | 2023-04-10
23S-025 | P.S. 41X | PO18 | 87890 | 134136 | ZB |  |  |  | Not Billed | D.B. | 2023-04-11
23S-026 | Q223 | CTF | 87623 | 131064 | Jesus | 207 |  |  | UNPAID | D.B. | 2023-04-12
23S-027 | P.S. 26R | PO18 | 87998 | 135301 | Jesus | 36 | 2023-08-04 | 6062.8 | PAID | D.B. | 2023-04-28
23S-028 | M440 | PO18 | 88001 | 135307 | Rafal | 124 | 2024-08-30 | 2603.21 | PAID | D.B. | 2023-04-28
23S-029 | P.S. 128K | PO18 | 88004 | 135304 | Seau | 210 |  |  | UNPAID | D.B. | 2023-04-25
23S-030 | P.S. 34R | PO18 | 88108 | 135371 | Jesus | 37 | 2023-08-04 | 5264.23 | PAID | D.B. | 2023-05-12
23S-031 | P.S. 14Q | PO18 | 88171 | 135414 | Lukasz | 104 | 2024-07-01 | 4293.03 | PAID | D.B. | 2023-05-16
23S-032 | M520 | CIP | 87777 | 130024 | Rafal |  |  |  | Not Billed | V.B. | 2023-07-19
23S-033 | P.S. 66M | PO18 | 87470 | 133948 | Rafal | 236 |  |  | UNPAID | D.B. | 2023-05-04
23S-034 | P.S. 80X | PO18 | 87691 | 134037 | ZB | 79 | 2024-06-20 | 20602.27 | PAID | D.B. | 2023-05-12
23S-035 | X470 | PO18 | 87938 | 135267 | Eman | 64 | 2025-04-28 | 7061.55 | PAID | D.B. | 2023-05-10
23S-036 | M133 | PO18 | 88183 | 135417 | Eman | 87 | 2024-07-01 | 6212.43 | PAID | D.B. | 2023-05-17
23S-037 | M001 | CIP | [6 empty] | Not Billed
23S-038 | P.S. 19X | PO18 | 88212 | 135441 | ZB | 133 | 2024-11-06 | 13225.51 | PAID | D.B. | 2023-05-18
23S-039 | M155 | PO18 | 88234 | 135459 | Rafal | 61 | 2024-05-02 | 5751.75 | PAID | D.B. | 2023-05-23
23S-040 | Q475 | PO18 | 88287 | 135491 | Lukasz | 62 | 2024-04-08 | 5783.81 | PAID | D.B. | 2023-05-30
23S-041 | X807 | PO18 | 88248 | 135467 | Eman |  |  |  | Not Billed | D.B. | 2023-05-24
23S-042 | I.S. 364K | PO18 | 88107 | 135370 | Alpal | 47 | 2024-02-13 | 7578.28 | PAID | D.B. | 2023-05-16
23S-043 | P.S. 2R | PO18 |  |  | Jesus | 44 | 2023-10-24 | 8535.7 | PAID | D.B.
23S-044 | Q397 | PO18 |  |  | Lukasz | 49 | 2023-11-08 | 7665.88 | PAID | D.B. | 2023-06-07 |  | Emergency
23S-045 | P.S. 115M | PO18 | 88295 | 135498 | Eman | 181 | 2025-06-23 | 60014.45 | PAID | D.B. | 2023-06-08
23S-046 | K505 FRANKLIN ROOSEVELT | PO18 |  |  | Scott |  |  |  | Not Billed | D.B.
23S-047 | P.S. 79Q | PO18 | 88112 | 135374 | Milton |  |  |  | Not Billed | D.B. | 2023-06-07
23S-048 | M520 | CIP | 87328 | 130026 | Rafal | 113 | 2024-08-15 | 31267.67 | PAID | D.B. | 2023-07-19 |  | Auditorium
23S-049 | P.S. 128K | PO18 | 88464 | 135562 | Seau | 217 |  |  | UNPAID | D.B. | 2023-06-15 |  | Emergency
23S-050 | P.S. 289K | PO18 | 88347 | 135526 | Alpal | 123 | 2024-10-10 | 7078.33 | PAID | D.B. | 2023-06-16
23S-051 | P.S. 18R | PO18 |  |  | Jesus |  |  |  | Not Billed | D.B. |  |  | Steam Line
23S-052 | P.S. 107X | PO18 | 88307 | 135515 | Eman |  |  |  | Not Billed | D.B. | 2023-06-21
23S-053 | P.S. 101X | PO18 | 88398 | 135554 | Eman | 58 | 2024-05-09 | 6284.13 | PAID | D.B. | 2023-06-15
23S-054 | P.S. 128M | PO18 | 88621 | 135645 | Eman | 106 | 2024-07-29 | 17521.67 | PAID | D.B. | 2023-07-06
23S-055 | P.S. 140M | CIP | [6 empty] | Not Billed | D.B.
23S-056 | R445 TOTTENVILLE HS | PO18 | 88731 | 135678 | Jesus | 224 |  |  | UNPAID | D.B. |  |  | Emergency
23S-057 | P.S. 196Q | PO18 |  |  | Lukasz |  |  |  | Not Billed | D.B.
23S-058 | P.S. 101X | CTF | 88631 | 133632 | Jesus | 100 | 2024-06-17 | 6341.5 | PAID | D.B. | 2023-07-19
23S-059 | P.S. 85X | PO18 | 88763 | 135845 | ZB | 158 | 2025-06-23 | 20155.11 | PAID | D.B. | 2023-07-19
23S-060 | M520 | LSP | 87777 | 130024 | Rafal | 149 | 2025-06-03 | 2131.98 | PAID | D.B. | 2023-07-14
23S-061 | M520 | LSP | 87328 | 130026 | Rafal |  |  |  | Not Billed | D.B. | 2023-07-19 |  | Auditorium Upgrade
23S-062 | P.S. 30Q | PO18 | 88617 | 135641 | Lukasz | 125 | 2024-09-12 | 20699.7 | PAID | D.B. | 2023-07-19 |  | Bralay 718-795-3586 Regard ASB
23S-063 | P.S. 176Q | PO18 | 88205 | 135438 | Milton |  |  |  | Not Billed | D.B. | 2023-07-24
23S-064 | P.S. 11X | PO18 | 88729 | 135676 | ZB | 94 | 2024-07-05 | 5219.18 | PAID | D.B. | 2023-07-24
23S-065 | P.S. 85X | PO18 | 88845 | 135869 | ZB | 92 | 2024-06-25 | 4410.05 | PAID | D.B. | 2023-07-24
23S-066 | P.S. 142K | CIP | 88679 | 132168 | Jesus |  |  |  | Not Billed | D.B. | 2023-07-24
23S-067 | P.S. 111K | PO18 | 88871 | 135879 | J. Walsh |  |  |  | Not Billed | D.B. | 2023-07-26
23S-068 | Q456 | PO18 |  |  |  | 56 | 2024-04-24 | 5992.9 | PAID |  | 2023-07-27 |  | Emergency
23S-069 | K445 NEW UTRECHT | PO18 | 88602 | 135632 | Scott | 107 | 2024-08-12 | 29861.89 | PAID | D.B. | 2023-07-13
23S-070 | P.S. 29Q | CIP | 88759 | D018318 | Milton | 237 |  |  | UNPAID | D.B. | 2023-07-25
23S-071 | P.S. 217Q | CIP | 88787 | D021615 | Lukasz |  |  |  | Not Billed | D.B. | 2023-07-26
23S-072 | P.S. 335K | PO18 | 88935 | 135918 | Alpal | 73 | 2024-07-05 | 20514.03 | PAID | D.B. | 2023-08-11 |  | 2nd Floor
23S-073 | P.S. 22Q | PO18 | 88744 | 135691 | Milton | 219 |  |  | UNPAID | D.B. | 2023-08-02
23S-074 | P.S. 53R | PO18 | 88746 | 135693 | Jesus |  |  |  | Not Billed | D.B. | 2023-08-07
23S-075 | P.S. 335K | PO18 | 88936 | 135919 | Alpal |  |  |  | Not Billed | D.B. | 2023-08-14 |  | 3rd Floor
23S-076 | P.S. 193Q | PO18 | 88616 | 135640 | Milton |  |  |  | Not Billed | D.B. | 2023-08-14
23S-077 | P.S. 38Q | PO18 | 88352 | 135531 | Milton | 152 | 2025-06-05 | 27200.01 | PAID | D.B. | 2023-08-14
23S-078 | P.S. 169M | CIP | 88870 | P025923 | Rafal |  |  |  | Not Billed | D.B. | 2023-08-15
23S-079 | P.S. 287K | PO18 | 89110 | 136064 | Joseph | 157 | 1966-04-04 09:07 | 24201.38 | PAID | D.B. | 2023-08-16
23S-080 | P.S. 40P | PO18 |  |  | Joseph | 126 | 2024-08-28 | 2964.88 | PAID | D.B. | 2023-08-30 |  | Emergency
23S-081 | K804 JOHN JAY | PO18 | 88907 | 135899 | Scott |  |  |  | Not Billed | D.B.
23S-082 | P.S. 146X | PO18 |  |  | Eman |  |  |  | Not Billed | D.B. | 2023-09-05 |  | Emergency
23S-083 | P.S. 804K | PO18 | [6 empty] | Not Billed | D.B.
23S-084 | P.S. 150K | PO18 | 89302 | 137053 | Alpal |  |  |  | Not Billed | D.B. | 2023-09-12
23S-085 | P.S. 5X | PO18 | 89249 | 136110 | Eman | 84 | 2024-07-01 | 11013.5 | PAID | D.B. | 2023-09-13 |  | Emergency
23S-086 | P.S. 173Q | PO18 |  |  | Milton | 229 |  |  | UNPAID | D.B. | 2023-09-14 |  | Emergency
23S-087 | P.S. 110K | PO18 | 89196 | 136078 | Joseph | 222 |  |  | UNPAID | D.B. | 2023-09-15
23S-088 | P.S. 116Q | PO18 |  |  | Milton | 63 | 2024-05-08 | 5116.55 | PAID | D.B. | 2023-09-21 |  | Emergency
23S-089 | P.S. 60Q | PO18 |  |  | Lukasz | 60 | 2024-04-02 | 3397.18 | PAID | D.B. | 2023-09-21 |  | Emergency
23S-090 | M465 | PO18 |  |  | Eman |  |  |  | Not Billed | D.B. |  |  | Emergency
23S-091 | P.S. 41Q | PO18 |  |  | Milton | 69 | 2024-05-13 | 3864.83 | PAID | D.B. |  |  | Emergency
23S-092 | P.S. 14R | PO18 |  |  | Sri | 65 | 2024-05-02 | 5413.73 | PAID | D.B. | 2023-09-29 |  | Emergency
23S-093 | P.S. 19K | CIP | 89478 | 128491 | J. Walsh | 163 |  |  | UNPAID | D.B. | 2023-09-22
23S-094 | P.S. 22M | PO18 |  |  | Rafal | 66 | 2024-05-15 | 2511.13 | PAID | D.B. | 2023-10-02 |  | Emergency
23S-095 | P.S. 115M | PO18 | 89597 | 137312 | Eman | 138 | 2025-01-23 | 6672.58 | PAID | D.B. | 2023-10-03 |  | 3rd Fl - Rm 315 Emergency
23S-096 | P.S. 57R | PO18 |  |  | Jesus | 238 |  |  | UNPAID | D.B. |  |  | Emergency
23S-097 | M475 | CIP |  |  | Jesus |  |  |  | Not Billed | D.B.
23S-098 | P.S. 50R | PO18 |  |  | Jesus |  |  |  | Not Billed | D.B. |  |  | Emergency
23S-099 | Q425 | PO18 | 89726 | 137379 | Milton | 74 | 2024-06-07 | 5378.1 | PAID | D.B. |  |  | Emergency
23S-100 | P.S. 81M | PO18 |  |  | Rafal | 143 | 2025-02-11 | 6575.51 | PAID | D.B. | 2023-08-23
23S-101 | P.S. 197M | PO18 |  |  | Eman | 139 | 2025-01-24 | 8303.85 | PAID | D.B. | 2023-10-12
23S-102 | P.S. 189Q | PO18 | 89542 | 137302 | Milton | 218 |  |  | UNPAID | D.B. | 2023-10-03
23S-103 | P.S. 165Q | PO18 | 88113 | 135375 | Milton |  |  |  | Not Billed | D.B. | 2023-10-16
23S-104 | P.S. 136K | PO18 | 89448 | 137124 | Scott | 128 | 2024-09-19 | 24419.64 | PAID | D.B. | 2023-10-24
23S-105 | P.S. 114K | CTF | 88538 | 133737 | Jesus |  |  |  | Not Billed | D.B. | 2023-10-24
23S-106 | P.S. 18K | PO18 | 89710 | 137371 | Walsh |  |  |  | Not Billed | D.B. | 2023-10-24
23S-107 | P.S. 26R | PO18 | 89785 | 137451 | Jesus | 122 | 2024-08-23 | 2523.58 | PAID | D.B. | 2023-10-26
23S-108 | P.S. 122Q | PO18 |  |  | Lukasz | 220 |  |  | UNPAID | D.B. | 2023-10-26 |  | Emergency
23S-109 | P.S. 55R | PO18 |  |  | Jesus | 216 |  |  | UNPAID | D.B. | 2023-10-27 |  | Emergency
23S-110 | P.S. 55K | PO18 | 89201 | 136080 | Al Palermo |  |  |  | Not Billed | D.B. | 2023-10-30
23S-111 | P.S. 85X | PO18 | 89844 | 137492 | ZB | 117 | 2024-09-12 | 7352.25 | PAID | D.B. | 2023-10-30
23S-112 | P.S 193Q | PO18 |  |  | Milton | 98 | 2024-07-05 | 5440.93 | PAID | D.B. |  |  | Emergency
23S-113 | M465 | PO18 |  |  | Eman | 101 | 2024-07-09 | 7865.63 | PAID | D.B. |  |  | Emergency
23S-114 | PS 75X | PO18 | 89840 | 137488 | Eman | 201 | 2025-06-23 | 47383.26 | PAID | D.B.
23S-115 | PS 30R | PO18 |  |  | Jesus | 70 | 2024-04-26 | 6029.25 | PAID | D.B. | 2023-11-18 |  | Emergency
23S-116 | R435 New Dorp HS | PO18 |  |  | Jesus | 182 | 2025-06-16 | 2346.04 | PAID | D.B. | 2023-11-26 |  | Emergency
23S-117 | PS 115M | PO18 |  |  | Eman |  |  |  | Not Billed | D.B. | 2023-11-29 |  | Emergency
23S-118 | P.S. 306K | CIP | 89334 | D021531 | Al Palermo |  |  |  | Not Billed | D.B. | 2023-09-18
23S-119 | M844 | PO18 |  |  | Jesus | 198 |  |  | UNPAID | D.B. | 2023-12-08 |  | Emergency
23S-120 | K224 | Safe Access | [6 empty] | Not Billed |  | 2023-02-04
23S-121 | K233 | Safe Access | [6 empty] | Not Billed |  | 2023-02-04
23S-122 | K244 | Safe Access | [6 empty] | Not Billed |  | 2023-12-11
23S-123 | K260 | Safe Access | [6 empty] | Not Billed |  | 2023-12-11
23S-124 | K273 | Safe Access | [6 empty] | Not Billed |  | 2023-12-12
23S-125 | K276 | Safe Access | [6 empty] | Not Billed |  | 2023-12-11
23S-126 | K279 | Safe Access | [6 empty] | Not Billed |  | 2023-12-11
23S-127 | R049 | PO 18 |  |  | Jesus |  |  |  | Not Billed | D.B. | 2023-12-13 |  | Emergency
23S-128 | M465 | PO18 |  |  | Eman |  |  |  | Not Billed | D.B. | 2023-12-18 |  | Emergency
23S-129 | K163 | LSP / CIP |  |  | Jesus |  |  |  | Not Billed | D.B. | 2023-12-07
23S-130 | K287 | Safe Access | [6 empty] | Not Billed
23S-131 | K250 | Safe Access | [6 empty] | Not Billed
23S-132 | P.S. 22R |  |  |  | Jesus |  |  |  | Not Billed | D.B.
23S-133 | P.S 61K | PO18 | 90221 | 138252 | Al | 78 | 2024-07-09 | 2731 | PAID | D.B. | 2023-12-27
23S-134 | P.S. 55 K | PO18 | 89203 | 136082 | Al | 239 |  |  | UNPAID | D.B. | 2023-12-05
23S-135 | K615 | PO18 | 90158 | 137997 | Al |  |  |  | Not Billed | D.B. | 2023-12-19
23S-136 | M128 | PO18 | 90120 | 137965 | Eman | 231 |  |  | UNPAID | D.B. | 2023-12-19
23S-137 | Q193 | PO18 | 88616 | 135640 | Milton |  |  |  | Not Billed | D.B. | 2023-08-14
23S-138 | X039 | PO18 | 89315 | 137057 | Eman | 168 |  |  | UNPAID | D.B. | 2023-09-19
23S-139 | [8 empty] | Not Billed
23S-140 | [8 empty] | Not Billed
24S-141 | [5 empty] | 183 |  |  | UNPAID
23S-142 | [8 empty] | Not Billed

## 2022 JOB LIST
SAI FILE NO. | PROJECT LOCATION | PROJECT DESCRIPTION | SCA SERVICE ID NO. | SCA PROJECT ID NO. | CONTACT PERSON | RFP No | DATE ON CHECK | AMOUNT RECEIVED | STATUS | SAI PROJECT MGR | DATE ASSIGNED | DATE COMPLETED | NOTE
22S-001 | [5 empty] | 4 | 2022-12-13 | 12189.08 | PAID
22S-002 | [5 empty] | 3 | 2022-11-09 | 38819.14 | PAID
22S-003 | [5 empty] | 1 | 2022-10-06 | 6453.9 | PAID
22S-004 | [5 empty] | 96 | 2024-07-05 | 5171.03 | PAID
22S-005 | [5 empty] | 21 | 2023-07-28 | 21825.8 | PAID
22S-006
22S-007
22S-008 | [5 empty] | 162 | 2025-06-06 | 9949.73 | PAID
22S-009
22S-010
22S-011 | [5 empty] | 151 | 2025-06-03 | 5589.53 | PAID
22S-012 | [5 empty] | 50 | 2023-12-11 | 20556.68 | PAID
22S-013 | [5 empty] | 42 | 2023-10-25 | 8661.09 | PAID
22S-014 | [5 empty] | 22 | 2023-07-31 | 7140.93 | PAID
22S-015 | [5 empty] | 12 | 2023-06-25 | 7579.36 | PAID
22S-016 | [5 empty] | 18 | 2023-07-12 | 9012.85 | PAID
22S-017 | [5 empty] | 20 | 2023-08-08 | 21497.37 | PAID
22S-018 | [5 empty] | 140 | 2025-01-23 | 19983.26 | PAID
22S-019 | [5 empty] | 13 | 2023-09-05 | 8548.59 | PAID
22S-020
22S-021 | [5 empty] | 16 | 2023-07-12 | 15635.03 | PAID
22S-022 | [5 empty] | 5 | 2023-02-09 | 3300.38 | PAID
22S-023 | [5 empty] | 45 | 2024-05-21 | 26283.31 | PAID
22S-024 | [5 empty] | 6 | 2023-03-08 | 6339.9 | PAID
22S-025 | [5 empty] | 116 | 2024-08-27 | 23786.87 | PAID
22S-026 | [5 empty] | 67 | 2024-05-29 | 7124.33 | PAID
22S-027 | [5 empty] | 80 | 2024-10-04 | 7902.2 | PAID
22S-028 | [5 empty] | 14 | 2023-07-11 | 6187.21 | PAID
22S-029
22S-030 | [5 empty] | 99 | 2024-07-08 | 8999.02 | PAID
22S-031
22S-032
22S-033 | [5 empty] | 148 | 2025-05-22 | 14183.93 | PAID
22S-034 | [5 empty] | 2 | 2022-10-06 | 29313.56 | PAID
22S-035 | [5 empty] | 232 |  |  | UNPAID
22S-036 | [5 empty] | 24 | 2023-09-22 | 11811.36 | PAID
22S-037 | [5 empty] | 17 | 2023-07-24 | 9715.23 | PAID
22S-038 | [5 empty] | 137 | 2024-12-30 | 32571.72 | PAID
22S-039 | [5 empty] | 192 |  |  | UNPAID
22S-040
22S-041
22S-042 | [5 empty] | 127 | 2024-10-07 | 16413.17 | PAID
22S-043 | [5 empty] | 48 | 2023-11-27 | 17824.18 | PAID
22S-044 | [5 empty] | 29 | 2023-07-25 | 12701.34 | PAID
22S-045 | [5 empty] | 108 | 2024-07-29 | 13333.61 | PAID
22S-046 | [5 empty] | 81 | 2024-07-15 | 6613.85 | PAID
22S-047 | [5 empty] | 41 | 2023-11-08 | 5954.03 | PAID
22S-048 | [5 empty] | 75 | 2024-05-10 | 5623.4 | PAID
22S-049 | [5 empty] | 82 | 2024-05-21 | 30284.62 | PAID
22S-050 | [5 empty] | 19 | 2023-07-20 | 25350.54 | PAID
22S-051 | [5 empty] | 171 | 2025-06-16 | 23934.9 | PAID
22S-052 | [5 empty] | 118 | 2024-08-30 | 4911.53 | PAID
22S-053 | [5 empty] | 23 | 2023-07-31 | 7033.25 | PAID
22S-054 | [5 empty] | 52 | 2024-04-15 | 11479.15 | PAID
22S-055 | [5 empty] | 15 | 2023-11-09 | 27095.76 | PAID
22S-056 | [5 empty] | 53 | 2024-05-08 | 15829.9 | PAID
22S-057 | [5 empty] | 43 | 2023-10-25 | 17026.88 | PAID
22S-058 | [5 empty] | 85 | 2024-06-13 | 4040.73 | PAID
22S-059 | [5 empty] | 172 | 2025-06-16 | 11726.56 | PAID
22S-060
22S-061 | [5 empty] | 34 | 2023-10-13 | 8454.45 | PAID
22S-062 | [5 empty] | 39 | 2023-08-04 | 4742.45 | PAID
22S-063 | [5 empty] | 76 | 2024-05-10 | 6509.07 | PAID
22S-064 | [5 empty] | 54 | 2024-05-08 | 6733.25 | PAID
22S-065 | [5 empty] | 40 | 2023-11-27 | 15915.63 | PAID
22S-066 | [5 empty] | 95 | 2024-07-08 | 11844.74 | PAID
22S-067
22S-068 | [5 empty] | 38 | 2023-09-11 | 16393.86 | PAID
22S-069 | [5 empty] | 86 | 2024-05-20 | 6607.2 | PAID
22S-070 | [5 empty] | 25 | 2023-08-04 | 12766 | PAID
22S-071 | [5 empty] | 93 | 2024-07-01 | 5505.39 | PAID
22S-072 | [5 empty] | 233 |  |  | UNPAID
22S-073 | [5 empty] | 227 |  |  | UNPAID
22S-074 | [5 empty] | 27 | 2023-07-18 | 5249.18 | PAID
22S-075 | [5 empty] | 197 |  |  | UNPAID
22S-076 | [5 empty] | 110 | 2024-07-12 | 26234.98 | PAID
22S-077 | [5 empty] | 121 | 2024-10-08 | 10543.6 | PAID
22S-078
22S-079
22S-080
22S-081 | [8 empty] | Not Billed
22S-082 | [5 empty] | 211 |  |  | UNPAID
22S-083 | [8 empty] | Not Billed
22S-084 | [5 empty] | 147 | 2025-05-13 | 2762.41 | PAID
22S-085 | [5 empty] | 97 | 2024-07-08 | 7813.38 | PAID
22S-086
22S-087
22S-088
22S-089
22S-090
22S-091
22S-092
22S-093
22S-094
22S-095
22S-096
22S-097
22S-098
22S-099
22S-100
22S-101
22S-102
22S-103
22S-104
22S-105
22S-106
22S-107
22S-108
22S-109
22S-110
22S-111
22S-112
22S-113
22S-114
22S-115
22S-116
22S-117
22S-118
22S-119
22S-120
22S-121
22S-122
22S-123
22S-124
22S-125
22S-126
22S-127
22S-128
22S-129
22S-130
22S-131
22S-132
22S-133
22S-134
22S-135
22S-136
22S-137
22S-138
22S-139
22S-140
22S-141
22S-142
22S-143
22S-144
22S-145
22S-146
22S-147
22S-148

## DATA DICTIONARY
CALCULATIONS IN "JOB LIST"
RFP No | IFERROR(
I removed "Not Billed", if empty | IF(INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
"",
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
""
)
AMOUNT RECEIVED | IFERROR(
I removed "Not Billed", if empty | IF(
OR(
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
INDEX('SAI MONTHLY STATUS'!W:W, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "UNPAID"
),
"",
INDEX('SAI MONTHLY STATUS'!S:S, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
""
)
DATE ON CHECK | IFERROR(
I removed "Not Billed", if empty | IF(
OR(
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
INDEX('SAI MONTHLY STATUS'!W:W, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "UNPAID"
),
"",
INDEX('SAI MONTHLY STATUS'!V:V, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
""
)
STATUS | IFERROR(
IF(
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
"Not Billed",
INDEX('SAI MONTHLY STATUS'!W:W, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
"Not Billed"
)
INITIAL PROMPT | I need a formula in excel for the following
I have 2 worksheets in one workbook, one sheet is called SAI MONTHLY STATUS, the other 2025 JOB LIST.
In MONTHLY STATUS column P is named "RFP No" (in JOB LIST 2025 column G is named "RFP No), if RFP No is empty in MONTHLY STATUS, indicate "Not Billed" in 2025 JOB LIST, otherwise if RFP No is not blank in MONTHLY STATUS then do the following:
Add the RFP No listed in MONTHLY STATUS to 2025 JOB LIST
In MONTHLY STATUS column T is called "Amount Received", I want the amount that is in that column to appear in 2025 JOB LIST column H is also named "Amount Received".
Similarly, I have a column in MONTHLY STATUS (column V) and 2025 JOB LIST (column G) named "Date on Check" in which I want to be able to see the date that is listed in MONTHLY STATUS "Date on Check" to appear in 2025 JOB LIST "Date on Check"
If RFP No is empty, indicated "Not Billed"
The unique identifier is "SAI FILE NO" which is column A in both sheets
RESPONSE | Column Name | Sheet | Column | Use in Formula
| SAI FILE NO | Both | A | Lookup key
| RFP No | SAI MONTHLY STATUS | P | Column 16
| Amount Received | SAI MONTHLY STATUS | T | Column 20
| Date on Check | SAI MONTHLY STATUS | V | Column 22
🟡 1. “RFP No” — Column G in 2025 JOB LIST
IFERROR(
IF(INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
"Not Billed",
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
"Not Billed"
)
🟢 2. “Amount Received” — Column H in 2025 JOB LIST
IFERROR(
IF(INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
"Not Billed",
INDEX('SAI MONTHLY STATUS'!T:T, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
"Not Billed"
)
🔵 3. “Date on Check” — Column I in 2025 JOB LIST
IFERROR(
IF(INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
"Not Billed",
INDEX('SAI MONTHLY STATUS'!V:V, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
"Not Billed"
)
✅ Tips
Format Column I ("Date on Check") as Date.
These formulas will return "Not Billed" if:
SAI FILE NO is not found in the SAI MONTHLY STATUS sheet
Or if the "RFP No" for that row is blank
UPDATED PROMPT | Ok, so I have another issue. RFP No may have a number but it may be unpaid. If that is the case then Amount Received is a negative number and Date on Check is empty and will give an incorrect date.
Column R in MONTHLY STATUS is named "Amount Invoiced (RFP)" which show the amount that has been invoiced, column W in MONTHLY STATUS indicates PAID or UNPAID. Can you help me
Yes! Thanks for that clarification—very helpful.
🔄 Updated Goal:
If a job has an RFP No, but it’s UNPAID, we should:
Still show the RFP No
Leave Amount Received and Date on Check blank
But we can optionally show Amount Invoiced if you want
Here’s how to fix the formulas based on your updated rules. We’ll add logic to check:
W = "UNPAID" → leave Amount Received and Date on Check blank
W = "PAID" → pull actual values
If RFP No is blank → treat as Not Billed
✅ 1. Column G – “RFP No”
Keep this the same (no change):
IFERROR(
IF(INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
"Not Billed",
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
"Not Billed"
)
💰 2. Column H – “Amount Received”
Update it to account for UNPAID status:
IFERROR(
IF(
OR(
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
INDEX('SAI MONTHLY STATUS'!W:W, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "UNPAID"
),
"",
INDEX('SAI MONTHLY STATUS'!T:T, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
""
)
📅 3. Column I – “Date on Check”
Same idea—leave blank if UNPAID or RFP No is blank:
IFERROR(
IF(
OR(
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
INDEX('SAI MONTHLY STATUS'!W:W, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "UNPAID"
),
"",
INDEX('SAI MONTHLY STATUS'!V:V, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
""
)
🧾 (Optional) Column – “Amount Invoiced (RFP)” if you want it:
This one shows the amount that was invoiced, even if unpaid:
IFERROR(
INDEX('SAI MONTHLY STATUS'!R:R, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)),
""
)
Would you like a column for "Status" that just shows "PAID" / "UNPAID" / "Not Billed" based on the same rules?
Great! Here's how you can create a Status column in your 2025 JOB LIST sheet to clearly show:
"Not Billed" if RFP No is blank
"UNPAID" if RFP No exists but the status in column W of SAI MONTHLY STATUS is "UNPAID"
"PAID" if the status is "PAID" and RFP No is present
🟦 Status Column Formula
Assume this is going in Column J of 2025 JOB LIST, starting in cell J2:
IFERROR(
IF(
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
"Not Billed",
INDEX('SAI MONTHLY STATUS'!W:W, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
"Not Billed"
)
✅ What it Does:
| RFP No | Status in SAI MONTHLY STATUS!W | Output
| Empty | (doesn’t matter) | Not Billed
| Filled | UNPAID | UNPAID
| Filled | PAID | PAID
| (File No not found) | — | Not Billed
Let me know if you'd like a conditional formatting rule to color code these too!
🔐 Safe version of “Date on Check” formula
IF(
OR(
INDEX('SAI MONTHLY STATUS'!P:P, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "",
INDEX('SAI MONTHLY STATUS'!W:W, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0)) = "UNPAID"
),
"",
INDEX('SAI MONTHLY STATUS'!V:V, MATCH(A2, 'SAI MONTHLY STATUS'!A:A, 0))
),
""
),
""
)
✅ This Ensures:
The SAI FILE NO must exist in 'SAI MONTHLY STATUS'
If it doesn't, the formula returns nothing
If it does exist, it checks if it's PAID before showing the check date